# Team 11 - daily log of activities, Kaabong District

Team: Mworozi Davis, Nalukwata Shadia. Supervisor: Kassim Luminsa.

# 2026-08-27

Local government covered: Kaabong District.

| Researcher | What was covered | Photographs |
| --- | --- | --- |
| Mworozi Davis | Sidok Seed Secondary School, still a building site, and the boxed ICT standing in it; the buildings schedule of the toolkit filled in by hand and the district's two delivery notes and price schedule obtained | 37 |
| Nalukwata Shadia | Nothing recorded for this district on this day | 0 |

37 photographs on 2026-08-27, of which 36 are at the school and 1 in the town. One facility was verified on this day, Sidok Seed Secondary School, by its own register filled in on site. The register carries the buildings only: its furniture and ICT schedules were left blank and the discussion guide was not answered.