# Namwaya HC III - facility report

# 1. Identification

| Facility | Namwaya HC III |
| --- | --- |
| Named on the programme list | Namwaya HC II |
| Type | Health centre |
| Local government | Tororo District |
| Region / sub-region | Eastern / Bukedi |
| Date of visit | 2026-08-29 |
| Team members present | Kayongo Tonny, Lydia Nakiganda |
| Informant interviewed | None recorded |
| Supervisor | Kassim Luminsa |
| Supervisor's contact | +256 702 806116 |
| Date of submission |  |

# 2. Entry

The team reached this facility on 29 August. A hand-filled register naming Namwaya HC III is on file together with 142 photographs. Nobody is named as having received the team.

# 3. Condition and status

The four things the exercise exists to establish. Only what was established on site appears here; the rest is marked as not reported, not guessed.

| Dimension | What was established on site |
| --- | --- |
| Ownership | Not reported. |
| Functionality | Established on the hand-filled register, mostly good condition with several lines marked not seen. |
| Usage / performance | Partly established. The informant says assets are new, service delivery has improved and staff welfare is better, but the facility is not fenced. |
| Location | Recorded on the register and shown in photographs of the wards, store, laboratory and water tanks. |

# 4. Supplied against found

The hand-filled register is the found side and nothing was counted on the day.

# 5. Engraving and identification

Most lines read not engraved on the register.

# 6. Obsolete, unserviceable or for disposal

Nothing on the register was named for disposal.

# 7. Operation and maintenance

The discussion guide was answered. The facility holds a record, reports no breakdowns yet, and asks for fencing.

# 8. Queries

Nothing here was counted on the day.

Ownership was not established.

The programme list carries level II and the signboard reads level III.