UGIFT ASSET VERIFICATION REPORT   FOR KASESE, BUNYANGABU, KAMWENGE AND KITAGWENDA;

Date of visit; From 24 to 31 of August
INTRODUCTION.
KASESE DISTRICT

Project/Facility for district;

- Rukoki Health General Hospital

- Kabingo Health Centre III

- Buhuhira Health Centre III

- Bwesumbu Health Centre III

- Nyabirungo Health Centre III

- Nyakimasa Health Centre III

- Kyempara Health Centre III

- Railway Health Centre III

- Bwesumbu Seed School

BUNYANGABU DISTRICT

- Rubona Health Centre III

- Kateebwa Health Centre III

- Kabahango Health Centre III

- Nsuura Seed School

- Katugunda Seed School

- Kiyombya Seed school

KAMWENGWE DISTRICT

- KABINGO Health Centre III

- KABAMBIRO Health Centre III

BWIIZI Seed School

KITAGWENDA DISTRICT

Kanara HCIII and Kanara Seed Secondary School.

Verification team; Nalunkuma Faridah and Kihumuro Jenifer

A field verification exercise was conducted to verify assets acquired and/or constructed under the (UGIFT) program. The exercise aimed at establishing the physical existence, location, condition, functionality, and utilization of the assets and ensuring that the assets are properly recorded and accounted for.

Process/ Methodology.

The exercise involved physical inspection of the assets at the respective project sites and consultation with the responsible officers and facility managers, at first we visited Districts where the sites are, We met with the Community Administrative Officers (CAOs) of respective districts who then introduced us to the DEO’s and the DHO’s and CFOs of respective districts, we asked for some documents concerning the sites we visited, we managed to get some in some districts and others we found them the schools and health facilities.

The specific objectives of the exercise were to:

- Physically verify UGIFT-funded assets at the respective facilities.

- Confirm the quantity, description, location, and ownership of the assets.

- Assess the physical condition and functionality of the assets.

- Establish whether the assets are being utilized for their intended purpose.

- Compare the assets physically found on site with the available records and asset registers.

- Identify assets that are functional and those that no longer functional, how they are taken care of in case of damage and if there are records in place that’s Asset registry books for UGIFT project.

The verification exercise was carried out through physical inspection and observation of the assets at the respective project sites. The team also reviewed available documents, including asset registers, procurement records, delivery notes, and other relevant project documentation.

Major observations.

- Condition: The condition of the Asset and Equipment was good in most of the facilities visited due to the fact that some were just completed and others upgrading from screed to Terrazzo, others constructions were going on Especially for Seed schools, most Equipment was still boxed and kept in the store.

- Utilization: Most of the Equipment was not in use due to the fact that some facilities received them from 2024/2025and 2026, so they were still using old equipment and other facilities were still using Equipment given to them by other Funders and others were using for UGIFT.

- Asset identification: most of the assets and Equipment had no Engravement numbers, and the buildings are just a few facilities that engraved their Equipment, even some Buildings have no names and are not yet commissioned.

- Record keeping: Almost all facilities had records in place, those are Asset registers, however these registers combined all equipment given out to them. So not specifically for UGIFT as a project.

- Maintenance and repair: All facilities had a small budget that is (PHC) Primary Heath Care facilitated under the government of Uganda given to all facilities for minor repairs of the Equipment.

The following challenges were noted during the field verification exercise:

- Since it was a financial year, most of the in-charges were change and transferred to different locations, there just a few of them who left proper documentation, the new people in charge had no idea about who funded the new Assets and Equipment.

- Most of the Equipment were not engraved or labelled yet there were other items similar to those delivered by UGIFT from other Projects or Funders.

- Limited documentation, this affected our way of doing work, some in charges misplaced the delivery notes, and others didn’t have anything in place, so we had to use information availed from the districts.

- Some facilities heads and workers didn’t know how to use some Equipment given to them, they kept them in store, so they asked UGIFT to always organize trainings to equip them with knowledge on how to use and install them.

- Some buildings have no facility names written on them and some are not yet commissioned, this limits the users a sense of belonging and ownership.

- We found many facilities keeping the equipment in store due to the fact that some were still under upgrade from screed to Terezzo, others like Kabingo HCIII  in Kasese is a hard out to reach area, so they had to relocate the facility  from Kabingo village to nearby village, they received Equipment from 2021 but they have been keeping it due to construction process that has been going on, and also items reaching them is really hard since there is no any proper means of transport that can reach their Area. We also failed as a team to reach them and we had to call the in-charge for information.

- The facilities in Kasese were hard to reach areas because of Terrains, facilities like Bwesumbu HCIII, Bwesumbu Seed School, Buhuhira, and Kabingo, we request concerned staff to look in to the issue of proper means of transport putting into consideration lives of Researchers especially in some areas where taxis can’t reach.

- Some DHOs and CFOs didn’t give us proper documentation and others didn’t give us at all, they were disorganized and others were on pressure because of the Anticorruption team that had visited them.

- Most of the CAOs of districts were not aware of our coming to their districts so we found a hard times explaining ourselves and being attended and we had to revisit them to seek for there consent yet the program team needed the work and was not willing to incur more costs.

RECOMADATIONS.

- The UGIFT project should get visiting books and asset registry books to the facilities for UGIFT only, this will help in simplifying the verification exercise and proper records keeping.

- Facilities should be encouraged to put label or engrave the Assets and Equipment for UgIFT as this will help in ease identification.

- Equipment requiring repairs and maintenance should be attended to promptly since they are expensive in buying and also DHOs doing thorough monitoring visits to educate in-charges and nurses in proper handling of these equipment and Assets.

- Facility heads and asset custodians should be sensitized on proper asset management and accountability.

In conclusion

The field verification exercise was successfully conducted and provided an opportunity to establish the current status of UGIFT-funded assets at the facilities visited. The exercise confirmed the physical existence and utilization of most of the assets, while also identifying areas requiring improvement in asset tagging, record keeping, maintenance, and accountability.

The identified discrepancies and observations should be addressed by the responsible officers, and the verified information should be incorporated into the relevant asset registers for purposes of proper management, accountability, and future reference.

## Signature

Name: 	Nalunkuma Faridah.

Date: 	10/10/2026