Over page

List of tables

List of acronyms

Executive Summary

Introduction and Background

Introduction

This Report has been prepared in light of the consultancy to verify and record assets under the UgIFT programme by Sejjaaka Kaawaase & Co Certified Public Accountants. The report presents the verification findings in line the IFMIS requirements.

Background to the verification exercise

The UgIFT programme implementation came to an end on 31st December 2025. As part of the programme closure activities, MoFPED through RCU, carried out an end of programme asset verification exercise to take stock of the assets procured under the programme to help put in place plans to hand them over to government for sustainability purposes. The exercise was conducted by Sejjaaka Kaawaase & Co Certified Public Accountants. It was conducted at two levels namely; 1) National level Ministries, Departments and Agencies (MDAs) of Government; 2) all the government secondary schools in underserved sub-counties; and health facilities upgrade from HCII to HCIII levels distributed across the country.  At the National level, the verification focused on retooling assets including ICT equipment such as Computers, Tablets and Photocopiers; Furniture (tables, chairs, desks, stools, shelves, wardrobes and cupboards); Motorcycles and Motor vehicles. The verification involved; Verification of the Asset’s Records, Physical and Functional Verification; Data Consolidation and Recommendations.

At the central government level, the following MDAs that received UgIFT assets were visited for asset verification by the verification teams appointed by the Consultant.

- Ministry of Works and transport (MoWT)

- Ministry of Education and Sports (MoES)

- Ministry of Agriculture Animal Industries and Fisheries (MAAIF)

- Ministry of Health (MoH)

- Office of the Prime Minister

- Ministry of Water and Environment (MoLG)

- Ministry of Gender, Labour and Social Development (MoGLSD)

- National Environment Management Authority (NEMA)

- Public Procument and Disposal of Assets Authority (PPDA)

- Office of the Auditor General (OAG)

- Ministry of Lands, Housing and Urban Development (MoLH&UD)

- Ministry of Local Government (MoLG)

- Ministry of Finance, Planning and Economic Development (MoFPED)

- Local Gvoernment Finance Commission

- Ministry of Public Service (MoPS)

At the Local Government level, all the Districts, Cities and Municipalities were also visited and the assets verified.

Objectives of the Assignment

The objective of the assignment was to undertake verification and recording of all assets acquired under the UgIFT Programme. Specifically, the assignment;

- Identified and verified the existence of the assets.

- Verified the assets condition and status: specifically, the condition on functionality, usage/performance and location among others

- Assessed financial management aspects: residual value of the investments/hardware/tools for purposes of financial reporting for project closure

- Listed the assets that are obsolete, unserviceable and require disposal

- Developed a computerized database of the investment/hardware/tools to facilitate recording of new deployed assets/investments

- Undertook PFM Assessment on Asset Management practices (including sustainability, Operations and Maintenance) of the UgIFT implementing LGs

Scope of work

The assignment covered all selected UgIFT beneficiary institutions distributed across the country and involved the following tasks.

- Verification of the Asset’s Records

- Physical and Functional Verification

- Data Consolidation and Recommendations

- IFMIS Asset Register Update, Integration, and Migration

- PFM Assessment of the UgIFT Asset Management Practices

Project Context/design architecture

The Uganda Intergovernmental Fiscal Transfer (UgIFT) Programme is a government programme implemented through a Program-for-Results (PforR), Launched and aligned with the broader IGFT Reform Programme (2015). UgIFT 1.0 began with US$200 million in FY2017/18, supporting Education and Health, and was later expanded through additional financing of US$300 million, including US$240 million in credit and US$60 million in grants. US$50 million was from the IDA Refugee Support Window, expanding beyond Education and Health to water and Environment and Agriculture (micro-scale irrigation) making the overall funding total of US$500 million.

In 2020, the Intergovernmental Fiscal Transfer Reform Programme (IGFT RP) was revised to align with the Third National Development Plan (NDP III-2020/21 to 2024/25), and to directly contribute to Four (04) NDPIII Programmes i.e. Human Capital Development, Public Sector Transformation, Natural Resources, Environment, Climate change, Land and Water Management, and Development Plan Implementation.

The UgIFT Programme had four components aimed at strengthening the intergovernmental fiscal transfer system while supporting investments in service delivery infrastructure. These are;

Component 1: Reform of the Intergovernmental Fiscal Transfer System. This supported the design and implementation of a reformed fiscal transfer framework based on objective and transparent allocation criteria. This resulted into the introduction of formula-based grants - Revised allocation formulas reflecting population, infrastructure gaps, and service delivery needs.

Component 2: Education Infrastructure Development.

This component financed the construction and upgrading of education facilities, particularly government secondary schools in underserved sub-counties. This involved Construction of new secondary schools - Classrooms, laboratories, administration blocks, sanitation facilities, and teachers’ houses in the different local governments across the country.

Component 3: Health Infrastructure Development.

This supported investments in health facilities to improve access to primary health care services at the local level. The major outputs under the component were construction and upgrading of health centers - Staff accommodation and sanitation facilities.

Component 4: Local Government Performance and Institutional Strengthening.

This aimed at strengthening Local Government capacity in planning, budgeting, procurement, and infrastructure management. Under this component, Annual Local Government Performance Assessments have been undertaken across the 176 Local Governments, Capacity building and technical support strengthened monitoring and reporting systems across the Local governments. The Programme was implemented through a clearly defined results framework that connected actions and incentives across three levels of government to strengthen service delivery outcomes. The programme came to an end in December 2025 and had accomplished the following outputs under the different components.

- Budget Support

- Education: 196 of 259 Seed Schools are complete of which 189 are operational

- Health: 354 of 373 health facility upgrades/new constructions (HC II to HC III) are complete

- Water and Environment: 758 - piped water systems, 5,398- point water sources, 7,082 water supply systems rehabilitated, 325 designs completed, and 256 sanitation facilities in

- Agriculture (Micro-scale Irrigation): Over 6,235 irrigation systems were installed (4,843 hectares under irrigation), 632 irrigation demonstration sites in 135 LGs set up,

- Refugee intervention: 51 primary schools and 35 health facilities in refugee hosting districts (RHD) were transitioned and integrated into the LG service

- Blood banks: Regional Blood Banks in Arua and Hoima were completed, commissioned while Soroti Regional Blood Bank was rehabilitated

- Under grant management

Assets for institutional strengthening and retooling including ICT equipment and; motorvehicles and motor cycles. The Ministry of Finance planning and Economic development (MoFPED) through PFM Coordination Unit (RCU) manages the Government of Uganda counterpart funding of the programme to support the grant management component of the UgIFT programme. The grant management supports in financing of Central Government actions intended to achieve programme objectives and disbursement linked indicators (DLIs). To this end, MoFPED through RCU supported MDAs to acquire different assets meant to support programme implementation.

UgIFT Proramme Objectives

The Overall development objective of the UgIFT Program was to: “Improve the adequacy, equity, and effectiveness of financing and the oversight, management, and delivery of Local Government services in Education, Health, Water and Environment, and Agriculture (micro-scale irrigation), including refugees and their host communities”.

Specifically, the Program sought to:

- Increase the adequacy and predictability of fiscal transfers to Local Governments for service delivery;

- Improve the equity and transparency of allocation mechanisms through the introduction of formula-based transfers;

- Strengthen performance incentives and accountability systems for Local Governments; and

- Expand access to quality education and health infrastructure, particularly in underserved areas.

Approach and methodology

This verification exercise conducted using a participatory and consultative process and implemented in three interlinked phases: Preparatory and inception phase, Data collection phase and the report writing phase.

## Inception and preparation phase

- Kick Off /entry meeting

Upon completion of the contracting, the assignment commenced with an entry meeting on 29th May 2026. The meeting discussed the execution of the assignment. Key issues discussed during the meeting included the scope of the assignment, the approach and methodology, key deliverables and the timelines attached to the assignment. The client also provided reference material to the consultant including;

- UgIFT Consolidated Fixed Assets Register FY 2024/25

- UgIFT Consolidated Fixed Assets Register FY 2023/24

- UgIFT Consolidated Fixed Assets Register FY 2022/23

- UgIFT Consolidated Fixed Assets Register FY 2021/22

- UgIFT Consolidated Fixed Assets Register FY 2020/21

Additionally, the local government stakeholders to be engaged were identified, including the accounting officers, district health and education officers, the district finance and administration offices, the seed school head teachers, and the health centre in-charges.

- Review of Relevant Documents

Based on the guidance from the inception meeting, the consultant embarked on a review of the provided literature. The consultant compiled secondary information necessary for the actual verification including the distribution of the assets to be verified at both the MDAs and LGs levels. This supported the planning and deployment of verification teams to the respective MDAs/LGs for data collection.

- Development of Data Collection Tools

The review of documents also facilitated the development of the data collection instruments needed in the execution of the assignment. The instruments include:

- Asset verification tool: The consultant developed an asset register template which was used to collect the data from the MDAs and the facilities in LGs. The designed verification tool captured the following asset data details:

  - Equipment/ Item

  - Department

  - Asset Number

  - Life in Months

  - Tag Number (engrave no.)

  - Asset description

  - Date Of Purchase

  - Date Placed in Service

  - Recoverable cost

  - Cost of Asset

  - Acc Depreciation Cost

  - Net Book Value

  - Ytd Depreciation

  - Equipment status

  - Remarks

- Pilot test verification

The verification team conducted a pilot visit to establish and ascertain how these assets are registered. The pilot was undertaken in Wakiso District Local government and verification done at Buloba Health centre III and Sumbwe seed school. This exercise helped in refining the data collection tool and the deployment plan based on experience gained from the pilot.

- Key informant interview: The consultant also developed a key informant interview guide on the asset management practices including operation and maintenance, asset functionality and value. These were used to generate information relating to asset use and value during the exercise.

- Preparation of Inception Report

This inception report was prepared by the consultant detailing; the methodology for undertaking the assignment, deployment plan, quality assurance measures, and the work plan and the team deployment plan with tasks to be performed.

## Data collection Phase/ asset Verification process:

The Data collection phase involved collection of information from the MDAs and Local Governments where the facilities and equipment are allocated. The consultant deployed a field verification team composed of 80 Research Assistants (RAs) to cover all the 176 local governments, 6 supervisors and a team leader. 13 MDAs at National level were visited by the supervisors and the teal leader. The field data collection at the LG level was completed in 10 working days. It also took 10 working days for data collection at MDA level including back and forth visits to the different MDAs.

- Training of the verification team.

The field verification team underwent a two days training session to ensure consistent understanding of the assignment and the tool before deployment to the field. The training conducted by the senior technical persons from SK&CO Certified Public Accountants took place from 20th to 21st August 2026.

- Verification at National Level.

The National level Physical verification exercise started on24th July 2026. This covered 15 MDAs including; Ministry of Works and transport (MoWT), Ministry of Education and Sports (MoES), Ministry of Agriculture Animal Industries and Fisheries (MAAIF), Ministry of Health (MoH), Office of the Prime Minister (OPM), Ministry of Water and Environment (MoWE), Ministry of Gender, Labour and Social Development (MoGLSD), Local Government Finance Commission, National Environment Management Authority (NEMA), Public Procurement and Disposal of Assets Authority (PPDA),Office of the Auditor General (OAG), Ministry of Public Service (MoPs), Ministry of lands housing and Urban Development, Ministry of Local Government (MoLG),and Ministry of Finance, Planning and Economic Development (MoFPED). The verification progress for each of the MDAs is indicated in Annex 1 of the report.

- Notification of Local governments

Before actual visits to the LG, the coordination team, from RCU sent out notification to the Local Governments through formal introductory letters. This was followed by the team from SK&CO Certified Public Accountants through telephone calls to notify each of the LGs about the exact date of the verification exercise.

- Verification at the Local Government level

Thirty-three teams each composed of 2-3 persons were deployed to cover a cluster of LGs in each region. The actual verification exercise at the local government level started on 24th August 2026 and concluded on 7th September 2026. It involved the following activities.

- Courtesy call to the Local Government leadership:

On entry into the District/Municipality, the team visited the office of the Accounting Officer, for an introduction and to present the verification work itinerary. The Accounting Officer guided the team on the responsible officers to coordinate the exercise. This served as the initial step for the exercise at the LG level.

- Desk review at Local Government level:

The verification process in each LG followed a consultative approach. It involved a review of program-related documents, including the UgFT asset delivery records and asset register (where it existed).  It also involved consultative discussions with the technical officers regarding the assets and the asset management practices.

- Visit to the facilities

After the consultation and review of the reports with the LG officials, the team carried out a physical verification of the assets. This involved office assets of fixed nature provided to support the programs in the LGs. In the Local governments, the team also took photographic evidence to clearly show status of the assets as supporting evidence during the field visits. This enabled physical and functional verification. However, the physical verification exercise did not include small office equipment like Stapling machines or punching machines and small school laboratory equipment that are disposable.

- Functionality assessment

While at the LG/ facility, the team engaged the administrators/management of the facility to discuss functionality aspects relating to the objectives of establishing the facility, and enlist any operational and maintenance challenges among others.

Itinerary

The consultants observed that the verification is a formal assignment that engaged different stakeholders, a detailed schedule of events followed by the verification Teams is presented below;

Table …..: Itinerary in the Local Government

| Day | Activity |
| --- | --- |
| 1 | - Arrival and signing in the visitor’s book by verification team at the Accounting Officer/CAO’s Office |
|  | - Entry meeting with finance and administration |
|  | - Desk based review at of UgIFT documents and asset register |
| 2 | - Physical verification of identified assets at Office level at MDA/LG offices and in the facilities (Health centres and schools) |
|  | - Service level interviews for functionality, maintenance and sustainability at MDA/LG/ facility level |
|  | - Follow ups and filling available gaps and Debrief and Finalize verification |

## Reporting phase

- Data Consolidation, Analysis & Reconciliation

After the data collection, the consultant consolidated all collected data based on their categories. The objective for this task was to clean, validate and analyze all acquired data.  This process involved.

- Data Cleaning & Validation based on outlier identification and correction

- Matching verified physical assets with existing asset registers.

- Documenting all discrepancies: missing assets, unrecorded assets, misclassified assets.

The cleaned data especially regarding asset register was consolidated into a comprehensive data base as part of the deliverables for the assignment.

- Triangulation and analysis of data

The consultant analysed the data to generate both statistical and financial reports.

- The statistical analysis generated information regarding the status of the UgIFT assets including the status of management, operation and maintenance, completed and functionality among others.

- Financial analysis provided information regarding Financial Valuation. This included indication of current value and remaining useful life for each asset., Assessing residual value based on the depreciation methods and market conditions.

- Generation of an IFMIS Ready Asset Register

The objective of this task was to prepare all verified asset data into the IFMIS structure, ensuring accuracy and completeness.

- Production and Presentation process report

The consultant prepared a process report of the verification exercise that comprised of Asset Management Practices, challenges and recommendations This was presented together with the different deliverables to the ministry team from Resource Enhancement and Accountability Programme (REAP) for review and feedback.

- Finalisation of the assignment

Upon presentation and discussion of the draft report, the Consultant addressed comments and suggestions from the meeting with the ministry team from Resource Enhancement and Accountability Programme (REAP) and produced the final report. A final report, together with the requite deliverables was submitted to Resource Enhancement and Accountability Programme (REAP).

## Quality assurance

To ensure quality data is collected from the verification exercise, a three-layered quality assurance framework was established as indicated below.

a)	Supervision by the central technical team

The Field work Coordinator and the field team leader made spot checks on the verification team, to ascertain the field work activities, challenges and constraints. Any issues arising were addressed immediately to ensure smooth implementation of the assignment.

b)	Regional Team leader supervision

The country was divided into 6 regions to ease management of data collection. Each region was assigned a regional supervisor who ensured that the data collected was in line with the set protocol (register requirements). These made daily checks to the teams under their jurisdiction ensuring that mistakes are corrected while the team was in the field. The regional supervisor ensured that each researcher submitted a daily log of activities in terms of LGs covered and the assets verified. All inappropriately filled registers/ incomplete entries were clarified and the respective team member was asked to follow-up for completion. The regional supervisors kept a copy of each team member’s register to validate all tools shared for any gaps or mismatches that can be flagged to the teams while at source.  The regional supervisors consulted with the team leader and field coordinator on any clarifications that was needed at any time during the course of the field work.

c)	Quality assurance during Data capture

The verification team validated the asset registers at two levels. Before going to the respective entities, the team provided a copy of the entity register to make preliminary review of the records, identify any gaps and any mismatches. This was validated with the register at the entity during the entry and desk review to identify and bridge any gaps and discrepancies. The verification team members also interacted with the responsible entity officers while capturing the data.

Findings

This section presents detailed results  (table…..) for each of the MDAs on which the verification was conducted, namely; 1) Ministry of Works and transport (MoWT), 2)Ministry of Education and Sports (MoES), 3)Ministry of Agriculture Animal Industries and Fisheries (MAAIF), 4)Ministry of Health (MoH), 5)	Office of the Prime Minister, 6)	Ministry of Water and Environment (MoLG), 7)Ministry of Gender, Labour and Social Development (MoGLSD), 8)National Environment Management Authority (NEMA), 9)Public Procument and Disposal of Assets Authority (PPDA), 10)	Office of the Auditor General (OAG), 11)	Ministry of Lands, Housing and Urban Development (MoH&UD), 12)Ministry of Local Government(MoLG), and 13)Ministry of Finance, Planning and Economic Development (MoFPED).

Table…. National Level (MDAs)

| MDA | Asset Category | QTY | Total Capital Cost (UGX) | Accumulated Depreciation (UGX) | Net Book Value (UGX) | Portfolio Health / Status |
| --- | --- | --- | --- | --- | --- | --- |
| MOFPED | Vehicles |  |  |  |  |  |
|  | Laptops |  |  |  |  |  |
|  | Printers |  |  |  |  |  |
|  | Desktop Computers |  |  |  |  |  |
|  | Projectors |  |  |  |  |  |
|  | Furniture |  |  |  |  |  |
|  | UPS Systems |  |  |  |  |  |
|  | Digital Phones |  |  |  |  |  |
|  | Paper Shredders |  |  |  |  |  |
|  | Water Dispensers |  |  |  |  |  |
|  | Accessories |  |  |  |  |  |
|  | Total value |  |  |  |  |  |
| MoWE |  |  |  |  |  |  |
| OAG |  |  |  |  |  |  |
| OPM |  |  |  |  |  |  |
| MoWT |  |  |  |  |  |  |
| MoES |  |  |  |  |  |  |
| MAAIF |  |  |  |  |  |  |
| MoH |  |  |  |  |  |  |
| MOGLSD |  |  |  |  |  |  |
| NEMA |  |  |  |  |  |  |
| PPDA |  |  |  |  |  |  |
| MoLG |  |  |  |  |  |  |
| MoLHUD |  |  |  |  |  |  |
| Overall Total Value |  |  |  |  |  |  |

Local government level

This section presents a list of assets acquired through the UgIFT program. It presents the status and value of the different assets in health facilities and schools. These are presented at Local government level by category (Buildings, Furniture, Vehicles/motorcycles and ICT).

Assets for Schools

| Asset Category | QTY | Total Capital Cost (UGX) | Accumulated Depreciation (UGX) | Net Book Value (UGX) | Portfolio Health / Status |
| --- | --- | --- | --- | --- | --- |
| Printers |  |  |  |  |  |
| Desktop Computers |  |  |  |  |  |
| CCTV cameras |  |  |  |  |  |
| Projectors |  |  |  |  |  |
| Airconditioners |  |  |  |  |  |
| Servers |  |  |  |  |  |
| Desks |  |  |  |  |  |
| Office Chairs |  |  |  |  |  |
| Tables |  |  |  |  |  |
| Stools |  |  |  |  |  |
| Cupboards |  |  |  |  |  |
| Book shelves |  |  |  |  |  |
| Non-Residential buildings |  |  |  |  |  |
| Residential buildings |  |  |  |  |  |
| Kitchen |  |  |  |  |  |
| Water tanks |  |  |  |  |  |
| Toilets |  |  |  |  |  |
| Pit latrines |  |  |  |  |  |
| Fences |  |  |  |  |  |
| Total value |  |  |  |  |  |

Assets for Health Facilities

| Asset Category | Total Capital Cost (UGX) | Accumulated Depreciation (UGX) | Net Book Value (UGX) | Portfolio Health / Status |
| --- | --- | --- | --- | --- |
| B.P. Machine, Digital |  |  |  |  |
| B.P. Machine (Aneroid wall mounted) |  |  |  |  |
| Autoclave 20 Liters., Duo Operated |  |  |  |  |
| Bowl, Kick |  |  |  |  |
| Bowl Stand |  |  |  |  |
| Counting chamber Neubauer- Improved |  |  |  |  |
| Cupboard Steel, Lockable |  |  |  |  |
| Drip Stand |  |  |  |  |
| ESR Stand |  |  |  |  |
| Examination Couch |  |  |  |  |
| Examination light,LED |  |  |  |  |
| Glucometer |  |  |  |  |
| Haemoglobin Meter, Digital |  |  |  |  |
| Height Meter |  |  |  |  |
| Instrument Trolley |  |  |  |  |
| Microscope Binocular |  |  |  |  |
| Otoscope |  |  |  |  |
| Patient Screen |  |  |  |  |
| Patient Trolley |  |  |  |  |
| Refrigerator, Basic |  |  |  |  |
| Stethoscope |  |  |  |  |
| Stop Watch |  |  |  |  |
| Stretcher |  |  |  |  |
| Stove, Gas |  |  |  |  |
| Weighing Scale with Height Meter, Adult |  |  |  |  |
| Weighing Scale, Infant |  |  |  |  |
| Weighing Scale, Toddler |  |  |  |  |
| Wheel Chair |  |  |  |  |
| Audio Visual Equipment |  |  |  |  |
| Medical Waste Bin |  |  |  |  |
| Wall Clock |  |  |  |  |
| Diagnostic Equipment Set for MCH |  |  |  |  |
| Diagnostic Equipment Set for OPD |  |  |  |  |
| Glassware Set, Laboratory, Basic |  |  |  |  |
| Hollow Ware Set, Treatment |  |  |  |  |
| Instrument Set, Dressing |  |  |  |  |
| Instrument Set, Basic ENT |  |  |  |  |
| Instrument Set, Suture |  |  |  |  |
| Pulse Oximeter, Hand held |  |  |  |  |
| Bed, Adult Patient with Mattress |  |  |  |  |
| Bed, Pediatric Patient, With Mattress |  |  |  |  |
| Bedside Locker |  |  |  |  |
| Cupboard, Instrument |  |  |  |  |
| Delivery Bed, Hydraulic Manual |  |  |  |  |
| Oxygen Therapy Apparatus, Mininum 45L cylinder |  |  |  |  |
| Resuscitator Manual, Infant, with all Mask sizes |  |  |  |  |
| Resuscitator Manual, Adult, with all mask sizes |  |  |  |  |
| Suction Apparatus, (Electric) |  |  |  |  |
| Nebulizer, Ultrasonic |  |  |  |  |
| Oxygen Concentrator, Duo Flow |  |  |  |  |
| Bench |  |  |  |  |
| Disinfection Buckets |  |  |  |  |
| Baby Cot |  |  |  |  |
| Diagnostic Equipment Set for Ward |  |  |  |  |
| Hollow Ware Set, Ward |  |  |  |  |
| Instrument Set, Delivery |  |  |  |  |
| Instrument Set, Stitch Removing |  |  |  |  |
| MVA Kit |  |  |  |  |
| Stool, Laboratory |  |  |  |  |
| Penguin Sucker |  |  |  |  |
| Fetoscope, Dopplar |  |  |  |  |
| Bubble CPAP |  |  |  |  |
| Centrifuge (Electric) |  |  |  |  |
| Kangaroo Mother Care Chair |  |  |  |  |
| Radiant Infant Warmer |  |  |  |  |
| Haemoglobin Meter, Sahli |  |  |  |  |
| Delivery Bed |  |  |  |  |
| Examination light |  |  |  |  |
| Instrument set, ENT Basic for HCIII |  |  |  |  |
| Bag Valve mask (Ambu Bag), Neonatal |  |  |  |  |
| Incubator |  |  |  |  |
| Office Chair |  |  |  |  |
| Desk |  |  |  |  |
| Filing Cabinet |  |  |  |  |
| Non-residential buildings |  |  |  |  |
| Residential buildings |  |  |  |  |
| Total Value |  |  |  |  |

Challenges and recommendations.

Recommendations

Appendices

IFMS-Ready Asset Register and Data Migration Report/ An automated up-to-date assets data base of UgIFT Investments across MDALGs;

- National (based on the agreed template of the IFMIS)

- Local government (based on the agreed template of the IFMIS)