# Team 14 - daily log of activities, Sironko District

Team: Kyanamira Nathan, Ahabwe Derrick, Asio Miriam Joyce. Supervisor: Kassim Luminsa. Supervisor's contact: +256 702 806116.

# 2026-08-24

Local government covered: Sironko District.

| Researcher | What was covered | Photographs |
| --- | --- | --- |
| Asio Miriam Joyce | The district offices, where the Senior Accountant and the District Health Officer's representative were seen; then Buteza Seed Secondary School, recorded from the gate and the frontage; then Buyobo HC III, written up from what its in-charge said | 30 |
| Ahabwe Derrick | St Mary's Bugitimwa Seed Secondary School, worked through with the head teacher, from the classrooms and the laboratory to the halls and the latrine blocks | 26 |
| Kyanamira Nathan | The call on the Chief Administrative Officer, then Simu Pondo HC III in Budadiri East, where the discussion guide was answered; Buyaya HC II was also reached and its nurse in charge said no UgIFT asset ever came to it | 57 |

# 2026-08-25

Local government covered: Sironko District.

| Researcher | What was covered | Photographs |
| --- | --- | --- |
| Ahabwe Derrick | Mutufu HC III in Bumalimba, worked through with the in-charge; rain held the journey up and the work ran on into the evening | 25 |
| Kyanamira Nathan | Wrote up the previous day's visit to Simu Pondo HC III and the funding the facility runs on | 0 |
| Asio Miriam Joyce | Worked Bulambuli this day; see that log | 0 |

# 2026-08-29

Local government covered: Sironko District.

| Researcher | What was covered | Photographs |
| --- | --- | --- |
| Kyanamira Nathan | Bundege HC III, worked through with the in-charge; the store could not be opened | 36 |

# 2026-09-01

Local government covered: Sironko District.

| Researcher | What was covered | Photographs |
| --- | --- | --- |
| Kyanamira Nathan | Circular Supply delivery notes for Simu Pondo HC III and Mutufu HC III, obtained from the district, and Simu Pondo's inventory register | 3 |

Simu Pondo, Bundege, Mutufu and Buyobo HC III are verified from named hand-filled booklets written up as Word toolkits, and so are St Mary's Bugitimwa and Buteza Seed Secondary School. Buyaya HC II still lacks a register. Buyobo HC III and Buyaya HC II were written up with nothing at either photographed. Buteza Seed Secondary School was closed.