PROCESS REPORT

# UGiFT Asset Verification and Register Review Process Report

Facility reconciliation, asset use, identification, custody, data quality and cost treatment

Reporting date 23 September 2026

Prepared for programme review and follow up

This report brings together the facility master list, field returns, consolidated registers and the prepared UGiFT asset register. It distinguishes confirmed records from matters that still require a field or local government decision.

# Executive summary

The review has produced a usable reconciliation and a traceable working asset register, but it is not yet a complete accounting or maintenance register. Facility identity and asset descriptions are generally strong. Cost, service dates, ownership markings, tags, serial numbers and current-use information remain incomplete. The immediate priority is to close the facility exceptions, confirm custody where assets moved, and inspect the assets that are unused, unmarked, missing or reported damaged.

| 629 Distinct master facilities 581 have a return or explained status | 163,498 Asset records Across 522 standardized facility names | 48 No return 7.6% of the master list | 6,926 Records with cost 4.2% of asset records |
| --- | --- | --- | --- |

## What the review found

| Area | Finding |
| --- | --- |
| Facility reconciliation | 581 of 629 listed facilities are covered. 8 are reported absent, 48 have no return and 46 still need a decision. |
| Ground returns | 37 submitted facility identities do not yet have a confirmed master-list match. They are leads for follow-up, not confirmed additional facilities. |
| Asset use | 55,347 records are marked in use, 7,221 are marked not in use and 100,930 have no use flag. |
| Engraving and identification | Only 14 records explicitly state UGiFT marking. 4,419 explicitly state that engraving is absent. 14,593 records contain a tag number, which does not by itself prove a physical UGiFT engraving. |
| Condition and maintenance | Source wording indicates good, working or in-use condition for 112,037 records. 2,915 are negative only, while 14,061 describe mixed groups. |
| Cost | Known asset costs total UGX 47.19 billion, but 156,572 records have no cost. This known total must not be read as the value of the full portfolio. |

A return can establish that information was received without proving that every item was seen. In the same way, a line describing a group of assets may say that some units are broken without identifying each unit. For that reason, this report keeps facility coverage, asset-level flags and text-screening results separate.

## Priority actions

Confirm the 8 facilities reported absent and resolve the 46 master entries whose identity, location or verification account remains uncertain.

Match or formally add the 37 ground-only returns, with the relevant local government approving each outcome.

Record custody transfers for the facilities whose UGiFT assets were relocated or whose original facility was replaced.

Inspect the 1,265 records with box or unopened wording and the 6,713 records described as not yet used, installed, assembled or commissioned.

Run a focused engraving and tagging exercise, starting with facilities that explicitly reported unengraved assets and high-value ICT or medical equipment.

Build a cost-estimation schedule from approved peer assets within the same local government. Keep estimated amounts separate from source costs until reviewed and approved.

# Scope and review process

The work began with the master list of schools and health centres, the team allocation, facility returns, district and ministry registers, and the raw evidence index. Files were preserved in their original form. Facility names were then reconciled before asset rows were normalized, because counting assets against an unresolved facility can create a clean-looking register with the wrong custodian.

## Process followed

Preserve and index the source files. Each usable record keeps its source filename and worksheet, table, row or page locator.

Create one master facility record for each distinct listed school or health centre. Repeated master rows remain traceable but do not increase the facility count.

Match field names to the master using local government, facility type, known aliases, source folders and reviewed supervisor decisions. Uncertain matches remain open.

Separate facility outcomes into field evidence, no return, needs review, reported absent, no UGiFT assets, outside UGiFT and replaced.

Normalize supported assets to one item per register row. Preserve group-level notes where the source does not identify individual units.

Classify assets, retain exact tags and serial numbers where available, and leave unsupported fields blank rather than creating identifiers or dates.

Retain explicit costs. Where a reliable line total and quantity exist, allocate the unit cost only when the source shows that the items are homogeneous.

Review exceptions separately. Overlaps, unknown quantities, consumables, unmatched facilities and conflicting source counts stay in review records instead of being silently forced into the main register.

## Evidence base

| Evidence | Count | Meaning |
| --- | --- | --- |
| Master facility records | 629 | Distinct schools and health centres after within-LG duplicate handling |
| Master source rows | 632 | Original rows retained for traceability |
| Asset source records | 34,599 | Selected source lines supporting the asset register |
| Asset records | 163,498 | One asset per row after supported quantities were expanded |
| Source files used | 425 | Facility returns and registers contributing selected asset lines |
| Review entries | 44,245 | Quantity, classification, overlap and reconciliation matters retained for review |

## Reporting levels

The same evidence can be reported at four levels. The national view shows the overall exposure. The local government view assigns follow-up and supports peer-cost analysis. The facility view identifies the custodian and the condition of assets at a site. The asset view carries the individual description, cost, tag, serial number and use status where the source supports them.

# Facility reconciliation

Coverage stands at 581 of 629 distinct master facilities, or 92.4%. This includes 519 facilities with identifiable evidence, 46 that need a decision and 16 with an explained outcome. It is an accountability measure, not a physical-verification rate.

| Status | Facilities | Share | Interpretation |
| --- | --- | --- | --- |
| Field evidence | 519 | 82.5% | A facility return or identifiable register information is available. |
| No return | 48 | 7.6% | No matched return or identifiable asset row is on file. |
| Needs review | 46 | 7.3% | The return exists, but identity, location or verification needs confirmation. |
| Reported absent | 8 | 1.3% | A field or supervisor account says the listed facility does not exist or was not constructed. |
| No UGiFT assets | 4 | 0.6% | The facility exists but has no UGiFT assets at the site. |
| Outside UGiFT | 2 | 0.3% | The facility exists but was reported outside the verified UGiFT scope. |
| Replaced | 2 | 0.3% | The listed facility was replaced and evidence is counted under the receiving facility. |

## Facilities on the list but reported absent

Eight master entries are reported absent. These are not treated as independently proven non-existent. Each local government should confirm the master-list treatment and retain the written decision.

| ID | Local government | Facility | Recorded basis |
| --- | --- | --- | --- |
| H227 | Yumbe | Lodonga Tc Health Centre III | The supervisor reports that Lodonga TC is not known to Yumbe District. This is a reported absence, not independent proof that the facility does not exist. |
| H205 | Pader | Olok Health Centre III | Combined Olok HC / Latanya school report records the DHO saying Olok HC does not exist and was not constructed. Latanya school is separate. |
| H190 | Lira | Alik Health Centre III | The supervisor explicitly reports that Alik does not exist in Lira. Barlonyo and Onywako are named on the ground, but neither is identified as a one-to-one replacement for Alik; the Onywako return also says physical verification was not performed. |
| H197 | Oyam | Acimi Health Centre III | The revised Oyam decision confirms that Acimi is not among the six upgraded UgIFT Health Centre IIIs and retains the earlier report that it does not exist. |
| H195 | Oyam | Acokara Health Centre III | The revised Oyam decision confirms that Acokara is not among the six upgraded UgIFT Health Centre IIIs and retains the earlier report that it does not exist. |
| H200 | Oyam | Ariba Health Centre III | The revised Oyam decision confirms that Ariba is not among the six upgraded UgIFT Health Centre IIIs and retains the earlier report that it does not exist. |
| H070 | Busia MC | Busia Eastern Division Health Centre III | Does not exist. Sofia Health Centre III is a separately named field return in Eastern Division and is not treated as an alias for this invalid master label. |
| S010 | Tororo MC | Eastern Division Seed Secondary School | Does not exist. The source master classifies this row as a school. Preserve the source type while marking the named master entry invalid. |

## Facilities found in returns but not confirmed on the list

There are 37 ground-return identities without a confirmed master match. Some may be spelling variants, district errors or facilities outside the original scope. They should be confirmed one by one before being added to the master or merged with an existing facility.

The full list appears in Appendix A, grouped by local government.

## Assets moved to another facility

| LG | Listed or sending facility | Receiving facility | Required treatment |
| --- | --- | --- | --- |
| Zombo | Alangi Health Centre III | Amwonyo Health Centre III | Assets relocated; source facility remains on the master with no assets. |
| Zombo | Ther-uru Health Centre III | Atyak Health Centre III | Assets relocated; source facility remains on the master with no assets. |
| Zombo | Abanga Seed Secondary School | Kango Seed Secondary School | Assets relocated; source facility remains on the master with no assets. |
| Nebbi | Oweko Health Centre III | Pamaka Health Centre III | Facility replaced; evidence retained under Pamaka. |
| Maracha | Loinya Health Centre III | Liko Health Centre III | Replacement already has its own master entry; count Liko once. |

For each movement, the register should record the sending facility, receiving facility, date, transfer authority, current custodian and asset identifiers. A change of location should not erase the original acquisition trail.

## Assets shared among facilities

The consolidated source text does not provide a reliable asset-level count of items shared between facilities. Shared documents and shared group tags do appear, but they are not evidence that the physical assets were jointly used. Future verification should capture the owning facility, host facility, borrowing facility, approval reference, date moved and expected return date for every shared item.

# Asset profile by local government and facility

The working register contains 163,498 asset rows against 522 standardized facility names and 149 book-type codes. The tables below show where the largest volumes sit. A high count can reflect more detailed source records rather than more assets in reality, so these figures should be used for workload planning, not performance ranking.

| Local government or book | Asset records | Share |
| --- | --- | --- |
| Tororo | 8,918 | 5.5% |
| Tororo Mc | 4,909 | 3.0% |
| Pallisa | 3,917 | 2.4% |
| Luweero | 3,036 | 1.9% |
| Amolatar | 3,027 | 1.9% |
| Kiryandongo | 2,885 | 1.8% |
| Yumbe | 2,823 | 1.7% |
| Bukedea | 2,715 | 1.7% |
| Zombo | 2,710 | 1.7% |
| Dokolo | 2,646 | 1.6% |

| Facility | Asset records | Share |
| --- | --- | --- |
| Kyamwinula Health Centre III | 4,909 | 3.0% |
| Iyolwa Seed Secondary School | 3,637 | 2.2% |
| Sop Sop Seed Secondary School | 3,255 | 2.0% |
| Luwube Muslim Seed Secondary School | 2,051 | 1.3% |
| Kabarwa Seed Secondary School | 2,015 | 1.2% |
| Akadot Seed Secondary School | 2,005 | 1.2% |
| Lwamata Town Council Seed Secondary School | 1,994 | 1.2% |
| Kitwara Seed Secondary School | 1,960 | 1.2% |
| Olok Seed Secondary School | 1,912 | 1.2% |
| Napak Seed Secondary School | 1,532 | 0.9% |

Every detailed register row retains the facility name and book code, allowing the complete dataset to be filtered by local government, facility, asset category and source reference. The Word report focuses on material exceptions and data quality rather than repeating all 163,498 rows.

# Functionality maintenance and use

Condition statements were not written in a single standard form. The source text was therefore screened into positive, negative, mixed and unclassified groups. This preserves the original meaning while showing where a site visit or item-by-item check is still required.

| Condition screen | Records | Share | Meaning |
| --- | --- | --- | --- |
| Positive only | 112,037 | 68.5% | Wording indicates functional, working, operational, in use or good working condition. |
| Negative only | 2,915 | 1.8% | Wording indicates broken, faulty, damaged, non-functional or needing repair. |
| Mixed group | 14,061 | 8.6% | The same source line describes both usable and unusable units; individual attribution is not safe. |
| Not classified | 34,485 | 21.1% | No clear positive or negative wording was found. |

The formal IN_USE_FLAG is more conservative: 55,347 records are marked YES, 7,221 are marked NO and 100,930 are blank. Good condition alone was not used to infer current use.

## Assets still boxed stored or not yet used

| Screen | Asset records | Source records | Follow up |
| --- | --- | --- | --- |
| Box or unopened wording | 1,265 | 228 | Inspect packaging, warranty, completeness and installation requirements. |
| Stored wording | 6,148 | 2,082 | Confirm whether storage is temporary, secure and appropriate for the asset. |
| Not yet used installed assembled or commissioned | 6,713 | 1,421 | Record the blocker, responsible officer and target date for use. |

These screens overlap. An item can be both stored and still boxed. The figures identify records to review; they should not be added together to produce a unique asset count.

## Maintenance and service follow up

Sixty source records, representing 124 asset rows, contain explicit wording that repair, maintenance, servicing or spare parts are required. This is a minimum count because group notes do not always identify each affected unit.

| Maintenance record | Minimum information |
| --- | --- |
| Asset identity | Facility, asset description, tag or serial number and source reference |
| Problem | Fault observed, date reported, effect on service and whether the item is safe to use |
| Action | Repair, service, replacement, calibration or disposal decision |
| Control | Work-order number, responsible officer, provider, cost, completion date and acceptance |

# Engraving identification and security

The current evidence is not strong enough to claim that the portfolio is properly engraved. Most records do not say whether a UGiFT mark is present. Tag numbers and serial numbers improve traceability, but they are reported separately because they do not prove that an ownership mark was physically engraved and easy to read.

| Evidence | Records | Share | Interpretation |
| --- | --- | --- | --- |
| Explicit UGiFT marking | 14 | 0.0% | Five source lines representing 14 assets explicitly state a UGiFT engraving or label. |
| Engraved owner not stated | 452 | 0.3% | The source says engraved, but does not establish that the mark identifies UGiFT. |
| Explicitly not engraved | 4,419 | 2.7% | The source explicitly says the asset or group was not engraved. |
| Engraving not stated | 158,613 | 97.0% | No reliable engraving statement was found. |

| Identification field | Records | Share |
| --- | --- | --- |
| Tag number present | 14,593 | 8.9% |
| Tag number missing | 148,905 | 91.1% |
| Serial number present | 662 | 0.4% |
| Serial number missing | 162,836 | 99.6% |

A focused engraving check should record the exact visible wording, tag number, serial number, photograph reference, legibility and whether the mark is permanent. Where assets are grouped, the team should avoid applying one shared tag to several physical items.

## Security observations

The source screening found 121 source records with theft or break-in wording. Those records represent grouped lines covering 746 asset entries, but that is not a confirmed count of stolen units. A further 428 source records use missing, lost, not seen or not available wording, and 6 explicitly mention a security-control gap such as a missing fence or lock.

Security follow-up should distinguish theft, temporary movement, non-delivery and an item that could not be seen during the visit. For theft cases, retain the police reference, date, responsible custodian, insurance position and management action.

# Asset registers and data quality

The prepared workbook is strong as a reconciliation register: every retained row has a standardized facility name, description and major category. It is much weaker as a complete accounting, maintenance and custody register because most rows do not have cost, service date, current-use status, tag or serial number.

| Field | Completed | Coverage | Assessment |
| --- | --- | --- | --- |
| Facility name | 163,498 | 100.0% | Strong |
| Description | 163,498 | 100.0% | Strong |
| Major category | 163,498 | 100.0% | Strong |
| Minor category | 155,525 | 95.1% | Strong |
| Placed in service date | 29,644 | 18.1% | Limited |
| Current use flag | 62,568 | 38.3% | Partial |
| Tag number | 14,593 | 8.9% | Limited |
| Serial number | 662 | 0.4% | Very limited |
| Cost | 6,926 | 4.2% | Very limited |

## Facilities supported by consolidated registers

For 38 master facilities across 17 local governments, completion is based on identifiable rows in a consolidated register rather than a facility-specific physical-verification return. These records support facility and asset identification, but they do not certify that each item was seen on site.

| Local government | Facilities | Facility names |
| --- | --- | --- |
| Alebtong | 2 | Abia .S Seed Secondary School; Awei Seed Secondary School |
| Bugiri | 1 | Budhaya Seed Secondary School |
| Buliisa | 1 | Avogera Health Centre III |
| Bunyangabu | 2 | Kateebwa Monument Health Centre III; Rubona Health Centre III |
| Dokolo | 1 | Batta Seed Secondary School |
| Hoima City | 1 | Kihuukya Health Centre III |
| Kakumiro | 5 | Birembo Health Centre III; Kabuubwa Health Centre III; Kakindo Health Centre III; Kigando Health Centre III; Kitaihuka Health Centre III |
| Kamwenge | 2 | Bwizi Seed Secondary School; Kabingo Health Centre III |
| Kasese | 6 | Buhuhira Health Centre III; Bwesumbu Health Centre III; Bwesumbu Seed Secondary School; Kyempara Health Centre III; Nyabirongo Health Centre III; Nyakimasa Health Centre III |
| Kiboga | 2 | Bulaga Health Centre III; Buninga Health Centre III |
| Kitagwenda | 1 | Kanara Seed Secondary School |
| Kyankwanzi | 2 | Banda Health Centre III; Mujunza Health Centre III |
| Mitooma | 4 | Bukuba Health Centre III; Mayanga Health Centre III; Nyakishojwa Health Centre III; Ryengyerero Health Centre III |
| Mubende | 1 | Lumbiri Health Centre III |
| Otuke | 2 | Ogoro Seed Secondary School; Okum Seed Secondary School |
| Serere | 1 | Kagwara Seed Secondary School |
| Sheema | 4 | Kigarama Seed Secondary School; Kyeibanga Health Centre III; Rugarama Health Centre III; Ryakasinga Seed Secondary School |

## Quality standard for each local register

A facility register should be rated Strong only when the item can be identified, located, valued and followed through its lifecycle. A register that lists assets but omits cost, service date and identifiers is useful for reconciliation, but it should be rated Partial until those fields are completed.

| Rating | Definition |
| --- | --- |
| Strong | Facility and location confirmed; description, quantity, cost, service date, tag or serial, condition, use and custodian substantially complete. |
| Partial | Assets are identifiable and attributable to the facility, but several accounting, custody or lifecycle fields are missing. |
| Limited | The register is a list or group schedule with weak facility identity, uncertain quantities, minimal identifiers or no condition evidence. |

# Cost treatment and estimation

Only 6,926 of 163,498 asset records have a supported positive cost. The known amount is UGX 47,188,668,915.44. The remaining 156,572 records should not be assigned a convenient average without checking that the comparison is genuinely like for like.

| Cost status | Records | Share | Treatment |
| --- | --- | --- | --- |
| Supported source unit cost | 6,926 | 4.2% | Retain as source cost with source reference. |
| Cost not established | 156,572 | 95.8% | Estimate only under an approved peer method and keep the estimate visibly separate. |

## Recommended peer cost method

The preferred estimate is the median unit cost of comparable assets in the same local government. The median is less distorted by unusually high or low prices than a simple average. The comparison group must match the asset class, specification, capacity, condition and acquisition period as closely as the source allows.

1.  Use the same facility first when at least three genuinely comparable assets have supported costs.

2.  If the facility has too few peers, use the same local government and the same normalized asset class, with at least five supported observations.

3.  If the local government has no adequate peer group, use the same service type, such as a Health Centre III or Seed Secondary School, and the same region or procurement period. Mark this as lower confidence.

4.  Do not use generic peer prices for land, buildings, major renovations, specialized systems or mixed bundles. Obtain the contract, bill of quantities, valuation or other approved evidence.

5.  Store source cost and estimated cost in separate fields. Record the method, peer count, median, range, reference assets, reviewer and approval date.

6.  Review estimates with finance and engineering staff before posting them to the accounting register. Never overwrite the original blank or source value without an audit trail.

## Minimum cost estimation record

| Record section | Required information |
| --- | --- |
| Target asset | Facility, local government, description, class, make or model, capacity, condition and acquisition period |
| Peer basis | Same facility or same local government; asset class and specification; procurement period |
| Calculation | Number of peers, median unit cost, lowest and highest peer cost, estimated quantity and total |
| Control | Source references, confidence level, preparer, reviewer, approval date and reason for using an estimate |

# Follow up plan

The next round should be organized around decisions, not another general request for data. Each exception needs an owner, a due date and evidence that closes the point. The table below gives a practical sequence.

| Step | Workstream | Task | Owner | Evidence of closure |
| --- | --- | --- | --- | --- |
| 1 | Facility list cleanup | Confirm 8 reported absences, 46 review cases and 37 ground-only returns. | Local government and programme reconciliation team | Approved master-list decision |
| 2 | Custody and movement | Document the three Zombo relocations and two facility replacements, then update the current custodian. | Local government accounting officer and facility head | Signed transfer or correction record |
| 3 | Engraving and tags | Inspect explicit non-engraving cases and complete the 148,905 rows without a tag where tagging is applicable. | Facility custodian and verification team | Readable mark, tag list and photo reference |
| 4 | Use and commissioning | Review 1,265 boxed or unopened records and 6,713 not-yet-used records. | Facility head and sector engineer | Use decision, blocker and target date |
| 5 | Maintenance and security | Open work orders for explicit repair needs and close theft, missing and security-control cases with documentary evidence. | Facility head, LG engineer and security officer | Work order or incident closure |
| 6 | Cost completion | Prepare peer-cost schedules for 156,572 missing-cost records, starting with high-value and high-risk assets. | LG finance team with programme review | Approved source or estimated cost trail |

## Close out test

Every master facility has one approved status and, where applicable, a matched return.

Every ground-only return is linked to a master facility, formally added, or documented as outside scope.

Every moved asset has a current custodian and an approved transfer trail.

Every high-value movable asset has a readable ownership mark and a unique tag or serial number where applicable.

Every non-functional, boxed, stored or unused asset has a recorded action and owner.

Every cost is identified as source, allocated from a valid homogeneous line total, or estimated under an approved peer method.

# Appendix A Ground returns without a confirmed master match

These returns should not be counted as confirmed additional facilities until the relevant local government approves the identity and the programme updates the master list.

| ID | Local government | Facility in return | Follow up note |
| --- | --- | --- | --- |
| X020 | Apac | Arocha Health Centre III | Facility-specific return received; no confirmed master match. |
| X028 | Bundibugyo | Busanga Health Centre III | Facility-specific return received; no confirmed master match. |
| X008 | Bunyangabu | Katungunda Seed Secondary School | Named in submitted register; no confirmed master match. Asset section: LOCAL GOVT: BUNYANGABU; FACILITY: KATUNGUNDA |
| X003 | Bushenyi | Kabushaho Seed Secondary School | Workbook is filed under Mitooma, but its facility heading explicitly says Bushenyi. No exact master-list school match. |
| X900 | Busia MC | Sofia Health Centre III | Facility-specific return identifies Sofia Health Centre III in Eastern Division, Busia Municipal Council. It is distinct from the invalid master label Busia Eastern Division. |
| X035 | Buvuma | Buvuma Health Centre III | Facility-specific return received; no confirmed master match. |
| X032 | Fort-Portal City | Bukuuku Community Seed Secondary School | Facility-specific return received; no confirmed master match. |
| X037 | Gomba | Kyayi Seed Secondary School | Facility-specific return received; no confirmed master match. |
| X029 | Kabarole | Iruhura Health Centre III | Facility-specific return received; no confirmed master match. |
| X030 | Kabarole | Nyambuusa Health Centre III | Facility-specific return received; no confirmed master match. |
| X043 | Kagadi | Muggi Health Centre III | Register says Kagadi; master Muggi is in Mayuge. Confirm the source LG. This is an unresolved return identity, not a confirmed additional Kagadi facility. |
| X009 | Kakumiro | Mukoora Health Centre III | Named in submitted register; no confirmed master match. Asset section: LOCAL GOVT: KAKUMURO; FACILITY: MUKOORA |
| X010 | Kakumiro | Silumira Health Centre III | Named in submitted register; no confirmed master match. Asset section: LOCAL GOVT: KAKUMIRO; FACILITY: SILUMIRA |
| X036 | Kalangala | Nekemiya Memorial Seed Secondary School | Facility-specific return received; no confirmed master match. |
| X026 | Kanungu | Bushogye Seed Secondary School | Facility-specific return received; no confirmed master match. |
| X022 | Karenga | Lokori Seed Secondary School | Facility-specific return received; no confirmed master match. |
| X011 | Kasanda | Namabaale Health Centre III | Team 30 return confirms Namabaale Health Centre III in Kasanda; no confirmed master-list match. |
| X007 | Kasese | Rukoki General Hospital | Named in submitted register; no confirmed master match. Asset section: LOCAL GOVT: KASESE; FACILITY: RUKOKI GENERAL HOSPITAL |
| X034 | Kiboga | Lwamata Town Council Seed Secondary School | Facility-specific return received; no confirmed master match. |
| X019 | Lira | Onywako Health Centre III | Form states that assets were reported by the in-charge and were not physically verified. Chat names Onywako on ground, but gives no one-to-one replacement for Alik. |
| X039 | Lwengo | Lwengenyi Health Centre III | Facility-specific return received; no confirmed master match. |
| X040 | Lwengo | Mbirizi Seed Secondary School | Facility-specific return received; no confirmed master match. |
| X041 | Lyantonde | Rwamabara Seed Secondary School | Facility-specific return received; no confirmed master match. |
| X016 | Maracha | Odupiri Health Centre III | Facility-specific return received; no confirmed master match. |
| X042 | Mbarara | Rutooma Health Centre III | New register heading says Mbarara without district/city distinction. It does not resolve the missing Rutooma in Bushenyi. |
| X004 | Mitooma | Kitojo Seed Secondary School | Named in submitted register; no confirmed master match. Asset section: Name of LG: MITOOMA DISTRICT Name of SCHOOL: KITOJO SEED SCHOOL |
| X021 | Moroto | Rupa Seed Secondary School | Facility-specific return received; no confirmed master match. |
| X038 | Mpigi | Wamatovu Seed Secondary School | Facility-specific return received; no confirmed master match. |
| X033 | Mubende | Nakawala Health Centre III | Facility-specific return received; no confirmed master match. |
| X031 | Ntoroko | Butungama Health Centre III | Facility-specific return received; no confirmed master match. |
| X025 | Rubanda | Kibuzigye Seed Secondary School | Facility-specific return received; no confirmed master match. |
| X027 | Rukungiri | Bikurungu Seed Secondary School | Facility-specific return received; no confirmed master match. |
| X005 | Sheema | Migina Health Centre III | Named in submitted register; no confirmed master match. Asset section: MIGINA HCIII, SHEEMA DC |
| X024 | Sironko | Simu Pondo Health Centre III | Facility-specific return received; no confirmed master match. |
| X017 | Yumbe | Lobe Health Centre III | Facility-specific return received; no confirmed master match. |
| X018 | Yumbe | Nyori Health Centre III | Facility-specific return received; no confirmed master match. |
| X013 | Zombo | Amei Seed Secondary School | Facility-specific return received; no confirmed master match. |

# Appendix B Data definitions and counting rules

| Term | Definition |
| --- | --- |
| Coverage | Every master facility except No return. Coverage does not mean every asset was physically inspected. |
| Field evidence | Identifiable facility information in a facility return or consolidated register. |
| Asset record | One retained row in the prepared asset register. A reliable group quantity is expanded to one row per item. |
| Explicit UGiFT marking | The source text states that the asset was engraved, labelled, tagged, marked or named as UGiFT. |
| Tag present | A tag value is recorded. This does not prove that the tag is permanent, legible or a UGiFT ownership mark. |
| Condition positive only | The source uses positive operational wording and no negative wording for that record. |
| Condition mixed | A group-level source line contains both positive and negative wording. Individual units cannot be separated safely. |
| Boxed or unopened | The source explicitly mentions a box, carton, unopened packaging or a still-boxed item. |
| Known cost | A supported positive unit cost is retained from the source. It is not an estimated replacement value. |
| Estimated cost | A separate, approved amount derived from comparable assets under the peer method. It should never replace the source value silently. |

## Source files

SCHOOLS BY DISTRICT AND HEALTH CENTRES.docx

team-distributions.docx

raw-data-grouped facility returns and evidence index

facility-reconciliation.csv and facility-evidence-index.csv

UgIFT Asset Register.xlsx

Updated Attributes for Asset Categories.xlsx

Location(3)2.xlsx

GOU Asset Accounting Policies and Guidelines 2023.pdf

## Limitations

The source material mixes physical-verification forms, consolidated registers, photographs, supervisor messages and other schedules. Some condition statements apply to groups rather than individual items. Keyword screening helps find records for review, but it does not replace field inspection. Blank fields remain blank where the source did not support a value. Reported absences, relocations and unmatched facilities require local government confirmation before the master list or accounting records are changed.