CONSULTANCY SERVICES TO VERIFY AND RECORD ASSETS UNDER THE UGIFT PROGRAMME

REF: MOFPED/UGIFT/CONS/25/26/00015

# ASSET VERIFICATION REPORT

SUBMITTED BY:

Plot 31, Bukoto Street

P.O Box 7657, Kampala, Uganda
+256 (0) 39 2000216/0772525235
email: cpa@cpa.ug

www.cpa.com

OCTOBER 2026

Contents

Executive summary	iv

1	INTRODUCTION AND BACKGROUND	1

1.1.	Introduction	1

1.2.	Background to the verification	1

1.3.	Justification	2

1.4.	Objectives of the assignment	2

1.5.	Scope of Work	3

1.6.	Expected deliverables	3

2	APPROACH AND METHODOLOGY	4

2.1	Preparation	4

2.2	Pilot Test	4

2.3	Data collection	4

2.4	Quality assurance	5

2.5	Asset categories, condition, use and identification	5

2.6 Financial analysis and Valuation	5

2.6	Analysis and reporting	5

2.7	Challenges and Limitations to the assignment	5

3	VERIFICATION FINDINGS	7

3.1	Overall results	7

3.2	National level Ministries and Agencies	13

3.3	MDA specific results	15

3.3.1	Ministry of Finance, Planning and Economic Development	15

3.3.2	Ministry of Works and Transport	15

3.3.3	Ministry of Education and Sports	16

3.3.4	Ministry of Agriculture, Animal Industry and Fisheries	17

3.3.5	Ministry of Health	18

3.3.6	Office of the Prime Minister	18

3.3.7	Ministry of Water and Environment	19

3.3.8	Ministry of Gender, Labour and Social Development	19

3.3.9	National Environment Management Authority	20

3.3.10	Public Procurement and Disposal of Public Assets Authority	20

3.3.11	Office of the Auditor General (OAG)	21

3.3.12	Ministry of Local Government	22

3.3.13	Ministry of Lands, Housing and Urban Development	22

3.4	Regional Blood Banks	23

3.4.1	Arua Regional Blood Bank	24

3.4.2	Hoima Regional Blood Bank	24

3.4.3	Soroti Regional Blood Bank	25

3.5	Local Government level results	27

3.5.1	Health Centres	27

3.5.2	Seed Secondary Schools	30

3.6	Field Observations	33

3.6.1	Completion Status of Facilities	33

3.6.2	Location and Name changes	34

3.7	Impact of UgIFT Programme on service delivery	34

3.8	Gaps and Challenges	35

4	4 ASSET MANAGEMENT	36

4.1 Maintenance and repairs	36

5	RECOMMENDATIONS	38

6	APPENDICES	39

List of Figures

Figure 1: Overall asset distribution by location	7

Figure 2: shows the reasons for non-deployment of some of the assets even when they were found to be in good condition.	8

Figure 3: Asset marking and Identification	11

Figure 4:: Asset marking and Identification at MDAs	14

Figure 5: Assets verified at MoH	18

Figure 6: Assets verified at OAG	21

Figure 7: Assets verified at MoLG	22

Figure 8: Assets verified at MoLHUD	23

Figure 9: Service gaps and challenges	35

Figure 10: Asset condition tracking intervals	36

List of tables

Table 1:Overall condition of UgIFT assets and functionality	7

Table 2: Overall Recorded asset value and net book value	13

Table 3: Number of verified UgIFT Assets by MDA	13

Table 4: Recorded costs and available accounting values at MoFPED	15

Table 5: Assets verified at MoWT	15

Table 6:  MoWT asset values by category	16

Table 7: Condition and use of assets for MoES	16

Table 8: Identification of assets for MoES	16

Table 9: Recorded costs and available accounting values at MoES	17

Table 10: Condition and use of assets at MAAIF	17

Table 11: Recorded tag content of assets at MAAIF	17

Table 12: Recorded costs and available accounting values at MAAIF	17

Table 13: Recorded costs and available accounting values for MoH	18

Table 14: Recorded costs and available accounting values at OPM	19

Table 15: Recorded costs and available accounting values for MoWE	19

Table 16: Recorded costs and available accounting values for MoGLSD	20

Table 17: Recorded costs and available accounting values for NEMA	20

Table 18: Recorded costs and available accounting values for PPDA	21

Table 19: Recorded costs and available accounting values for OAG	21

Table 20: Recorded costs and available accounting values for MoLG	22

Table 21: Recorded costs and available accounting values for MoLHUD	23

Table 22: Recorded value and net book value: Blood banks	24

Table 23: Asset categories for Arua Regional Blood Bank	24

Table 24: Asset categories for Hoima Regional Blood Bank	25

Table 25: Asset categories at Soroti Regional Blood Bank	25

Table 26: Availability of assets in Health Centres	27

Table 27: Condition of assets at Health centres	28

Table 28: Health Centre buildings	28

Table 29: Identification of assets at Health centres	29

Table 30: Recorded and net book values at Health centres	29

Table 31: Availability of assets in schools	30

Table 32: Condition of assets in schools	31

Table 33: Identification of assets in schools	31

Table 34: Recorded value and net book value for schools	32

Table 35: Completion Status for both Health centers and seed secondary schools	33

Table 36: Inconsistencies between the programme list and the facilities found	34

List of acronyms

GOU	Government of Uganda

HC	Health centre

ICT	Information and communications technology

IFMIS	Integrated Financial Management Information System

KCCA	Kampala Capital City Authority

LGFC	Local Government Finance Commission

MAAIF	Ministry of Agriculture, Animal Industry and Fisheries

MDA	Ministry, department or agency

MoDVA	Ministry of Defence and Veteran Affairs

MoES	Ministry of Education and Sports

MOES	Ministry of Education and Sports (as engraved)

MoFPED	Ministry of Finance, Planning and Economic Development

MoGLSD	Ministry of Gender, Labour and Social Development

MoH	Ministry of Health

MOH	Ministry of Health (as engraved)

MoLG	Ministry of Local Government

MoLHUD	Ministry of Lands, Housing and Urban Development

MoPS	Ministry of Public Service

MoWE	Ministry of Water and Environment

MoWT	Ministry of Works and Transport

NEMA	National Environment Management Authority

OAG	Office of the Auditor General

OPM	Office of the Prime Minister

PforR	Program-for-Results

PPDA	Public Procurement and Disposal of Public Assets Authority

RCU	Reform Coordination Unit

TELA	Teacher Effectiveness and Learner Assessment

UBTS	Uganda Blood Transfusion Services

UgIFT	Uganda Intergovernmental Fiscal Transfer

UGX	Uganda shillings

UPS	Uninterruptible power supply

# Executive summary

# INTRODUCTION AND BACKGROUND

## Introduction

This report presents the findings of the UgIFT asset verification undertaken by the Ministry of Finance, Planning and Economic Development as part of programme closure activities. It sets out the status of the assets provided by the programme to the targeted national institutions responsible for supporting the implementation of the programme, Blood Banks and local governments specifically targeting Seed Secondary Schools and health facilities upgraded from Health Centre II to Health Centre III.

## Background to the verification

The Uganda Intergovernmental Fiscal Transfers (UgIFT) Programme is a government programme implemented through a Programme-for-Results (PforR) launched and aligned with the broader IGFT Reform Programme (2015). UgIFT 1.0 began with US$200 million in FY2017/18, supporting Education and Health. This was later expanded through additional financing of US$300 million, including US$240 million in credit and US$60 million in grants, with US$50 million from the IDA Refugee Support Window, expanding beyond Education and Health to water and Environment and Agriculture (micro-scale irrigation) making the overall funding total of US$500 million.

The Intergovernmental Fiscal Transfer Reform Programme (IGFT RP) was revised in 2020 to align with the Third National Development Plan (NDP III 2020/21 - 2024/25), and to directly contribute to Four (04) Programmes i.e. Human Capital Development; Public Sector Transformation; Natural Resources, Environment, Climate change, Land and Water Management; and Development Plan Implementation.

Overall, the development objective of the UgIFT Programme was to: “Improve the adequacy, equity, and effectiveness of financing and the oversight, management, and delivery of Local Government services in Education, Health, Water and Environment, and Agriculture (micro-scale irrigation), including refugees and their host communities”.

Specifically, the Programme sought to:

- Increase the adequacy and predictability of fiscal transfers to Local Governments for service delivery;

- Improve the equity and transparency of allocation mechanisms through the introduction of formula-based transfers;

- Strengthen performance incentives and accountability systems for Local Governments; and

- Expand access to quality education and health infrastructure, particularly in under-served areas.

The UgIFT Programme had four components aimed at strengthening the intergovernmental fiscal transfer system while supporting investments in service delivery infrastructure. These included;

Component 1: Reform of the Intergovernmental Fiscal Transfer System

This supported the design and implementation of a reformed fiscal transfer framework based on objective and transparent allocation criteria. This resulted into introduction of formula-based grants - Revised allocation formulas reflecting population, infrastructure gaps, and service delivery needs.

Component 2: Education Infrastructure Development

This component financed the construction and upgrading of education facilities, particularly government secondary schools in under-served sub-counties. This involved construction and equipping of new secondary schools - classrooms, laboratories, administration blocks, sanitation facilities, teachers’ houses, furniture and ICT equipment in the different local governments.

Component 3: Health Infrastructure Development

This supported investments in health facilities to improve access to primary health care services at the local level. The major outputs under the component were construction and upgrading of health centers - Staff accommodation, sanitation facilities and provision of medical equipment.

Component 4: Local Government Performance and Institutional Strengthening

This aimed at strengthening LG capacity in planning, budgeting, procurement, and infrastructure management. Under this component, annual Local Government Performance Assessments have been undertaken across the 176 LGs, capacity building and technical support strengthened monitoring and reporting systems.

The Programme was implemented through a clearly defined results framework that connected actions and incentives across three levels of government to strengthen service delivery outcomes. The programme came to an end on 31 December 2025. The following areas of support describe the following outputs under the different components; current asset and facility findings are presented later in this report.

- Budget Support

- Education: 196 of 259 Seed Secondary Schools are complete of which 189 are operational.

- Health: 354 of 373 health facilities, upgrades/new constructions (HC II to HC III) are complete.

- Water and Environment: 758 - piped water systems, 5,398- point water sources, 7,082 water supply systems rehabilitated, 325 designs completed, and 256 sanitation facilities in the targeted service units.

- Agriculture (Micro-scale Irrigation): Over 6,235 irrigation systems were installed (4,843 hectares under irrigation), 632 irrigation demonstration sites in 135 LGs set up.

- Refugee intervention: 51 primary schools and 35 health facilities in refugee hosting districts (RHD) were transitioned and integrated into the LG service.

- Blood Banks: Regional Blood Banks in Arua and Hoima were completed and commissioned while Soroti Regional Blood Bank was rehabilitated.

- Grant management

Assets for institutional strengthening and retooling including ICT equipment and vehicles were provided. The Ministry of Finance, Planning and Economic Development (MoFPED) through PFM Coordination Unit (RCU) manages the Government of Uganda counterpart funding of the programme to support the grant management component of the UgIFT programme. The grant management supports in financing of Central Government actions intended to achieve programme objectives and Disbursement Linked Indicators (DLIs). To this end, MoFPED through RCU supported MDAs to acquire different assets meant to support programme implementation.

## Justification

The UgIFT programme came to an end on 31st December 2025. As part of the programme’s closure activities, MoFPED, through RCU, commissioned an end-of-programme asset verification exercise to take stock of the assets procured under the programme and to establish where those assets were, how they were being used as part of the processes to hand them over to government for sustainability purposes.

## Objectives of the assignment

The objective of the assignment was to undertake verification and recording of all assets acquired under the UgIFT Programme. Specifically, the assignment intended to;

- Identify and verify the existence of the assets

- Verify the assets condition and status: specifically, the condition on functionality, usage/performance and location among others

- Assess financial management aspects: residual value of the investments/hardware/tools for purposes of financial reporting for project closure

- List the assets that are obsolete, unserviceable and require disposal

- Develop a computerized database of the investment/hardware/tools to facilitate recording of new deployed assets/investments.

- Undertake PFM Assessment on Asset Management practices (including sustainability, Operations and Maintenance) of the UgIFT implementing LGs

## Scope of Work

The assignment covered institutions at national and local government level that directly implemented the UgIFT programme through coordination, support and implementation. At local government level, the study focused on upgraded health facilities and Seed Secondary Schools that received assets under the programme. Health Centers and other local-government assets are also reported separately.

Specifically, the assignment involved the following tasks;

- Verification of the Asset’s Records of targeted ministries departments and agencies and local governments

- Physical and Functional Verification of assets

- Data Consolidation for generation of a single data base of assets provided by the program

- Generation of an IFMIS ready Asset Register for Integration, and Migration into IFMIS

- Review of the UgIFT Asset Management Practices

## Expected deliverables

Key expected outputs of the consultant include:

- Report with the list and current status of assets acquired under the programmes;

- An automated up-to-date assets data base of UgIFT Investments across MDALGs;

- Report on the estimated value of assets under the programme as well as operations and maintenance arrangements;

- IFMIS-Ready Asset Register and Data Migration Report

- Report on functionality of assets relating to systems investments;

- Report on Assessment of Asset Management Practices, Risks and recommendations.

# APPROACH AND METHODOLOGY

The verification exercise was conducted using a participatory and consultative process and implemented in three interlinked phases: Preparatory and inception phase, Data collection phase and the report writing phase.

## Preparation

After signing of the contract, the assignment commenced with an entry meeting on 28th May 2026. During this meeting, the Client specified target MDAs to be visited, the LG stakeholders to be reached as well as the documents to be reviewed. The Inception phase was completed and the inception report submitted on 18th June, 2026 which provided an agreed scope, approach and work plan for the exercise.

## Pilot Test

The team also undertook a pilot test in Wakiso District Local Government, with verification carried out at Buloba Health Centre III and Sumbwe Seed Secondary School. During the pilot test, it was found out that, among others, there are cases of mismatches of facility names, that UgIFT assets can be integrated into the general LG asset register. This facilitated improving the design of the data collection process including; design of data collection tools, determining the timeline for data collection and estimated costs.

## Data collection

This exercise was undertaken in two phases first at National level and later at the Local government level.

National level: Physical visits to verify assets provided by the programme at the national-level was completed on the 19th of August 2026. This covered 15 MDAs including; Ministry of Works and Transport (MoWT); Ministry of Education and Sports (MoES); Ministry of Agriculture, Animal Industries and Fisheries (MAAIF); Ministry of Health (MoH); Office of the Prime Minister (OPM); Ministry of Water and Environment (MoWE); Ministry of Gender, Labour and Social Development (MoGLSD); Local Government Finance Commission; National Environment Management Authority (NEMA); Public Procurement and Disposal of Assets Authority (PPDA); Office of the Auditor General (OAG); Ministry of Public Service (MoPs); Ministry of Lands, Housing and Urban Development (MoLHUD); Ministry of Local Government (MoLG) and Ministry of Finance, Planning and Economic Development (MoFPED). Additionally, three Blood Banks of Hoima, Arua and Soroti were covered.

Local government level: The local government verification targeted UgIFT upgraded or constructed Health Centres and Seed Secondary Schools. The programme reconciliation list contains 629 distinct entries: 371 Health Centres and 258 schools under 160 recorded local government names. The process began with training of field teams prior to the actual field verification.

Training of field teams: A total of 85 Research Assistants (RAs) and 7 Regional Supervisors were trained. The training took place from 21st to 23rd August 2026 while physical verification started on the 24th of August 2026. During the asset verification, the RAs visited Seed Secondary Schools, Health Centres and Blood Banks.

Physical verification: This exercise commenced on the 24th of August 2026 and was completed on 17th September 2026. The local government physical verification involved entry meetings with the LG leadership at the LG headquarters for authorization and review of reports relating to UgIFT assets, key informant interviews with the technical teams especially the Chief Administrative Officers, Finance Officers, District Health Officers and District Education Officers. Thereafter, the RAs proceeded to the facilities for physical verification of the assets.

At local government level, the programme list had 629 facilities: 371 Health Centres and 258 Seed Secondary Schools. The list recorded 547 facilities (87.0%) as complete and 82 (13.0%) as ongoing. The ongoing works were more common among Seed Secondary Schools (63, or 24.4%) than among Health Centres (19, or 5.1%).

## Quality assurance

Regional supervisors checked daily field activity and reviewed the completed tools. The central technical team carried out spot checks and helped resolve operational questions. Teams compared institutional asset information with the items and explanations provided during visits, while supervisors referred matters requiring clarification to the team leader and field coordinator.

## Asset categories, condition, use and identification

Asset categories: Each entry in the Asset Register represents one recorded unit. The analysis covers buildings, ICT equipment, transport equipment, furniture and fittings, medical, laboratory and research equipment, other classified assets, items outside fixed-asset classification and unclassified entries. Assets are grouped by the institution or beneficiary to which they are attributed.

Condition and use: Condition and use were reported for each asset during the verification. A working asset is one recorded as functional and in use. An asset recorded as faulty was reported as not working and not in use. This included assets that were broken down or damaged. An asset that was new and in store was recorded as functional but not in use. Additionally, an asset that was held elsewhere, not yet delivered or awaiting power installation, completion of buildings or trained users, was also recorded as functional but not in use.

Identification: An asset is properly identified when carried a UgIFT programme marking. However, there were other assets that had no UgIFT marking but the officers on ground identified them as UgIFT assets.

## 2.6 Financial analysis and Valuation

The Government of Uganda Asset Accounting Policies and Guidelines 2023 was used to determine as the policy basis for determining recorded values, depreciation and net book values. Financial values are reported as at 30th September 2026. Straight-line depreciation was applied where the required information was available.

## Analysis and reporting

Analysis and reporting was done through triangulation of the literature from different policy, Planning and Financial documents including: Government of Uganda Asset Accounting Policies and Guidelines 2023; asset registers; asset records at national and local government levels; physical inspections; discussions with facility managers; photographs and asset counts for each institution.

## Challenges and Limitations to the assignment

- Difficult terrain and poor physical accessibility of facilities: Physical accessibility presented a significant operational challenge especially for facilities located in areas characterised by difficult terrain and limited transport accessibility such as Bwesumbu HC III, Bwesumbu Seed School, Buhuhira and Kabingo in Kasese District. In addition, accessing facilities within the Island was difficult, time consuming and expensive. This led the teams to overshoot the anticipated time for data collection.

- High transportation cost: Given the national wide coverage, the rising fuel prices led to high field costs. The field teams spent more money than was anticipated. The costs were extra ordinarily higher for island facilities like Kalangala, Buvuma, Mayuge among others. For instance, Kalangala had 3 facilities with long distance on water that required hiring a private boat since it was not a common route to the transporters and outside the ferry schedules. A similar situation was encountered in Buvuma and Namayingo districts.

- Poor record keeping: In many LGs and facilities, there were no clear records about the assets delivered under UgIFT. The LGs and the facilities had incomplete or missing UgIFT asset registers which delayed data collection. Subsequently, the teams took longer in such facilities identifying the assets as most of these were not engraved with the UgIFT identifiers while others were not engraved at all. In addition, the field teams encountered situations where some Assets could not be physically accessed especially for schools since it was holiday time.

# VERIFICATION FINDINGS

This section presents results of the verification exercise based on the specific objectives. The results are presented in different results levels indicating availability of assets, asset condition and functionality, asset marking and identification and the financial analysis in each subsection.

## Overall results

This section provides an overall view of the UgFT asset status combining both National level agencies, schools and health centres.

Overall asset availability

A total of 228,800 assets are recorded across the targeted MDAs, beneficiary Blood Banks, Upgraded Health Centres and Seed Secondary School. These include vehicles, laptops, printers, desktop computers, projectors, cameras, furniture (desks, chairs, tables and stools), UPS systems, digital phones, paper shredders, tablets and clinical equipment, among others.

Overall, the Seed Secondary Schools hold the majority of assets 63.4% (145,256), followed by Health Centres with 29.% (66,499). MDAs hold 7.3% (16,663) and regional Blood Banks with 0.3% (602). In addition, some assets were found to have been reallocated by LGs from Health Center to hospitals such as Rukoki general hospital in Kasese Municipality.

Figure 1: Overall asset distribution by location

Source: Primary data analysis

Overall asset Condition and functionality

Overall, 215,280 assets constituting 94.1% were classified as functional and in use, while 13,504 (5.9%) were classified as faulty and out of use. The detailed analysis of asset condition is indicated in table 1.

Table 1:Overall condition of UgIFT assets and functionality

| Institution | No. of Assets | Functional |  | Faulty and not in use | % functional |
| --- | --- | --- | --- | --- | --- |
|  |  | In use | In store |  |  |
| MoFPED | 458 | 458 | 0 | 0 | 100.0% |
| MoWT | 87 | 71 | 16 | 160 | 100.0% |
| MoES | 10,783 | 10,783 | 0 | 0 | 100.0% |
| MAAIF | 2,045 | 2,045 | 0 | 0 | 100.0% |
| MoH | 51 | 50 | 0 | 1 | 98.0% |
| OPM | 10 | 7 | 0 | 3 | 70.0% |
| MoWE | 2,939 | 2,939 | 0 | 0 | 100.0% |
| MoGLSD | 10 | 10 | 0 | 0 | 100.0% |
| NEMA | 6 | 6 | 0 | 0 | 100.0% |
| PPDA | 5 | 5 | 0 | 0 | 100.0% |
| OAG | 20 | 20 | 0 | 0 | 100.0% |
| MoLG | 13 | 13 | 0 | 0 | 100.0% |
| MoLHUD | 12 | 12 | 0 | 0 | 100.0% |
| Health centres | 66,499 | 60,814 | 0 | 5,685 | 91.4% |
| Seed Secondary Schools | 145,256 | 137,465 | 0 | 7,791 | 94.6% |
| Blood Banks | 602 | 578 | 0 | 24 | 96.0% |
| Total | 228,800 | 215,280 | 16 | 13,504 | 94.1% |

Source: Primary data analysis

As indicated in table 1 above, most of the deployed assets were already in service while some were in store and still in good condition but not in use. This was attributed mainly to some localized challenges such as power, incomplete structures, untrained staff, among others. Some assets were broken mainly furniture in Seed Secondary Schools and require repair.

Verification also noted that 13,520 assets, mainly in seed secondary schools and Health Centres, were classified as faulty and out of use. Some were awaiting installation or the facility itself was not yet ready as indicated in figure 2. Notable among the facilities include Lungulu Seed Secondary School in Nwoya District where desktop computers, a printer and UPS units were still boxed because the school was waiting for power connection. At Nansanga Seed Secondary School in Budaka, 27 of 28 desktop computers remained packed for lack of reliable power.

Figure 2: shows the reasons for non-deployment of some of the assets even when they were found to be in good condition.

Source: Primary data analysis

In addition, broken desks and stools were in classrooms and stores at Seed schools in Namisindwa and Napak. At Arua Regional Blood Bank, six blood pressure machines were recorded as damaged or not functional. The information above is depicted in some of the photos presented below.

| Delivery bed with a torn mattress cover at a health centre, Busia District (Bukedi) | Pedal suction unit marked MAJANJI H/C III still in its packing, recorded as not in use for lack of technical knowledge, Majanji Health Centre III, Busia District (Bukedi) |
| --- | --- |
| Stacked desks, chairs and stools, some recorded as broken and none engraved, at Napak Seed Secondary School, Napak District (Karamoja) | Cracked health centre block above collapsed ground, Bulambuli District (Bugisu) |
| Broken desk frame at a seed secondary school, Namisindwa District (Bugisu) | Empty ICT and library block with a few chairs and items kept in one corner at Iriiri Seed Secondary School, Napak District (Karamoja), not yet in use while the school remained with the contractor |
| Stained and peeling ceiling at a health centre, Sironko District (Bugisu) | Flood-affected older health facility at Butiaba, Buliisa District (Bunyoro) |
| Desktop computers, a printer and UPS units still boxed in the store at Lungulu Seed Secondary School, Nwoya District (Acholi), awaiting a power connection for installation | Laboratory stools and desks stored and not yet in use at Butungama Seed Secondary School, Ntoroko District (Tooro), where the school buildings were still under construction |
| HP computer sets stacked in store with cables still bundled and not installed at Bumufuni Seed Secondary School, Bulambuli District (Bugisu) | beds and screens stacked in storage at a health centre, Kagadi District (Bunyoro) |
| Boxed projector, air conditioner and other equipment in store at King Solomon Seed Secondary School, Kagadi District (Bunyoro), kept boxed because the school was still under construction | Boxed handheld pulse oximeters at Kibiri Health Centre III, Makindye-Ssabagabo Municipal Council (Buganda), where equipment was still being arranged after the facility opened on 31 August 2026 |

Asset Marking and Identification

The verification revealed that 50,329 (22.0%) of the assets had UgIFT marking and 178,695 (78.0%) were not engraved. Of all assets, 22,253 (9.7%) had identifiers containing UgIFT markings. Identification varied at the different asset locations. Identifiers are recorded for 30.3% of MDA records, 24.5% of school records and 15.0% of health-centre records. Among the MDAs, the Ministry of Education and Sports accounts for most of the ministry assets without usable identifiers, and these were mainly the TELA handsets and tablets. The details of asset identification are provided in figure 3.

Figure 3: Asset marking and Identification

Source: Primary data analysis

Below are some of the photos depicting the different markings and identification engravement of assets across the institutions

| Engraving reading GOU/MOH-UGIFT PROJECT FY/2023/2024 on a desk at Namwaya Health Centre III, Tororo District | Engraving reading APESSS MOES/UGIFT/KABE/SPLRS/2023-24/001 on a desk at Aperikira Seed Secondary School, Kaberamaido District |
| --- | --- |
| Chair engraved UgIFT/ BUDDE SEED S.S M-PHALL CHAIR with a serial number at Budde Seed Secondary School, Butambala District | Wheelchair backrest marked GOU/MOH UGIFT-PROJECT. FY2023/2024 at Kalemungole Health Centre III, Moroto District |
| Engraving reading GOU/MOH-UGIFT PROJECT FY2023-2024/01 on a weighing scale at Kalemungole Health Centre III, Moroto District | Microscope marked KAMORU HC III by hand at Kamoru Health Centre III, Kotido District |
| Engraving reading KING SOLOMON SEED SECONDARY SCHOOL, without a UgIFT marking, on furniture at King Solomon Seed Secondary School, Kagadi District | Engraving reading KWN/MED-EQ/MOYOK HCIII on a steel cupboard at Moyok Health Centre III, Kween District |

Financial analysis

Overall, the 229,024 assets across the different institutions had an available recorded value of UGX 996,812,628,890. Based on the straight-line depreciation method, available accumulated depreciation was UGX 165,185,197,307 and available net book value was UGX 595,801,587,531 as at 30th September 2026. Recorded values vary by institution, with MDAs at UGX 32,054,743,836, Blood Banks at UGX 1,503,720,926, Seed Secondary Schools at UGX 700,242,561,371; Health Centers at UGX 260,692,452,291, hospitals and other local-government assets account for the remaining UGX 2,319,150,466 as indicated in table 2.

Table 2: Overall Recorded asset value and net book value

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| Schools | 700,242.56 | 104,574.53 | 394,241.71 | 79.00% |
| Health centres | 263,011.60 | 40,269.47 | 190,467.32 | 72.42% |
| Ministries and agencies | 32,054.74 | 19,787.51 | 10,265.93 | 34.20% |
| Regional blood banks | 1,503.72 | 553.689 | 826.632 | 59.90% |
| Total | 996,812.63 | 165,185.20 | 595,801.59 | 78.30% |

Table 2 further indicates that the net book value represents 78.3% of the recorded costs of the assets that was determined by the STL method.

## National level Ministries and Agencies

Asset availability at Ministries and Agencies: The exercise recorded 16,663 assets of the different categories across all the thirteen asset-holding Ministries and agencies. In terms of categorization, the exercise recorded 15,192 ICT equipment items including desktop computers, laptops, tablets and Uninterruptible Power Supply (UPS) units, 77 transport items, 99 furniture and fittings, 48 other classified assets, 1,235 items outside fixed-asset classification and 12 unclassified entries.

By location, most MDA assets (94.6%) were at MoES, MoWE and MAAIF while PPDA was found with only five assets including three Lenovo think pad Laptops, one HP Laser Jet Color Printer and one Samsung Galaxy tablet as indicated in Table 3.

Table 3: Number of verified UgIFT Assets by MDA

| Ministries and Agencies | No. of Assets |
| --- | --- |
| Ministry of Finance, Planning and Economic Development (MoFPED) | 458 |
| Ministry of Works and Transport (MoWT) | 87 |
| Ministry of Education and Sports (MoES) | 10,783 |
| Ministry of Agriculture, Animal Industry and Fisheries (MAAIF) | 2,045 |
| Ministry of Health (MoH) | 260 |
| Office of the Prime Minister (OPM) | 10 |
| Ministry of Water and Environment (MoWE) | 2,939 |
| Ministry of Gender, Labour and Social Development (MoGLSD) | 10 |
| National Environment Management Authority (NEMA) | 6 |
| Public Procurement and Disposal of Public Assets Authority (PPDA) | 5 |
| Office of the Auditor General (OAG) | 20 |
| Ministry of Local Government (MoLG) | 13 |
| Ministry of Lands, Housing and Urban Development (MoLHUD) | 27 |
| Total | 16,663 |

Asset Condition and functionality: At MDA level, apart from Ministry of Health that had one double cabin boarded off and three broken laptops at the Office of the Prime minister, the rest of the assets 16,643 (99.9%) were in good condition and were in use. The Ministry of Education and Sports held 10,783 of these assets, mainly TELA handsets and tablets and were all in use at the different schools across the country. LGFC and MoPS indicated that they never received UgIFT assets.

Asset marking and Identification: At MDA level, there were 16,663 asset records, of which 5,045 (30.3%) had UgIFT markings, with 4,925 assets (29.6%) bearing UgIFT markings and 120 (0.7%) had other markings. The majority of assets, 11,618 (69.7%), were not engraved. The figure 4 shows the identification status of the assets at the different MDAs.

Figure 4:: Asset marking and Identification at MDAs

Source: Primary data analysis

Financial value of assets: recorded costs total UGX 32,054,743,836 across 16,651 of 16,663 records. Accumulated depreciation totals UGX 19,787,511,232 and net book value totals UGX 10,265,924,979 as at 30th September 2026.

## MDA specific results

### Ministry of Finance, Planning and Economic Development

Asset availability: The ministry keeps a UgIFT asset register and the consolidated register for all MDAs that received UgIFT assets. A total of 458 assets were recorded at the ministry including 230 ICT items, 99 furniture and fittings, 21 transport items, 37 other classified assets, 65 items outside fixed-asset classification and six unclassified entries. The main items were office chairs and desks, desktop computers, tablets and 20 Toyota Hilux double-cabin pickups.

Condition and functionality: All 458 assets (100.0%) were recorded as functional and in use, and none was classified as faulty.

Reports described spoilt keyboards and UPS units, computers that freeze and laptop losses. The affected quantities and individual assets were not specified, so the number of broken or lost items could not be established. The asset manager should identify the affected items and reconcile the damage and loss reports.

Marking and identification: A total of 282 assets (61.6%) had usable identifiers and 176 (38.4%) had no usable tag recorded. Of all 458 assets, 247 (53.9%) had UgIFT or UGFT in the tag field and 35 (7.6%) carried another identifier. The 20 double-cabin pickups were identified by their registration numbers rather than UgIFT tag text. These tag-field counts do not confirm physical engraving.

Financial Value of assets: The recorded value of the ministry's UgIFT assets is UGX 6,204,318,000. Accumulated depreciation is UGX 4,312,193,629 and net book value is UGX 1,785,677,771 at 30 September 2026. Net book value remains unavailable for 20 records. Table 4 presents the category breakdown.

Table 4: Recorded costs and available accounting values at MoFPED

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| ICT equipment | 1,350.105 | 1,011.732 | 238.731 | 19.1% |
| Furniture and fittings | 137.037 | 96.069 | 40.968 | 29.9% |
| Non-fixed-asset | 6.564 | 0.000 | 0.000 | n/a |
| Other assets | 159.987 | 158.377 | 1.610 | 1.0% |
| Transport equipment | 4,550.385 | 3,046.016 | 1,504.369 | 33.1% |
| Total | 6,204.318 | 4,312.194 | 1,785.678 | 29.3% |

### Ministry of Works and Transport

Asset availability: The Ministry did not provide a UgIFT Asset Register. The MoWT register contained 87 assets, of which 70 ICT items were mainly desktop computers, monitors, uninterruptible power supply (UPS) units, video-conferencing equipment, printers and photocopiers; one Toyota Hilux pickup; sixteen items outside fixed-asset classification; and one unclassified entry. The sixteen items outside fixed-asset classification were keyboards as presented in Table 5.

Table 5: Assets verified at MoWT

| Asset category | Assets |
| --- | --- |
| ICT equipment | 70 |
| Non-fixed-asset | 16 |
| Transport equipment | 1 |
| Total | 87 |

Asset condition and functionality: All the assets were functional and in use.

Asset Marking and Identification: Of the 87 assets, 79 (90.8%) had usable identifiers, with 77 (88.5%) having UgIFT or UGFT in the tag field and two (2.3%) carrying another identifier; eight (9.2%) had no usable tag recorded.

Financial Value of assets: The recorded value was established as UGX 455,932,376. Accumulated depreciation is UGX 326,484,882 and net book value is UGX 115,311,494 as at 30th September 2026 as presented in Table 6

Table 6:  MoWT asset values by category

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| ICT equipment | 259.914 | 137.001 | 108.778 | 44.3% |
| Transport equipment | 196.018 | 189.484 | 6.534 | 3.3% |
| Total | 455.932 | 326.485 | 115.311 | 26.1% |

### Ministry of Education and Sports

Asset availability: The verification at the Ministry of Education and Sports (MoES) established that the ministry had 10,783 assets. All the assets are ICT equipment and these include 9,324 TELA handsets, 1,001 tablets (976 of them inspection tablets), 456 laptops, a photocopier and a printer. Teacher, Effectiveness and Learner Achievement (TELA) is the system, financed by UgIFT, that the ministry uses to monitor attendance and performance in schools; the handsets and inspection tablets are deployed in local governments and remain MoES assets.

All the 10,783 assets (100.0%) are recorded as functional and in use. All the 456 laptops are recorded as functional and in use. Table 7 presents condition and use.

Table 7: Condition and use of assets for MoES

| Condition | No. of Assets | Proportion |
| --- | --- | --- |
| Functional | 10,783 | 100.0% |
| Faulty | 0 | 0.0% |
| Total | 10,783 | 100.0% |

Marking and Identification: Of the 10,783 assets, 458 (4.2%) had UgIFT or UGFT in the tag field, while 10,325 (95.8%) had no UgIFT tag recorded. None of the handsets or tablets carries an engravement mark.

Table 8: Identification of assets for MoES

| Identification | No. of Assets | Proportion |
| --- | --- | --- |
| Engraved UgIFT | 458 | 4.2% |
| Not engraved | 10,325 | 95.8% |

Financial Value of assets: The recorded value is UGX 14,925,128,359, the highest among the MDAs. Accumulated depreciation is UGX 10,607,476,704 and net book value is UGX 4,317,651,655 as at 30th September 2026. Table 9 presents the category breakdown.

Table 9: Recorded costs and available accounting values at MoES

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| ICT equipment | 14,925.128 | 10,607.477 | 4,317.652 | 28.9% |
| Total | 14,925.128 | 10,607.477 | 4,317.652 | 28.9% |

### Ministry of Agriculture, Animal Industry and Fisheries

Asset availability: The team recorded UgIFT assets at the Ministry of Agriculture, Animal Industry and Fisheries (MAAIF) and established that it held 2,045 assets. These included 1,236 ICT equipment items, two transport items and 807 others, comprising 797 outside fixed-asset classification, five other classified assets and five unclassified entries. The ICT items were mainly 819 tablets, 211 computers (162 desktop CPU entries and 49 laptops), 149 monitors and 21 printers.

Asset condition and functionality: All 2,045 assets (100.0%) are recorded as functional and in use. All 211 computers and 819 tablets are recorded as functional and in use. Table 10 presents condition and use of asset.

Table 10: Condition and use of assets at MAAIF

| Condition | No. of Assets | Proportion |
| --- | --- | --- |
| Functional | 2,045 | 100.0% |
| Faulty | 0 | 0.0% |
| Total | 2,045 | 100.0% |

Asset Marking and Identification: Of the 2,045 verified assets, 1,232 (60.2%) are engraved, 1,228 (60.0%) with the UgIFT marking while 4 (0.2%) had other engravement marks, and 813 (39.8%) were not engraved as indicated in table 11.

Table 11: Recorded tag content of assets at MAAIF

| Identification | No. of Assets | Proportion |
| --- | --- | --- |
| Engraved UgIFT | 1,228 | 60.0% |
| Another identifier | 4 | 0.2% |
| Not engraved | 813 | 39.8% |

Financial Value of assets: The recorded value was UGX 2,856,556,593. Accumulated depreciation is UGX 1,380,059,505 and net book value is UGX 1,403,429,899 as at 30th September 2026. Table 12 presents the category breakdown.

Table 12: Recorded costs and available accounting values at MAAIF

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| ICT equipment | 2,278.449 | 952.109 | 1,326.341 | 58.2% |
| Outside fixed-asset classification | 72.467 | 0.000 | 0.000 | n/a |
| Other assets | 8.000 | 5.467 | 2.533 | 31.7% |
| Transport equipment | 497.040 | 422.484 | 74.556 | 15.0% |
| Total | 2,856.557 | 1,380.060 | 1,403.430 | 50.4% |

### Ministry of Health

The verification at the MoH did not find a Ugift Asset Register but relied on the list provided by the Ministry of Finance, Planning and Economic Development.

Asset availability: A total of 51 assets were recorded. Of the 51 assets, 31 were classified as ICT equipment, 16 as transport equipment (motor vehicles and motorcycles), 4 were classified as other assets. The Ministry’s other items include 2 heavy-duty binding machine and 2 CC20240 paper shredders. as indicated in Figure 9

Figure 5: Assets verified at MoH

Asset condition and functionality: The assets recorded as functional and in use were 50 (98.0%). Only one asset, a double-cabin pickup, was recorded as faulty and not in use.

Asset Marking and Identification: Out of the 51 assets, 24 (47.1%) were engraved while 27 (52.9%) were not engraved. There were 14 (27.5%) assets with UgIFT markings and 10 (19.6%) with other identifiers.

Financial Value of assets: The MoH assets had a recorded value of UGX 879,893,642. Accumulated depreciation value was UGX 406,599,572 and net book value was UGX 287,726,201 as at 30th September 2026. Table 11 presents the category breakdown.

Table 13: Recorded costs and available accounting values for MoH

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| ICT equipment | 211.927 | 109.806 | 102.122 | 48.2% |
| Transport equipment | 663.136 | 294.379 | 183.189 | 38.4% |
| Other assets | 4.831 | 2.415 | 2.415 | 50.0% |
| Total | 879.894 | 406.600 | 287.726 | 41.4% |

### Office of the Prime Minister

The Assets Register for the Office of the Prime Minister was not obtained and no list of assets was provided.  The verification relied on the listing obtained from the Ministry of Finance, Planning and Economic Development.

Asset availability: Office of the Prime Minister received 10 assets which were all HP laptop computers

Condition and functionality: Seven assets (70.0%) were recorded as functional and in use. Three (30.0%) were recorded as faulty and out of use.

Marking and identification: All the ten laptops (100.0%) had UgIFT or UGFT in the tag field.

Financial Value of assets: The recorded value of these computers in OPM was UGX 53,535,300. Accumulated depreciation is UGX 48,181,770 and net book value is UGX 5,353,530 as at 30 September 2026. Table 14 presents the category breakdown.

Table 14: Recorded costs and available accounting values at OPM

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| ICT equipment | 53.535 | 48.182 | 5.354 | 10.0% |
| Total | 53.535 | 48.182 | 5.354 | 10.0% |

### Ministry of Water and Environment

Asset availability: The Asset Verification at the Ministry of Water and Environment found out that the ministry keeps a general register which does not conform to IFMIS Standards. The register recorded 2,782 assets, of which 2,782 were classified as ICT equipment. The assets received by the Ministry included 2,368 tablets, of which 2,344 were Euron tablets; computers and related monitors, keyboards and UPS units; and 31 laptops. The Ministry also received sixteen real-time kinematic GPS machines

However, other assets were received which included; seven survey units described as ground-penetrating radar equipment, 3 Samsung Galaxy Tab S9 tablets, 2 Lenovo Think Book notebooks, 1 Kyocera heavy-duty copier, 1 Huawei 65-inch infrared screen and 1 UPS unit.

Asset condition and functionality: The findings further indicated that 2,756 assets (99.1%) were recorded as functional and in use, 26 (0.9%) were functional and in store, and none was classified as faulty.

Asset Marking and Identification: The ministry received a total of 2,782 assets, of which 2,740 (98.5%) were engraved, 2,707 (97.3%) with UgIFT markings and 33 (1.2%) with other markings; 42 (1.5%) were not engraved.

Financial Value of the assets: The recorded value was UGX 3,773,982,079. Accumulated depreciation is UGX 2,092,642,121 and net book value is UGX 1,535,627,440 as at 30th September 2026. Table 15 presents the category breakdown.

Table 15: Recorded costs and available accounting values for MoWE

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| ICT equipment | 3,773.982 | 2,092.642 | 1,535.627 | 42.3% |
| Total | 3,773.982 | 2,092.642 | 1,535.627 | 42.3% |

### Ministry of Gender, Labour and Social Development

Asset availability: The Asset Verification at the Ministry of Gender, Labour and Social Development found out that the ministry keeps a UgIFT asset register which had ten UgIFT assets. These comprised eight Lenovo computers, including four ThinkBook laptops, and two Samsung tablets. Figure 11 presents the UgIFT assets recorded for MoGLSD.

Asset condition and functionality: The findings further indicate that all ten UgIFT assets (100.0%) were recorded as functional and in use.

Asset Marking and Identification: A total of Eight Lenovo ThinkPad Laptops (80.0%) were properly engraved with the UgIFT markings and the Two Samsung Tablets (20.0%) were not engraved.

Financial Value of the assets: The findings pointed out that the recorded value to be UGX 46,180,000. Accumulated depreciation is UGX 13,260,000 and net book value is UGX 14,860,000 as at 30th September 2026. Table 16 presents the category breakdown.

Table 16: Recorded costs and available accounting values for MoGLSD

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| ICT equipment | 46.180 | 13.260 | 14.860 | 52.8% |
| Total | 46.180 | 13.260 | 14.860 | 52.8% |

### National Environment Management Authority

Asset availability: National Environment Management Authority (NEMA) had six ICT items: four computers, a printer and a heavy-duty photocopier. Figure 12 presents the asset categories.

Condition and functionality: All six assets (100.0%) were recorded as functional and in use.

Asset marking and identification: One asset (16.7%), the heavy-duty photocopier, had UgIFT or UGFT in the tag field while the other five (83.3%) had no usable tag recorded.

Financial value of Assets: The recorded value is UGX 46,824,409. Accumulated depreciation is UGX 32,841,273 and net book value is UGX 13,983,136 as at 30th September 2026. Table 17 presents the category breakdown.

Table 17: Recorded costs and available accounting values for NEMA

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| ICT equipment | 46.824 | 32.841 | 13.983 | 29.9% |
| Total | 46.824 | 32.841 | 13.983 | 29.9% |

### Public Procurement and Disposal of Public Assets Authority

Public Procurement and Disposal of Public Assets Authority (PPDA) did not provide a Ugift Asset Register. The verification relied on the information obtained from the Ministry of Finance, Planning and Economic Development.

Asset availability: A total of 5 assets were verified in PPDA; these were 3 Lenovo ThinkPad laptops, a Samsung Galaxy tablet and an HP printer.

Asset condition and functionality: All the five assets (100.0%) were recorded as functional and in use.

Asset marking and identification: All five assets (laptops, a tablet and a printer) had UgIFT engravement.

Financial Value of assets: The recorded cost was UGX 30,153,500. Accumulated depreciation is UGX 13,066,516 and net book value was UGX 17,086,984 as at 30th September 2026. Table 18 presents the category breakdown.

Table 18: Recorded costs and available accounting values for PPDA

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | %NBV |
| --- | --- | --- | --- | --- |
| ICT equipment | 30.154 | 13.067 | 17.087 | 56.7% |
| Total | 30.154 | 13.067 | 17.087 | 56.7% |

### Office of the Auditor General (OAG)

Asset availability: Evidence gathered during the verification confirmed that OAG had no UgIFT asset register rather a list which indicated 20 assets; 18 of which were ICT items (16 laptops and 2 printers) and 2 pickup vehicles. The above information is depicted in figure 14.

Asset condition and functionality: All 20 (100.0%) were in good condition and in use.

Asset marking and Identification: Six (30.0%) were properly engraved with the UgIFT markings and 14 (70.0%) were not properly engraved with UgIFT markings. The engravement was carrying the office's own asset code or vehicle registration number for the two pickups as in figure 6.

Figure 6: Assets verified at OAG

Financial value of Assets: The assets were worth UGX 388,773,680. Accumulated depreciation was UGX 111,591,545 and net book value is UGX 277,182,135 as at 30th September 2026. Table 19 presents the category breakdown.

Table 19: Recorded costs and available accounting values for OAG

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| ICT equipment | 228.774 | 71.592 | 157.182 | 68.7% |
| Transport equipment | 160.000 | 40.000 | 120.000 | 75.0% |
| Total | 388.774 | 111.592 | 277.182 | 71.3% |

### Ministry of Local Government

Asset availability: The asset verification at the Ministry of Local Government (MoLG) found that the ministry kept a UgIFT asset register and had 13 UgIFT assets; one double-cabin pickup and 12 ICT items. The ICT assets comprised of 6 computers, 4 computer peripherals and 2 heavy duty photocopiers. Figure 7 presents the UgIFT assets verified for MoLG.

Figure 7: Assets verified at MoLG

Asset condition and functionality: The findings further indicate that all thirteen assets (100.0%) were recorded as functional and in use.

Asset marking and identification: Out of the 13 assets, eight (61.5%) were engraved while five (38.5%) were not.  Of the eight assets that were engraved, 7 (53.8%) were engraved with a UgIFT markings while one was not. In terms of ICT equipment which formed the bulk of assets, 3 (50.0%) were engraved and 3 (50.0%) were not engraved while 1 (7.7%) carried another identifier.

Financial Value of assets: The findings pointed out the recorded value to be UGX 343,320,450. Accumulated depreciation was UGX 284,670,827 and net book value was UGX 54,649,623 as at 30th September 2026. Table 18 presents the category breakdown.

Table 20: Recorded costs and available accounting values for MoLG

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | %NBV |
| --- | --- | --- | --- | --- |
| ICT equipment | 94.800 | 36.151 | 54.650 | 60.2% |
| Transport equipment | 248.520 | 248.520 | 0.000 | 0.0% |
| Total | 343.320 | 284.671 | 54.650 | 16.1% |

### Ministry of Lands, Housing and Urban Development

Asset availability: The findings from the verification exercise indicate that MoLH &UD had 27 UgIFT assets. These include 25 Honda motorcycles and two other entries described as Accessories (12 Helmets). Additionally, the ministry received survey equipment and other motorcycles that it gave out to local governments.

Figure 8: Assets verified at MoLHUD

Asset condition and functionality: All the 27 assets (100.0%) were recorded as functional and in use, and none was classified as faulty.

Asset marking and Identification: All the 27 (100.0%) were not engraved with UgIFT markings. Thirteen (48.1%) had other identifiers and fourteen (51.9%) were not engraved. It was also noted that the motorcycles did not have the UgFT labelling but were identified by their registration numbers only.

Financial Value of assets: The findings further indicate the recorded value to be UGX 487,349,999. Accumulated depreciation was UGX 123,840,000 and net book value was UGX 340,559,999 as at 30th September 2026. Table 21 presents the category breakdown.

Table 21: Recorded costs and available accounting values for MoLHUD

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | %NBV |
| --- | --- | --- | --- | --- |
| Transport equipment | 483.750 | 123.840 | 340.560 | 73.3% |
| Non-fixed assets | 3.600 | 0.000 | 0.000 | n/a |
| Total | 487.350 | 123.840 | 340.560 | 73.3% |

## Regional Blood Banks

UgIFT financed the construction of the Arua and Hoima regional blood banks, which were completed and commissioned, and the rehabilitation of Soroti Regional Blood Bank. The three Blood Banks operate under Uganda Blood Transfusion Services (UBTS) and were verified.

Asset availability: The blood banks held a total of UgFT asset base of 602 fixed assets inclusive of the Assets at the Uganda Blood transfusion services. The exercise verified all assets at the three regional blood banks as follows. Arua Regional Blood Bank held 324 assets, Hoima Regional Blood Bank had 163 and Soroti Regional Blood Bank had 115 assets.

Asset Condition and functionality: Assets at the regional blood banks were generally recorded as functional and in use: 578 (96.0%) had that status. Only Arua Regional Blood Bank had faulty assets, accounting for all 24 (4.0%) faulty assets in the three-bank total.

Asset Marking and Identification: Of the 602-regional blood-bank assets, 76 (12.6%) had UgIFT engravement and 526 (87.4%) were not engraved. Of the engraved, 26 (4.3%) carried UgIFT markings and 50 (8.3%) carried a none UgIFT engravement.

Financial aspects: The recorded asset value was UGX 1,503,720,926 and the net book value as at 30th September 2026 was UGX 826,632,084. Accumulated depreciation was UGX 553,688,842. Table 22 presents the blood-bank financial values.

Table 22: Recorded value and net book value: Blood banks

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| Arua Regional Blood Bank | 1,153.115 | 472.399 | 557.316 | 54.1% |
| Hoima Regional Blood Bank | 312.991 | 48.561 | 264.430 | 84.5% |
| Soroti Regional Blood Bank | 37.615 | 32.729 | 4.886 | 13.0% |
| Total | 1,503.721 | 553.689 | 826.632 | 59.9% |

### Arua Regional Blood Bank

Asset availability: Arua Regional Blood Bank held a total of 324 assets.

Asset Marking and identification: Twenty-six assets (8.0%) have identifiers containing UgIFT or UGFT, 48 (14.8%) have another identifier and 250 (77.2%) have no usable identifier. Physical engraving still requires confirmation.

Asset condition and functionality: Out of 324 assets at Arua regional blood bank, 300 (92.6%) were classified as functional and in use, while 24 (7.4%) were classified as faulty and not in use.

Financial value of assets: The recorded asset value was UGX 1,153,114,971. Accumulated depreciation value was UGX 472,399,460 and net book value UGX 557,315,511as at 30th September 2026. Table 23gives the category breakdown of values.

Table 23: Asset categories for Arua Regional Blood Bank

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| Medical, laboratory and research appliances | 57.612 | 41.213 | 16.400 | 28.5% |
| Furniture and fittings | 192.104 | 99.390 | 92.715 | 48.3% |
| ICT equipment | 91.478 | 41.308 | 50.170 | 54.8% |
| Other classified assets | 261.024 | 142.271 | 118.753 | 45.5% |
| Outside fixed-asset classification | 123.400 | 0.000 | 0.000 | n/a |
| Transport equipment | 240.000 | 124.000 | 116.000 | 48.3% |
| Buildings and structures | 187.496 | 24.218 | 163.278 | 87.1% |
| Total | 1,153.115 | 472.399 | 557.316 | 54.1% |

### Hoima Regional Blood Bank

Asset availability: The verification team established that, Hoima Regional Blood Bank had a total of 163 assets.

Asset Marking and identification: No asset was engraved with UgIFT marking. Two assets (1.2%) had other identification marks and 161 (98.8%) were not engraved at all.

Asset condition and functionality: All 163 assets at Hoima Regional blood bank were functional and in use.

Financial value of assets: The recorded asset value was UGX 312,990,807. Accumulated depreciation value was UGX 48,560,694 and net book value was UGX 264,430,113 as at 30th September 2026. Table 24 gives the category breakdown.

Table 24: Asset categories for Hoima Regional Blood Bank

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| Medical, laboratory and research appliances | 54.192 | 37.973 | 16.219 | 29.9% |
| Other classified assets | 6.840 | 3.544 | 3.296 | 48.2% |
| Furniture and fittings | 0.520 | 0.338 | 0.182 | 34.9% |
| Buildings and structures | 251.439 | 6.705 | 244.734 | 97.3% |
| Total | 312.991 | 48.561 | 264.430 | 84.5% |

### Soroti Regional Blood Bank

Asset availability: Soroti Regional Blood Bank held 115 assets.

Asset Marking and identification: None of the 115 assets were engraved.

Asset condition and functionality: All the asset were functional and in use.

Financial value of assets: The recorded asset value was UGX 37,615,148. Accumulated depreciation value was UGX 32,728,688 and net book value was UGX 4,886,460 as at 30th September 2026. Table 25 gives the category breakdown.

Table 25: Asset categories at Soroti Regional Blood Bank

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| Medical, laboratory and research appliances | 32.599 | 28.131 | 4.468 | 13.7% |
| ICT equipment | 4.416 | 4.048 | 0.368 | 8.3% |
| Furniture and fittings | 0.600 | 0.550 | 0.050 | 8.3% |
| Total | 37.615 | 32.729 | 4.886 | 13.0% |

Asset photographs below shows some of the assets verified at regional blood banks.

| Blood-bank building at Arua Regional Blood Bank, Arua City | Plasma snap freezer at Hoima Regional Blood Bank, Hoima City. |
| --- | --- |
| Blood bank refrigerator at Arua Regional Blood Bank, Arua City | Platelet agitator at Arua Regional Blood Bank, Arua City |
| Donor couches in the donor room at Hoima Regional Blood Bank, Hoima City | Blood-bank refrigerators and plasma snap freezer at Soroti Regional Blood Bank. |
| Benchtop centrifuge at Hoima Regional Blood Bank, Hoima City | Markings PEP II/UBTS/COMP/11/016 and UBTS/UGIFT/ARBB/UPS/001 on uninterruptible power supplies at Arua Regional Blood Bank, Arua City |

## Local Government level results

The programme list at the LG level contained 629 UgIFT facilities, of which 371 were Health Centres and 258 were Seed Secondary Schools. Supporting returns accounted for 590 entries and 39 had discrepancies requiring reconciliation. A total of 208,688 assets were recorded at Health Centres and school locations, of which 63,432 were for Health Centres and 145,256 were for schools. Of the 208,688 assets, 195,224 (93.5%) were recorded as functional and in use while 13,464 (6.5%) were recorded as faulty and not in use. A further 3,067 assets were attributed to hospitals and four to other local-government locations. The details are presented in sections 3.6 (Health Centres) and 3.7 (Seed Secondary Schools).

## Health Centres

Availability of the assets: The verification findings indicate that health facilities had 63,432 recorded assets across the different categories which include clinical and laboratory equipment, furniture, maternity ward equipment, ICT equipment, buildings, land and other items. The register includes 7,746 non-fixed assets. Table 26 presents assets by category and proportion.

Table 26: Availability of assets in Health Centres

| Asset category | No. of Assets | Proportion |
| --- | --- | --- |
| Medical, laboratory and research appliances | 36,721 | 57.9% |
| Furniture and fittings | 15,671 | 24.7% |
| Outside fixed-asset classification | 7,746 | 12.2% |
| Buildings and structures | 2,260 | 3.6% |
| Other classified assets | 537 | 0.8% |
| ICT equipment | 424 | 0.7% |
| Unclassified | 64 | 0.1% |
| Transport equipment | 5 | 0.0% |
| Land (pieces) | 4 | 0.0% |
| Total | 63,432 | 100.0% |

Asset condition and functionality: The findings indicate that of the 63,432 health-centre assets, 57,759 (91.1%) were recorded as functional and in use and 5,673 (8.9%) were recorded as faulty and not in use. Table 27 presents the condition of the assets.

Table 27: Condition of assets at Health centres

| Asset category | No. of Assets | Functional | Faulty |
| --- | --- | --- | --- |
| Medical, laboratory and research appliances | 36,721 | 32,473 | 4,248 |
| Furniture and fittings | 15,671 | 14,988 | 683 |
| Outside fixed-asset classification | 7,746 | 7,231 | 515 |
| Buildings and structures | 2,260 | 2,144 | 116 |
| Other classified assets | 537 | 479 | 58 |
| ICT equipment | 424 | 374 | 50 |
| Unclassified | 64 | 62 | 2 |
| Transport equipment | 5 | 4 | 1 |
| Land (pieces) | 41 | 4 | 0 |
| Total | 63,432 | 57,759 | 5,673 |

The records indicated that some health-centre assets were not in use due to a number of reasons such as assets not delivered to the health centre (still in stores at LGs), idle assets, assets with missing parts, lack of power, assets not required at the facility, rooms or wards unavailable for installation, assets held at another facility, items awaiting installation, lost or missing items and equipment unused because staff were not trained or no specialist was available to operate it. Examples include a wall-mounted blood-pressure machine at Butawata Health Centre III (Mubende District) recorded as not functional; a wheelchair at Aarapoo Health Centre III (Serere District) that had not been delivered; a patient screen at Ayer Health Centre III (Kole District) that was on the delivery note but not seen; a paediatric bed at Okwerodot Health Centre III (Kole District) supplied without a mattress; and an autoclave at Anamwany Health Centre III (Amolatar District) unused for lack of electricity. The register's two condition categories do not provide a separate count for these reasons.

In terms of buildings, there were 2,260 assets comprising of 487 residential-building, 1,402 non-residential building, 364 other-structure entries and seven water supply systems. Table 28 presents the classifications.

Table 28: Health Centre buildings

| Asset category | No. of Assets |
| --- | --- |
| Non-residential buildings | 1,402 |
| Residential buildings | 487 |
| Other Structures | 364 |
| Water supply systems | 7 |

Asset marking and Identification: Of the 63,432 assets in Health Centres, 9,541 (15.0%) were engraved while 53,891 (85.0%) were not engraved. It was noted that 3,824 (6.0%) carried UgIFT markings and 5,717 (9.0%) carried other markings as shown in Table 29.

Table 29: Identification of assets at Health centres

| Asset category | No. of Assets | UgIFT markings | Other markings | Not engraved |
| --- | --- | --- | --- | --- |
| Medical, laboratory and research appliances | 36,721 | 1,786 | 2,826 | 32,109 |
| Furniture and fittings | 15,671 | 1,484 | 1,888 | 12,299 |
| Outside fixed-asset classification | 7,746 | 356 | 689 | 6,701 |
| Buildings and structures | 2,260 | 45 | 179 | 2,036 |
| Other classified assets | 537 | 20 | 43 | 474 |
| ICT equipment | 424 | 133 | 32 | 259 |
| Unclassified | 64 | 0 | 54 | 10 |
| Transport equipment | 5 | 0 | 4 | 1 |
| Land (pieces) | 4 | 0 | 2 | 2 |
| Total | 63,432 | 3,824 | 5,717 | 53,891 |

Financial Value of assets: The findings indicate that the available recorded value of assets was UGX 260,692,452,291 and the available net book value was UGX 189,403,577,197, while available accumulated depreciation was UGX 39,211,094,700 as at 30th September 2026. Table 30 gives the recorded value and net book value.

Table 30: Recorded and net book values at Health centres

| Asset category and coverage | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| Medical, laboratory and research appliances | 39,592.633 | 14,080.055 | 18,715.685 | 57.1% |
| Furniture and fittings | 15,109.270 | 5,764.153 | 6,584.582 | 53.3% |
| Non-fixed assets | 479.803 | 0.000 | 0.000 | n/a |
| Buildings | 203,954.138 | 18,304.241 | 163,802.803 | 89.9% |
| Other assets | 347.206 | 172.492 | 133.099 | 43.6% |
| ICT equipment | 929.345 | 825.749 | 85.256 | 9.4% |
| Unclassified | 134.958 | 0.971 | 0.485 | 33.3% |
| Transport equipment | 75.100 | 63.433 | 11.667 | 15.5% |
| Land | 70.000 | 0.000 | 70.000 | 100.0% |
| Total | 260,692.452 | 39,211.095 | 189,403.577 | 82.8% |

The verification established that some buildings were complete and in use while others were incomplete as presented in photographs below.

Photographs in Figures 20 to 23 show some of the facilities that are complete

| Health centre building at Kibiri HC III, Makindye-Ssabagabo Municipal Council | Health centre buildings and covered walkway at Kihuukya HC III, Hoima City |
| --- | --- |
| Binocular microscope at Kihuukya HC III, Hoima City | : Maternity block entrance and access ramp at Kamuli HC III, Tororo District |
| Unfinished laboratory building at a health centre, Sironko District | Incomplete staff quarters at Benet Health Centre III, Kween District. Field visit 27 August 2026. |
| Interior awaiting completion at Benet Health Centre III, Kween District. Field visit 27 August 2026. | A further unfinished room at Benet Health Centre III, Kween District |

## Seed Secondary Schools

Availability of the assets: The findings showed that schools had 145,256 recorded assets covering the following categories: school buildings, water facilities, furniture, computers and related equipment such as monitors, UPS units and keyboards; ICT equipment including printers, photocopiers, cameras and projectors; and other school assets such as laboratory items, electrical items, plant and machinery and sports equipment. Table 31 presents the details.

Table 31: Availability of assets in schools

| Asset category | No. of Assets | Proportion |
| --- | --- | --- |
| Furniture and fittings | 107,792 | 74.2% |
| ICT equipment | 12,036 | 8.3% |
| Outside fixed-asset classification | 9,081 | 6.3% |
| Buildings and structures | 7,505 | 5.2% |
| Medical, laboratory and research appliances | 5,604 | 3.9% |
| Other classified assets | 2,716 | 1.9% |
| Unclassified | 500 | 0.3% |
| Land (pieces) | 14 | 0.0% |
| Transport equipment | 8 | 0.0% |
| Total | 145,256 | 100.0% |

Asset condition and functionality: Out of 145,256 assets, 137,465 (94.6%) were recorded as functional and in use. The verification further established that 7,791 (5.4%) were recorded as faulty and not in use. Table 32 indicates the asset condition.

Table 32: Condition of assets in schools

| Asset category | No. of Assets | Functional | Faulty |
| --- | --- | --- | --- |
| Furniture and fittings | 107,792 | 102,521 | 5,271 |
| ICT equipment | 12,036 | 10,404 | 1,632 |
| Outside fixed-asset classification | 9,081 | 8,692 | 389 |
| Buildings and structures | 7,505 | 7,220 | 285 |
| Medical, laboratory and research appliances | 5,604 | 5,498 | 106 |
| Other classified assets | 2,716 | 2,623 | 93 |
| Unclassified | 500 | 485 | 15 |
| Land (pieces) | 14 | 14 | 0 |
| Transport equipment | 8 | 8 | 0 |
| Total | 145,256 | 137,465 | 7,791 |

Table 32 further indicates that school furniture and fittings (desks, tables, chairs, shelves and stools) is the largest category with 107,792 assets. Of these, 102,521 were recorded as functional and in use while 5,271 were recorded as faulty. ICT equipment had 10,404 assets recorded as functional and in use.

Asset marking and Identification: Of the 145,256 school assets, 35,601 (24.5%) were engraved while 109,655 (75.5%) were not engraved. A total of 13,478 (9.3%) had UgIFT markings and 22,123 (15.2%) had other markings, as shown in Table 33

Table 33: Identification of assets in schools

| Asset category | No. of Assets | UgIFT Marking | Other Markings | Not engraved |
| --- | --- | --- | --- | --- |
| Furniture and fittings | 107,792 | 12,985 | 18,503 | 76,304 |
| ICT equipment | 12,036 | 315 | 2,426 | 9,295 |
| Non-fixed-assets | 9,081 | 0 | 452 | 8,629 |
| Buildings and structures | 7,505 | 40 | 391 | 7,074 |
| Medical, laboratory and research appliances | 5,604 | 121 | 242 | 5,241 |
| Other classified assets | 2,716 | 17 | 96 | 2,603 |
| Unclassified | 500 | 0 | 10 | 490 |
| Land (pieces) | 14 | 0 | 2 | 12 |
| Transport equipment | 8 | 0 | 1 | 7 |
| Total | 145,256 | 13,478 | 22,123 | 109,655 |

Financial Value of school assets: The recorded asset value was UGX 700,242,561,371, accumulated depreciation was UGX 104,574,530,246 and the net book value was UGX 394,241,708,595 as at 30th September 2026, as shown in Table 34.

Table 34: Recorded value and net book value for schools

| Asset category | Recorded cost (ugx million) | Accumulated depreciation (ugx million) | Net book value (ugx million) | % NBV |
| --- | --- | --- | --- | --- |
| Furniture and fittings | 22,612.957 | 11,733.742 | 7,406.367 | 38.7% |
| ICT equipment | 29,669.809 | 15,836.227 | 9,584.916 | 37.7% |
| Non-fixed-assets | 40,839.592 | 0.000 | 0.000 | n/a |
| Buildings and structures | 601,004.483 | 74,561.320 | 374,906.543 | 83.4% |
| Medical, laboratory and research appliances | 1,455.366 | 864.426 | 511.352 | 37.2% |
| Other classified assets | 2,488.189 | 1,037.888 | 1,224.696 | 54.1% |
| Unclassified | 610.010 | 33.415 | 141.245 | 80.9% |
| Land (pieces) | 110.029 | 0.000 | 110.029 | 100.0% |
| Transport equipment | 1,452.127 | 507.511 | 356.561 | 41.3% |
| Total | 700,242.561 | 104,574.530 | 394,241.709 | 79.0% |

The verification established that some buildings were complete and in use while others were incomplete as presented in photographs below.

Photographs in Figures 28 to 30 show some of the facilities that are complete

| Classroom furnished with desks and a whiteboard at Gyagenda Memorial Seed Secondary School, Kalangala District | Books displayed in library shelves at Sibanga Seed School, Manafwa District |
| --- | --- |
| ICT laboratory block and entrance ramp at Sisiyi Seed Secondary School, Bulambuli District | Unfinished school block at Got Apwoyo Seed Secondary School, Nwoya District |
| Unfinished classroom block at Sidok Seed Secondary School, Kaabong District | Building works and construction materials at Ndhew Seed Secondary School, Nebbi District (West Nile) |
| School block awaiting completion at Butungama Seed Secondary School, Ntoroko District | Building works at a seed secondary school, Kiboga District |
| : Library interior under construction at Kihungya Seed Secondary School, Buliisa District | ICT laboratory interior under construction at Kitawoi Seed Secondary School, Kween District |

## Field Observations

## Completion Status of Facilities

The verification established that there were a number of facilities that were either completed or not completed. Table 35 provides the status of the completed and non-completed buildings for both health centers and seed secondary schools.

Table 35: Completion Status for both Health centers and seed secondary schools

| Status | Health centres | Schools | Total |
| --- | --- | --- | --- |
| Completed | 352 | 195 | 547 |
| Ongoing | 19 | 63 | 82 |
| Incomplete works | 13 | 57 | 70 |
| Awaiting commissioning | 2 | 11 | 13 |
| Total | 371 | 258 | 629 |

Table 35 indicates that 547 facilities were completed. Eighty-two facilities were ongoing comprising of 19 health centers and 63 seed secondary schools. The verification also showed that 70 facilities were incomplete, comprising 57 schools and 13 Health Centres. Another 13 facilities were awaiting handover or commissioning, comprising 11 schools and 02 Health Centres. Some facilities were providing services while works remained incomplete.

## Location and Name changes

The verification exercise established that there were mismatches between information from the programme list and what was found on the ground. Out of 629 programme-list entries, 606 (96.3%) had supporting returns and 23 (3.7%) had discrepancies requiring reconciliation. These include entries on the programme list without matching returns or with conflicting location or facility-type information. Table 36 provides the details.

Table 36: Inconsistencies between the programme list and the facilities found

| Status | Health centres | Schools | Total | Facilities |
| --- | --- | --- | --- | --- |
| Facilities on the programme list but not on ground | 7 | 3 | 10 | Health centres: Olok HC II (Pader); Alik HC II (Lira); Acimi HC II (Oyam); Acokara HC II (Oyam); Ariba HC II (Oyam); Busia Eastern Division (Busia Municipal Council); Butoloogo HC II (Kassanda) Seed schools: Eastern Division (Tororo Municipal Council); Central Division (Jinja City); Kishangara Seed School (Ibanda) |
| Not a UgIFT beneficiary | 2 | 1 | 3 | Health centres: Alira HC II (Oyam); Buyinda HC II (Kaliro) Seed schools: Kiziranfumbi Seed School (Kikuube) |
| Exists with no UgIFT assets | 2 | 3 | 5 | Health centres: Pandwong HC II (Kitgum Municipal Council); Rwamujojo HC II (Sheema Municipal Council) Seed schools: Bumbaire Seed School (Bushenyi); Kyamuhunga (Bushenyi); Kashenshero (Mitooma) |
| UgIFT assets relocated to another facility | 2 | 1 | 3 | Health centres: Alangi (Zombo) to Amwonyo HC III; Ther-uru HC II (Zombo) to Atyak HC III Seed schools: Abanga (Zombo) to Kango SSS |
| Represented by another name | 2 | 0 | 2 | Health centers: Loinya HC II in Maracha (H213) was replaced by Liko HC III (H212), Bussi HC II in Wakiso (H054) is treated as a village name for Zinga Health Centre III (H052). |
| Total | 15 | 08 | 23 |  |

## Impact of UgIFT Programme on service delivery

Of the 284 health centres, 238 (83.8%) reported at least one benefit from the UgIFT support. Improved maternity and delivery services were reported by 117 (41.2%), and 51 (18.0%) reported more or safer births at the facilities. Improved antenatal, immunisation, laboratory or other specific services were reported by 89 (31.3%), improved access to care or shorter distances by 71 (25.0%) and more patients’ attendance reported by 61 (21.5%). More than half, 164 (57.7%), linked better services to the equipment and furniture supplied.

Of the 193 seed schools, 144 (74.6%) reported at least one benefit. A better learning environment, with classrooms, furniture and libraries, was reported by 74 (38.3%), and improved access to secondary education or shorter distances by 59 (30.6%). Practical science or ICT teaching improved at 39 schools (20.2%), and 37 (19.2%) reported higher enrolment. Forty schools (20.7%) also reported jobs and local economic benefits around the school. Figure 44 compares the benefits reported by the two types of facility.

## Gaps and Challenges

The main gaps identified by the facilities include;the following below as indicated in figure 9

- Insufficient Power supply which was reported by 201 facilities (42.1%), including 44.4% of Health Centre respondents and 38.9% of school respondents;

- Inadequate Staffing which was reported by 32.1% of the facilities (153 of 477).

- Inadequate space or infrastructure reported by 31.7% of the facilities (151 of 477).

- Insecurity or absence of fencing reported by 27.0% of the facilities (129 of 477).

- Limited maintenance support was raised by 22.2% of the facilities (106 of 477).

- Inadequate staff houses reported by 22.0% of the facilities (105 of 477).

- Poor water supply reported by 20.1% of the facilities (96 of 477).

- inadequate training of staff to operate the equipment reported by 28.9% of the health centres (82 of 284), and 1.6% of schools (three of 193).

- Incomplete or delayed works, handover or commissioning reported by 28.0% of Seed Secondary School respondents (54 of 193) and 10.2% of Health Centre respondents (29 of 284).

- Equipment not installed, not assembled or delivered incomplete was raised by 17.6% of the facilities (84 of 477).

Figure 9: Service gaps and challenges

# 4 ASSET MANAGEMENT

## 4.1 Maintenance and repairs

Most of the verified assets were furniture, clinical equipment and computers in daily use at Health Centres, seed schools and MDAs.  During the verification, each facility reported how it maintains, repairs, services or replaces UgIFT assets and whether it keeps a regular record of their functionality or breakdown.

Repair arrangements: Most facilities (Include percentage) reported maintaining of the provided assets. However, the maintenance arrangements varied by facility. All MDAs reported using own funds for maintenance and repairs. At LG level it was noted that 260 (55.4%) met repairs at facility level, with own funds (Primary Health Care funds 33.8%) for health centres while capitation or Universal Secondary Education grant, (52 of 191, 27.2%). for schools. 152 facilities (32.4%) relied on external support for maintenance either citing support from district or higher-level facilities, hired technicians and artisans 27 (5.8%); and contractors or suppliers under defects liability, guarantee or warranty 12 (2.6%).

A significant proportion of facilities (97 facilities (20.7%) with schools accounting for 59, had not yet needed maintenance because the assets were new, some not yet handed over or the buildings were still under construction, and 36 (7.7%) reported no repair arrangement, with broken items set aside or not repaired. However, (6.3%) of the facilities reported insufficient funds for maintenance of assets, particularly for major repairs. At Kyankaramata Health Centre III in Kyenjojo, Primary Health Care funds met minor repairs, but the cost of major repairs was a constraint.

Asset condition/Life cycle tracking: The verification noted that a small proportion of facilities 13.7% (68) kept track of the asset condition/lifecycle. Of these 10.1% (50) had fixed maintenance interval with facilities 28.0% (14) checking asset condition annually, 22.0% (11) monthly, 20.0% (10) quarterly, 18.0% (9) every school term, 6.0% (3) twice a year and 6.0% (3) weekly. Eighteen (18) facilities (3.6%) depended on routine/scheduled servicing by regional referral hospital maintenance teams as shown in Figure 10. Furthermore, 12.3% (61 facilities) repaired their assets as need arose.

Figure 10: Asset condition tracking intervals

Asset Records management: Of the 629 facilities, 354 (56.3%) facilities had asset records. Of these, 318 (89.8%) kept a regular record of asset functionality or breakdowns, 36 (10.2%) kept partial or informal records. On the other hand, 275 (43.7%) had no records at all, because the assets were new or the facility was not yet operating. Records indicated that some assets were obsolete and unserviceable for example; two wall-mounted aneroid blood-pressure machines at Nyanja Health Centre III, UGIFT-012842 and UGIFT-012843, were reported as spoilt, beyond repair and requiring replacement.

In addition, records indicate that some assets were reported stolen, others not received, while others equipment had missing accessories. Example of these include; the incubator at Buwembe Health Centre III (UGIFT-114904) and the ENT instrument set at Rubingo Health Centre III (UGIFT-188911) were reported not received. At Paloga Seed Secondary School, two monitors were reported stolen.

Asset Disposal: The verification exercise noted lack of a clear asset planning and disposal process for UgIFT assets across the facilities. Obsolete assets and faulty equipment remained at the facilities with no specific disposal schedules due to lack of UgIFT asset disposal guidelines.

# RECOMMENDATIONS

Adopt a fixed routine asset condition check in addition to already existing routine checks from external stakeholders. A condition check at least every school term in schools and every quarter in health centres, and a full count of UgIFT assets each year. Each facility should keep a condition book or fault list naming each item requiring action, the responsible person and the agreed completion date; District health and education offices should review unresolved repairs each quarter and arrange technical assistance, and regional referral hospital workshops should include UgIFT equipment in their scheduled visits. Facilities should prepare annual maintenance plans separate minor repairs from major repairs.

Fast track outstanding buildings, utilities, furniture and equipment: LG Accounting Officers, engineers, health and education officers and contractors should fast track outstanding buildings, utilities, furniture and equipment through site-specific completion plans for each of the 83 documented facilities with works or handover outstanding, comprising seventy with incomplete works and thirteen awaiting handover or commissioning.

Provision of user training: District technical officers suppliers and regional technical teams should provide user training or practical training for staff who use specialist equipment. This is especially so since some Health Centres pointed idle equipment to a lack of skills, including oxygen equipment users, for example, at Bubago and Sop Sop and staff requiring orientation at Avogera. Handover should include a demonstration, basic maintenance guidance and a named route for technical support. Future supply contracts should make on-site demonstration to the staff who will use the equipment, a condition of acceptance.

Assign Unique programme Identifiers to UgFT assets. The program secretariat should engrave all the verified assets with UgIFT markings and confirm their locations and custodians. Assets carrying another marking only should receive the programme identifier

Report asset Losses: All lost assets should be reported and investigated under the public finance rules, and every facility should hold a list of the UgIFT assets it received, showing each item, its engraving and its custodian. Maintain site, ownership and handover records for buildings and land.

Leverage LG performance assessment: MoFPED and LGs should utilize the assessment process to track the life of assets and use it to plan for asset disposal.

Issue UgIFT asset planning and disposal guidelines: The responsible government agencies should issue UgIFT asset-planning and disposal guidelines and ensure that all Accounting Officers who holds UgIFT assets apply the guideline. Each facility manager should submit a list of assets that are obsolete, beyond repair for inclusion in the procurement and disposal schedules

# APPENDICES

  - Asset Register

  - Photographs

The four land entries were for Kyamwinula Health Centre III (UGIFT-119332), Sop Sop Health Centre III (UGIFT-128460), Nalubembe Health Centre III (M161488) and Kabweri Health Centre III (M183544). Dimensions are stated only for Sop Sop, at 70 × 300 metres.