# Kapchorwa Mc District - local government report

# 1. Identification

| Local government | Kapchorwa Mc |
| --- | --- |
| Region / sub-region | Eastern / Elgon |
| Team | Team 15 - Alybo Marry Topista, Shadrack Biyinzika, Nakiwala Doreen |
| Supervisor | Kassim Luminsa |
| Dates worked | 2026-08-30 to 2026-08-31 |
| Date of submission |  |

# 2. Coverage

| Facility | Type | State | Return | Photographs |
| --- | --- | --- | --- | --- |
| Kaplelko HC III | Health centre | verified | Incomplete | 26 |

Allocated 1 · reported on 1 · verified 1. 26 photographs. Hand-filled registers that name their facilities are on file. Word toolkits are written up as each booklet is gone through; the rest stay photographed until then.

Every return above is marked incomplete where a hand-filled register has not yet been written up into the programme toolkit, or where ownership, usage or another required dimension is still open. What else is missing at a facility is set out in that facility's own report.

# 3. The local government record

| Required | Status |
| --- | --- |
| Courtesy call on the CAO or Town Clerk | No record |
| Record of assets held at the district | No record |
| Interviews with the CFO, DEO and DHO | No record |
| Debrief to the local government | No record |

The delivery notes obtained in this local government were held at the facilities themselves. The district produced nothing of its own.

# 4. Key findings

Kaplelko HC III was worked and its hand-filled booklet has been written up into the programme toolkit.

Most items were recorded as not yet engraved or not tagged, against a field note that most things at Kaplelko are engraved - that difference is an open item.

No municipal record of programme assets is on file.

# 5. Supplied against found

No municipal delivery note for Kaplelko HC III is on file. Found stands on what the team recorded and the hand-filled booklet alone.

# 6. Obsolete, unserviceable or for disposal

Nothing was reported as obsolete or unserviceable.

# 7. Outstanding queries

2 open items are carried with the district record. Each is given here in one line; the full wording sits with the record.

Kaplelko HC III's hand-filled booklet is on file and has been written up.

No separate municipal record of programme assets is on file.

# 8. Sign-off

| Verifier | Not signed |
| --- | --- |
| Supervisor | Kassim Luminsa - not signed |
| Date of submission |  |