# Kapchorwa District - local government report

# 1. Identification

| Local government | Kapchorwa District |
| --- | --- |
| Region / sub-region | Eastern / Elgon |
| Team | Team 15 - Alybo Marry Topista, Shadrack Biyinzika, Nakiwala Doreen |
| Supervisor | Kassim Luminsa |
| Dates worked | 2026-08-28 to 2026-08-31 |
| Date of submission |  |

# 2. Coverage

| Facility | Type | State | Return | Photographs |
| --- | --- | --- | --- | --- |
| Chemosong HC III | Health centre | verified | Incomplete | 35 |
| Kabeywa Seed Secondary School | School | verified | Incomplete | 14 |
| Kaptanya Seed Secondary School | School | verified | Incomplete | 18 |
| Ngangatta HC III | Health centre | verified | Incomplete | 10 |

Allocated 4 · reported on 4 · verified 4. 77 photographs. Hand-filled registers that name their facilities are on file. Word toolkits are written up as each booklet is gone through; the rest stay photographed until then.

Every return above is marked incomplete where a hand-filled register has not yet been written up into the programme toolkit, or where ownership, usage or another required dimension is still open. What else is missing at a facility is set out in that facility's own report.

# 3. The local government record

| Required | Status |
| --- | --- |
| Courtesy call on the CAO or Town Clerk | No record |
| Record of assets held at the district | No record |
| Interviews with the CFO, DEO and DHO | No record |
| Debrief to the local government | No record |

The delivery notes obtained in this local government were held at the facilities themselves. The district produced nothing of its own.

# 4. Key findings

Four facilities were worked and each has a hand-filled booklet on file. Kabeywa Seed Secondary School's booklet has been written up; Kaptanya, Chemosong and Ngangatta remain to be written up from their photographed pages.

Kabeywa reported serious ICT losses. Twenty-three of twenty-eight UPS units were stolen and the projector was reported lost.

The district offices were visited, but no visitors' book from the CAO or Town Clerk is on file and no district asset record was obtained.

Ngangatta HC III returned its booklet without a separate field-photo set, so the register pages are the main evidence on file for that facility.

# 5. Supplied against found

No district delivery note for Kapchorwa programme assets is on file. Found quantities come from what the team recorded and the hand-filled booklets; supplied cannot yet be set against them.

Kaptanya Seed Secondary School has an ICT delivery note on file; its lines have not yet been worked through against what was seen.

# 6. Obsolete, unserviceable or for disposal

Chemosong HC III - Hospital beds - 2 broken.

Nothing was recommended for disposal in terms.

# 7. Outstanding queries

3 open items are carried with the district record. Each is given here in one line; the full wording sits with the record.

Hand-filled booklets for Kapchorwa facilities are on file and still being written up.

No visitors' book from the Kapchorwa CAO or Town Clerk office is on file.

Kabeywa Seed Secondary School reported twenty-three UPS units stolen and a projector lost.

# 8. Sign-off

| Verifier | Not signed |
| --- | --- |
| Supervisor | Kassim Luminsa - not signed |
| Date of submission |  |