## FIELD REPORT ON UgIFT ASSET VERIFICATION.

## Facility visited: KATARAZA HC III

## Introduction

The field exercise was conducted to verify UGIFT assets in kyankaramata HC III in kyenjojo district. The exercise involved onsite physical verification of all asset acquired under UgIFT program for the period 2018-2025. This was intended to establish the status of the assets and identify any issues requiring follow-up

Process/ methodology.

The team kick started the exercise with a courtesy visit to the office of the Chief administrative officer, kyenjojo district local government where it met with the deputy chief administrative officer and then had an entry meeting with the team in his office. The team present an introductory letter where he recommended and forwarded the team to the relevant officers, in charges /head teachers at schools and health centres funded by UGIFT.

After the meeting Chief administrative officer with, the team dispatched to different facilities where I, went to Kataraza hc III in kyenjojo district.

At Kataraza hc III, the incharge had an inventory book where assets are listed with their sources including those received from UGIFT.

The exercise involved physical counting and verification of assets, taking photographic evidence of the available equipment.

The absence of asset registers both at the district offices and health centres slowed down the verification process and some crucial information on asset numbers, life in months among other parameters could not be obtained.

Majority of the equipment supplied especially beside lockers were broken, medical sets were still in the store and health workers at the facility could not identify them in the store and were unaware of their availability.

Inadequate storage at health centres was also a challenge, to properly store UGIFT assets.

In addition, the facility staff did not know the some of the medical equipment, their functions, and that they were supplied with some equipment that should be used in schools e.g. counting chambers, glucometers were supplied with strip, but they were used up and the facility could not get their replacement from NMS

# Recommendations

The staff should be reoriented in how to use the different medical equipment at their facility to improve service delivery. The durability of furniture should be closely monitored so that facilities do not incur immediate repair costs after a month of order delivery.

Facility in charge should be involved during the procurement of medical equipment so that issues of over stock and facility needs are catered for. A CBC Machine and an ultra-sonic sound scan should be included on the supply lists.