## FIELD REPORT ON UgIFT ASSET VERIFICATION.

## Facility visited: BUTAWATA HC III

## Introduction

The field exercise was conducted to verify UGIFT asset butawata HC III in mubende district. The exercise involved onsite physical verification of all asset acquired under UgIFT program for the period 2018-2025. This was intended to establish the status of the assets and identify any issues requiring follow-up

Process/ methodology.

The team kick started the exercise with a courtesy visit to the office of the Chief administrative officer, kyenjojo district local government where it met with the deputy chief administrative officer and then had an entry meeting with the team in his office. The team present a copy an introductory letter from SK & CO. to the CAO Who recommended and forwarded the team to the relevant officers, in charges /head teachers at schools and health centres funded by UGIFT.

After the meeting Chief administrative officer with the team, dispatched to different facilities where I, went to butawata hc III.

At hc III, the incharge did not have an asset register, however a small functionality list was availed and supplemented by information given by the store personnel for items received from UGIFT.

The exercise involved physical counting and verification of assets, taking photographic evidence of the available equipment.

The absence of asset registers both at the district offices and health centres slowed down the verification process and some crucial information on asset numbers, life in months could not be obtained.

Un assembled equipment at the health facility made it hard to verify some assets since they were tightly packed in the store.

In addition, the facility staff did not know the some of the medical equipment, their functions, and that they were supplied with some equipment that should be used in schools e.g. counting chambers. Glucometers were supplied with strip, but they were used up and the facility could not get their replacement from NMS

She also complained about the quality of office chairs and tables that were delivered to her facility that lasted only 2 weeks and were spoilt and that some equipment was too expensive to be replaced by the facility.

# Recommendations.

Facility in charge should be involved during the procurement of medical equipment so that issues of over stock and facility needs are catered for.

She recommended that CME, on equipment use should be arranged for health workers after delivery of these items, and that they should be involved in the procurement of the equipment to avoid over supply which causes storage problems