CONSULTANCY SERVICES TO VERIFY AND RECORD ASSETS UNDER THE UGIFT PROGRAMME

REF: MOFPED/UGIFT/CONS/25/26/00015

ASSET VERIFICATION REPORT

SUBMITTED BY:

Plot 31, Bukoto Street

P.O Box 7657, Kampala, Uganda
+256 (0) 39 2000216/0772525235
email: cpa@cpa.ug

# www.cpa.com

September 2026

Table of Contents

Executive summary	4

1	Introduction and background	5

1.1	Introduction	5

1.2	Background to the verification	5

1.3	Justification	7

1.4	Objectives of the assignment	7

1.5	Scope of Work	7

1.6	Expected deliverables	7

2	Approach and methodology	8

2.1	Preparation:	8

2.2	Data collection	8

2.3	Quality assurance	9

2.4	Asset categories, condition, use and identification	9

2.5	Financial analysis and Valuation	9

2.6	Analysis and reporting	9

2.7	Challenges and Limitations to the assignment	9

3	Findings	11

3.1	Overall results	11

3.2	National level Ministries and Agencies results	18

3.3	MDA specific results	19

3.3.1	Ministry of Finance, Planning and Economic Development	19

3.3.2	Ministry of Works and Transport	20

3.3.3	Ministry of Education and Sports	21

3.3.4	Ministry of Agriculture, Animal Industry and Fisheries	22

3.3.5	Ministry of Health	23

3.3.6	Office of the Prime Minister	23

3.3.7	Ministry of Water and Environment	24

3.3.8	Ministry of Gender, Labour and Social Development	25

3.3.9	National Environment Management Authority	25

3.3.10	Public Procurement and Disposal of Public Assets Authority	25

3.3.11	Office of the Auditor General (OAG)	26

3.3.12	Ministry of Local Government	26

3.3.13	Ministry of Lands, Housing and Urban Development	27

3.4	Results from blood banks	28

3.4.1	Condition of assets	28

3.4.2	Identification, including engraving	29

3.4.3	Financial aspects	30

3.5	Local government level results	33

3.6	Health Centres	33

3.6.1	Availability of the assets	33

3.6.2	Condition of Assets	34

3.6.3	Identification	35

3.6.4	Financial aspects	36

3.7	Seed Secondary Schools	37

3.7.1	Availability of the assets	37

3.7.2	Condition of assets	37

3.7.3	Identification	38

3.7.4	Financial aspects	38

3.8	Field Observations,	41

3.8.1	Location and Name changes	41

3.8.2	Complete works and bring stored assets into use	44

3.8.3	Service delivery Improvements	45

4	Asset management	46

4.1	Maintenance and repairs	46

5	Recommendations	49

6	Annexures	52

List of acronyms

GOU	Government of Uganda

HC	Health centre

ICT	Information and communications technology

IFMIS	Integrated Financial Management Information System

KCCA	Kampala Capital City Authority

LGFC	Local Government Finance Commission

MAAIF	Ministry of Agriculture, Animal Industry and Fisheries

MDA	Ministry, department or agency

MoDVA	Ministry of Defence and Veteran Affairs

MoES	Ministry of Education and Sports

MOES	Ministry of Education and Sports (as engraved)

MoFPED	Ministry of Finance, Planning and Economic Development

MoGLSD	Ministry of Gender, Labour and Social Development

MoH	Ministry of Health

MOH	Ministry of Health (as engraved)

MoLG	Ministry of Local Government

MoLHUD	Ministry of Lands, Housing and Urban Development

MoPS	Ministry of Public Service

MoWE	Ministry of Water and Environment

MoWT	Ministry of Works and Transport

NEMA	National Environment Management Authority

OAG	Office of the Auditor General

OPM	Office of the Prime Minister

PforR	Program-for-Results

PPDA	Public Procurement and Disposal of Public Assets Authority

RCU	Reform Coordination Unit

TELA	Teacher Effectiveness and Learner Assessment

UBTS	Uganda Blood Transfusion Services

UgIFT	Uganda Intergovernmental Fiscal Transfer

UGX	Uganda shillings

UPS	Uninterruptible power supply

# Executive summary

# Introduction and background

## Introduction

This report presents the findings of the UgIFT asset verification undertaken by the Ministry of Finance, Planning and Economic Development as part of programme closure activities. It sets out the status of the assets provided by the programme to the targeted national institutions responsible for supporting the implementation of the programme, Blood Banks and local governments specifically targeting seed secondary schools and health facilities upgraded from Health Centre II to Health Centre III.

## Background to the verification

The Uganda Intergovernmental Fiscal Transfers (UgIFT) Programme is a government programme implemented through a Programme-for-Results (PforR) launched and aligned with the broader IGFT Reform Programme (2015). UgIFT 1.0 began with US$200 million in FY2017/18, supporting Education and Health. This was later expanded through additional financing of US$300 million, including US$240 million in credit and US$60 million in grants, with US$50 million from the IDA Refugee Support Window, expanding beyond Education and Health to water and Environment and Agriculture (micro-scale irrigation) making the overall funding total of US$500 million.

The Intergovernmental Fiscal Transfer Reform Programme (IGFT RP) was revised in 2020 to align with the Third National Development Plan (NDP III 2020/21 - 2024/25), and to directly contribute to Four (04) Programmes i.e. Human Capital Development; Public Sector Transformation; Natural Resources, Environment, Climate change, Land and Water Management; and Development Plan Implementation.

Overall, the development objective of the UgIFT Programme was to: “Improve the adequacy, equity, and effectiveness of financing and the oversight, management, and delivery of Local Government services in Education, Health, Water and Environment, and Agriculture (micro-scale irrigation), including refugees and their host communities”.

Specifically, the Programme sought to:

- Increase the adequacy and predictability of fiscal transfers to Local Governments for service delivery;

- Improve the equity and transparency of allocation mechanisms through the introduction of formula-based transfers;

- Strengthen performance incentives and accountability systems for Local Governments; and

- Expand access to quality education and health infrastructure, particularly in under-served areas.

The UgIFT Programme had four components aimed at strengthening the intergovernmental fiscal transfer system while supporting investments in service delivery infrastructure. These included;

Component 1: Reform of the Intergovernmental Fiscal Transfer System

This supported the design and implementation of a reformed fiscal transfer framework based on objective and transparent allocation criteria. This resulted into introduction of formula-based grants - Revised allocation formulas reflecting population, infrastructure gaps, and service delivery needs.

Component 2: Education Infrastructure Development

This component financed the construction and upgrading of education facilities, particularly government secondary schools in under-served sub-counties. This involved construction and equipping of new secondary schools - classrooms, laboratories, administration blocks, sanitation facilities, teachers’ houses, furniture and ICT equipment in the different local governments.

Component 3: Health Infrastructure Development

This supported investments in health facilities to improve access to primary health care services at the local level. The major outputs under the component were construction and upgrading of health centers - Staff accommodation, sanitation facilities and provision of medical equipment.

Component 4: Local Government Performance and Institutional Strengthening

This aimed at Strengthening local government capacity in planning, budgeting, procurement, and infrastructure management. Under this component, Annual local government performance assessments have been undertaken across the 176 Local governments, capacity building and technical support strengthened monitoring and reporting systems across the Local governments.

The Programme was implemented through a clearly defined results framework that connected actions and incentives across three levels of government to strengthen service delivery outcomes. The programme came to an end in December 2025 and had accomplished the following outputs under the different components;

- Budget Support

- Education: 196 of 259 Seed Schools are complete of which 189 are operational.

- Health: 354 of 373 health facility upgrades/new constructions (HC II to HC III) are complete.

- Water and Environment: 758 - piped water systems, 5,398- point water sources, 7,082 water supply systems rehabilitated, 325 designs completed, and 256 sanitation facilities in the targeted service units.

- Agriculture (Micro-scale Irrigation): Over 6,235 irrigation systems were installed (4,843 hectares under irrigation), 632 irrigation demonstration sites in 135 LGs set up.

- Refugee intervention: 51 primary schools and 35 health facilities in refugee hosting districts (RHD) were transitioned and integrated into the LG service.

- Blood Banks: Regional Blood Banks in Arua and Hoima were completed and commissioned while Soroti Regional Blood Bank was rehabilitated.

- Grant management

Assets for institutional strengthening and retooling including ICT equipment and vehicles were provided. The Ministry of Finance, Planning and Economic Development (MoFPED) through PFM Coordination Unit (RCU) manages the Government of Uganda counterpart funding of the programme to support the grant management component of the UgIFT programme. The grant management supports in financing of Central Government actions intended to achieve programme objectives and Disbursement Linked Indicators (DLIs). To this end, MoFPED through RCU supported MDAs to acquire different assets meant to support programme implementation.

## Justification

The UgIFT programme came to an end on 31st December 2025. As part of the programme’s closure activities, MoFPED, through RCU, commissioned an end-of-programme asset verification exercise to take stock of the assets procured under the programme and to establish where those assets were, how they were being used as part of the processes to hand them over to government for sustainability purposes.

## Objectives of the assignment

The objective of the assignment was to undertake verification and recording of all assets acquired under the UgIFT Programme. Specifically, the assignment intended to;

- Identify and verify the existence of the assets

- Verify the assets condition and status: specifically, the condition on functionality, usage/performance and location among others

- Assess financial management aspects: residual value of the investments/hardware/tools for purposes of financial reporting for project closure

- List the assets that are obsolete, unserviceable and require disposal

- Develop a computerized database of the investment/hardware/tools to facilitate recording of new deployed assets/investments.

- Undertake PFM Assessment on Asset Management practices (including sustainability, Operations and Maintenance) of the UgIFT implementing LGs

## Scope of Work

The assignment all institutions at National and local government that directly implemented the UgIFT program from coordination, support and implementation across the country. At the local government level, the study focused on upgradedimproved health facilities and seed secondary schools only as these had received assets upgraded under the programs as a result.

Specifically, the assignment involved the following tasks;

- Verification of the Asset’s Records of targeted ministries departments and agencies and local governments

- Physical and Functional Verification of assests

- Data Consolidation for generation of a single data base of assets provided by the program

- Generation of an IFMIS ready Asset Register for Integration, and Migration into IFMIS

- Review of the UgIFT Asset Management Practices

## Expected deliverables

Key expected outputs of the consultant include:

- Report with the list and current status of assets acquired under the programmes;

- An automated up-to-date assets data base of UgIFT Investments across MDALGs;

(iii)	Report on the estimated value of assets under the programme as well as operations and maintenance arrangements;

(iv)	IFMS-Ready Asset Register and Data Migration Report

(v)	Report on functionality of assets relating to systems investments;

(vi)	Report on Assessment of Asset Management Practices, Risks and recommendations.

# Approach and methodology

The verification exercise was conducted using a participatory and consultative process and implemented in three interlinked phases: Preparatory and inception phase, Data collection phase and the report writing phase.

## Preparation:

The Inception phase was completed and the inception report submitted on 18th June 2026 which provided an agreed scope, approach and work plan for the exercise. The team also undertook a pilot test in Wakiso District Local Government, with verification carried out at Buloba Health Centre III and Sumbwe Seed Secondary School, which helped in design of data collection tool and the deployment plans.

## Data collection

This exercise was undertaken in two phases first at National level and later at the Local government level.

National level: Physical visits to verify assets provided by the programme at the national-level was completed on the 19th of August 2026. This covered 15 MDAs including; Ministry of Works and Transport (MoWT); Ministry of Education and Sports (MoES); Ministry of Agriculture, Animal Industries and Fisheries (MAAIF); Ministry of Health (MoH); Office of the Prime Minister (OPM); Ministry of Water and Environment (MoWE); Ministry of Gender, Labour and Social Development (MoGLSD); Local Government Finance Commission; National Environment Management Authority (NEMA); Public Procurement and Disposal of Assets Authority (PPDA); Office of the Auditor General (OAG); Ministry of Public Service (MoPs); Ministry of Lands, Housing and Urban Development (MoLHUD); Ministry of Local Government (MoLG) and Ministry of Finance, Planning and Economic Development (MoFPED). Additionally, three Blood Banks of Hoima, Arua and Soroti were covered.

Local government level: The local government verification covered all UgIFT upgraded/ constructed Health Centres and Seed Secondary Schools in all the 176 LGs. The process began with a training of field teams prior to the actual field verification.

Training of field teams:  A total of 85 Research Assistants (RAs) and 7 Regional Supervisors were trained. The training took place from 21st to 23rd August 2026 and physical verification started on the 24th of August 2026 across all the 176 Local governments. During the Asset verification, the RAs visited Seed Secondary Schools, Health Centres and Blood Banks.

Physical verification: This exercise commenced on the 24th of August 2026 and was completed on 17th September 2026. The local government physical verification involved entry meetings with the LG leadership at the LG headquarters for authorization and review of reports relating to UgiFT assets, key informant interviews with the technical teams especially the Chief Administrative Officers, Finance Officers, District Health Officers and District Education Officers. Thereafter, the RAs proceeded to the facilities for physical verification of the assets.

At local government level, the programme list had 629 facilities: 371 health centres and 258 seed secondary schools. The list recorded 547 facilities (87.0%) as complete and 82 (13.0%) as ongoing. The ongoing works were more common among seed secondary schools (63, or 24.4%) than among health centres (19, or 5.1%).

## Quality assurance

Regional supervisors checked daily field activity and reviewed the completed tools. The central technical team carried out spot checks and helped resolve operational questions. Teams compared institutional asset information with the items and explanations provided during visits, while supervisors referred matters requiring clarification to the team leader and field coordinator.

## Asset categories, condition, use and identification

Asset categories. Each asset was counted once and assigned to one report category. Health centre assets were grouped as clinical equipment, clinical furniture, maternity ward equipment and health centre ICT equipment. On the other hand, seed secondary school assets were grouped as school furniture, school computers and related equipment and school support equipment. Another category included other ICT equipment, other furniture, vehicles, motorcycles and buildings, which apply to MDAs, Blood Banks and LGs alike.

Condition and use. Condition and use were reported as recorded for each asset during the verification. A working asset is one recorded as functional and in use. An asset recorded as faulty was reported as not working and not in use. This included assets that were broken down or damaged. An asset that was new and in store was recorded as functional but not in use. Additionally, an asset that was held elsewhere, not yet delivered or awaiting power installation, completion of buildings or trained users, was also recorded as functional but not in use.

Identification. An asset is properly identified when carried a UgIFT programme marking. However, there were other assets that had no UgIFT marking but the officers on ground identified them as UgIFT assets.

## Financial analysis and Valuation

The Government of Uganda Asset Accounting Policies and Guidelines 2023 was used to determine the recorded values, depreciation and net book values.

## Analysis and reporting

Analysis and reporting was done through triangulation of the literature from different policy, Planning and Financial documents including: the Government of Uganda Asset Accounting Policies and Guidelines 2023; asset registers; asset records at national and local government levels; physical inspections; discussions with facility managers; photographs and asset counts for each institution.

## Challenges and Limitations to the assignment

Difficult terrain and poor physical accessibility of facilities: Physical accessibility presented a significant operational challenge especially for facilities located in areas characterised by difficult terrain and limited transport accessibility such as Bwesumbu HC III, Bwesumbu Seed School, Buhuhira and Kabingo in Kasese District. In addition, accessing facilities within the Island was difficult, time consuming and expensive. This led the teams to overshoot the anticipated time for data collection.

High transportation cost: Given the national wide coverage, the rising fuel prices led to high field costs. The field teams spent more money than was anticipated. The costs were extra ordinarily higher for island facilities like Kalangala, Buvuma, Mayuge among others. For instance, Kalangala had 3 facilities with long distance on water that required hiring a private boat since it was not a common route to the transporters and outside the ferry schedules. A similar situation was encountered in Buvuma and Namayingo districts.

Poor record keeping: In many LGs and facilities, there were no clear records about the assets delivered under UgIFT. The LGs and the facilities had incomplete or missing UgIFT asset registers which delayed data collection. Subsequently, the teams took longer in such facilities identifying the assets as most of these were not engraved with the UgIFT identifiers while others were not engraved at all. In addition, the field teams encountered situations where some Assets could not be physically accessed especially for schools since it was holiday time.

# Findings

This section presents results of the verification exercise based on the specific objectives. The results are presented in different results levels indicating availability of assets, asset condition and functionality, asset marking and identification and the financial analysis in each of the subsections.

## Overall results

This section provides an overall view of the UgFT asset status combining both National level agencies and schools and health centres.

- Overall asset availability

Physical verification of all UgFT assets across the targeted MDAs, beneficiary Blood Banks, Upgraded Health Centres and Seed Secondary Schools indicated a total of 226,280 assets of different categories including Vehicles, Laptops, Printers, Desktop Computers, Projectors, Furniture (desks, chairs, stools), UPS Systems, Digital Phones, Paper Shredders, Mobile Tablets, clinical equipment’s among others.

Overall, the Seed Secondary Schools hold the majority of assets 64.2% (145,376) followed by the Health Centres with 28.1% (63,606), the MDAs hold 7.4% (16,668) while the Blood Banks held the least number of assets at 0.3% (626) as indicated in Figure 1.

Figure 1: Overall distribution of UgFT Assets

Source: Primary data analysis

- Overall asset Condition and functionality

Overall, 215,879 assets constituting 95.4% were in good condition, 3,392 assets (1.5%) were broken, while 7,009 (3.1%) were not in use. Of all assets in good condition, 94% were in use, while 1.4% were in store not yet used. The detailed analysis of the overall asset condition is indicated in table 1.

Table 1: Overall condition of UgFT assets and functionality

| Institution | Assets verified | Good condition |  | Broken | Other |
| --- | --- | --- | --- | --- | --- |
|  |  | In use | In store |  |  |
| MoFPED | 458 | 458 | 0 | 0 | 0 |
| MoWT | 88 | 72 | 0 | 0 | 0 |
| MoES | 10,783 | 10,783 | 0 | 0 | 0 |
| MAAIF | 2,045 | 2,045 | 0 | 0 | 0 |
| MoH | 264 | 263 | 0 | 1 | 0 |
| OPM | 10 | 7 | 0 | 3 | 0 |
| MoWE | 2,939 | 2,939 | 0 | 0 | 0 |
| MoGLSD | 10 | 10 | 0 | 0 | 0 |
| NEMA | 6 | 6 | 0 | 0 | 0 |
| PPDA | 5 | 5 | 0 | 0 | 0 |
| OAG | 20 | 20 | 0 | 0 | 0 |
| MoLG | 13 | 13 | 0 | 0 | 0 |
| MoLHUD | 27 | 27 | 0 | 0 | 0 |
| Health centres | 63,606 | 57,921 | 2,629 | 660 | 2,396 |
| Seed secondary schools | 145,376 | 137,585 | 490 | 2,722 | 4,579 |
| Blood banks | 626 | 602 | 0 | 6 | 18 |
| Total | 226,280 | 212,760 | 3,119 | 3,392 | 7,009 |
| Overall proportion |  | 94.03% | 1.38% | 1.50% | 3.10% |

Source: Primary data analysis

As indicated in table 1 above, most of the deployed assets were already in service while some were in store and still in good condition but not in use. This was attributed mainly to some localized challenges such as power, incomplete structures, untrained staff, among others. Some assets were broken mainly furniture in Seed Secondary Schools and require repair. Verification also noted that over 7000 assets mainly in seed secondary schools and health centres had not been used requiring installation or the facility itself was not yet ready. Figure 2 shows the reasons for non-deployment of some of the assets even when they were found to be in good condition.

Figure 2: Reasons for idle or unused assets and equipment

Source: Primary data analysis

Notable among the facilities include Lungulu Seed Secondary School in Nwoya District where desktop computers, a printer and UPS units were still boxed because the school was waiting for power connection. At Nansanga Seed Secondary School in Budaka, 27 of 28 desktop computers remained packed for lack of reliable power. Broken desks and stools were in classrooms and stores at Seed schools in Namisindwa and Napak. At Arua Regional Blood Bank, six blood pressure machines were damaged or not functional. The information above is depicted in some of the photos presented below.

| Delivery bed with a torn mattress cover at a health centre, Busia District (Bukedi) | Pedal suction unit marked MAJANJI H/C III still in its packing, recorded as not in use for lack of technical knowledge, Majanji Health Centre III, Busia District (Bukedi) |
| --- | --- |
| Stacked desks, chairs and stools, some recorded as broken and none engraved, at Napak Seed Secondary School, Napak District (Karamoja) | Cracked health centre block above collapsed ground, Bulambuli District (Bugisu) |
| Broken desk frame at a seed secondary school, Namisindwa District (Bugisu) | Empty ICT and library block with a few chairs and items kept in one corner at Iriiri Seed Secondary School, Napak District (Karamoja), not yet in use while the school remained with the contractor |
| Stained and peeling ceiling at a health centre, Sironko District (Bugisu) | Flood-affected older health facility at Butiaba, Buliisa District (Bunyoro) |
| Desktop computers, a printer and UPS units still boxed in the store at Lungulu Seed Secondary School, Nwoya District (Acholi), awaiting a power connection for installation | Laboratory stools and desks stored and not yet in use at Butungama Seed Secondary School, Ntoroko District (Tooro), where the school buildings were still under construction |
| HP computer sets stacked in store with cables still bundled and not installed at Bumufuni Seed Secondary School, Bulambuli District (Bugisu) | beds and screens stacked in storage at a health centre, Kagadi District (Bunyoro) |
| Boxed projector, air conditioner and other equipment in store at King Solomon Seed Secondary School, Kagadi District (Bunyoro), kept boxed because the school was still under construction | Boxed handheld pulse oximeters at Kibiri Health Centre III, Makindye-Ssabagabo Municipal Council (Buganda), where equipment was still being arranged after the facility opened on 31 August 2026 |

- Asset Marking and Identification

The verification revealed that only 49,457 (22.8%) of the movable assets were engraved and 167,279 (77.2%) were not engraved. Out of the engraved assets, 23,434 (10.8%) carried the UgIFT marking on them as a form of identification.

Identification and engraving varied at the different asset locations. The level of engravement stood at 31.5%, 25.3% and 15.2% for MDAs, Seed Secondary Schools and Health Centers respectively. Among the MDAs, the Ministry of Education and Sports accounts for most of the ministry assets that were not engraved, and these were mainly the TELA handsets and tablets. The details of asset identification are provided in figure 3.

Figure 3: Asset marking and Identification

Below are some of the photos depicting the different markings and identification engravements of assets across the institutions

| Engraving reading GOU/MOH-UGIFT PROJECT FY/2023/2024 on a desk at Namwaya Health Centre III, Tororo District | Engraving reading APESSS MOES/UGIFT/KABE/SPLRS/2023-24/001 on a desk at Aperikira Seed Secondary School, Kaberamaido District |
| --- | --- |
| Chair engraved UgIFT/ BUDDE SEED S.S M-PHALL CHAIR with a serial number at Budde Seed Secondary School, Butambala District | Wheelchair backrest marked GOU/MOH UGIFT-PROJECT. FY2023/2024 at Kalemungole Health Centre III, Moroto District |
| Engraving reading GOU/MOH-UGIFT PROJECT FY2023-2024/01 on a weighing scale at Kalemungole Health Centre III, Moroto District | Microscope marked KAMORU HC III by hand at Kamoru Health Centre III, Kotido Distric |
| Engraving reading KING SOLOMON SEED SECONDARY SCHOOL, without a UgIFT marking, on furniture at King Solomon Seed Secondary School, Kagadi District | Engraving reading KWN/MED-EQ/MOYOK HCIII on a steel cupboard at Moyok Health Centre III, Kween District |

- Financial analysis/ valuation

Overall, the 226,280 assets verified across the different institutions had a recorded value of UGX 971,615,425,138. Basing on the straight-line depreciation policy and the dates of deployment for the different assets, the computed net book value was UGX 808,621,845,836 as at 30 September 2026.

The recorded values vary by classification with MDAs at UGX 31,822,306,095, Blood Banks UGX 1,451,584,715, Seed Secondary Schools UGX 678,247,549,426 and Health Centers UGX 259,662,849,164 as indicated in the table 2.

Table 2: Overall Recorded asset value and net book value

| Institution | Assets | Recorded value UGX | Depreciation UGX | Net book value UGX |
| --- | --- | --- | --- | --- |
| Ministries and agencies | 16,668 | 31,822,306,095 | 19,372,809,078 | 12,449,497,017 |
| Blood banks | 626 | 1,451,584,715 | 514,105,544 | 937,479,171 |
| Health centres | 63,606 | 259,662,849,164 | 41,291,859,808 | 218,378,252,366 |
| Seed secondary schools | 145,376 | 678,247,549,426 | 101,549,907,057 | 576,704,905,370 |
| Total | 226,276 | 971,184,289,400 | 162,728,681,487 | 808,470,133,924 |

## National level Ministries and Agencies results

- Overall Asset availability at Ministries and Agencies

The exercise verified 16,668 assets of the different categories across all the thirteen Ministries and agencies. In terms of categorization, the exercise verified 15,136 ICT equipment including desktop computers, laptops, tablets, Uninterruptible Power Supply (UPS), 76 Vehicles and motorcycles, 99 Furniture and fittings and 1,357 small equipment including shredders, binders, projectors among others.

By location, most assets (64.7%) were at MoES, MoWE and MAAIF while PPDA was found with only five assets including three Lenovo think pad Laptops, one HP Laser Jet Color Printer and one Samsung Galaxy tablet as indicated in figure 4 below.

Figure 4: UgFT Assets available at each of the verified MDAs

- MDA asset Condition and functionality

At MDA level, apart from Ministry of Health that had one double cabin boarded off and three broken laptops at the Office of the Prime minister, the rest of the assets 16,664 (99.9%) were in good condition and were in use. The Ministry of Education and Sports holds 10,783 of these assets, mainly TELA handsets and tablets and were all in use at the different schools across the country. LGFC and MoPS indicated that they never received UgIFT assets.

- Asset marking and Identification

At MDA level, there were 15,401 movable assets, of which 4,843 (31.4%) were engraved with 4,730 assets (30.7%) bearing the UgIFT marking. Majority of assets 10,558 (68.6%) were not engraved. The figure 5 below shows the identification status of the assets at the different MDAs.

Figure 5: Asset marking and Identification at MDAs

- Financial analysis/ valuation

## MDA specific results

### Ministry of Finance, Planning and Economic Development

Asset availability: The ministry keeps a UgIFT asset register and the consolidated register for all MDAs that received UgIFT assets. A total of 458 assets were verified at the ministry including 217 ICT items, 122 other assets, 99 furniture and fittings and 20 transport assets. The main items were office chairs and desks, desktop computers, tablets and 20 Toyota Hilux double cabin pickups.

Condition and functionality: All 458 assets (100.0%) were working and in use, and none was broken down.

Marking and identification: A total of 272 assets (76.0%) were engraved and 86 (24.0%) were not engraved. 252 assets were found to have the UgIFT marking. It was also noted that the 20 double cabin pickups, did not have the UgFT labelling but were identified by their registration numbers only.

Financial Value of assets: The recorded value of the ministry's UgIFT assets is UGX 5,615,661,760.

The table below shows the detailed financial analysis of assets verified at MoFPED

| MDA | Asset Category | Recorded cost (UGX) | Accumulated Depreciation (UGX) | Net Book Value (UGX) | Portfolio Health |
| --- | --- | --- | --- | --- | --- |
| MOFPED | Vehicles |  |  |  |  |
|  | Laptops |  |  |  |  |
|  | Printers |  |  |  |  |
|  | Desktop Computers |  |  |  |  |
|  | Projectors |  |  |  |  |
|  | Furniture |  |  |  |  |
|  | UPS Systems |  |  |  |  |
|  | Digital Phones |  |  |  |  |
|  | Paper Shredders |  |  |  |  |
|  | Water Dispensers |  |  |  |  |
|  | Accessories |  |  |  |  |

### Ministry of Works and Transport

Asset availability:  The Ministry did not provide a UgIFT Asset Register. Physical verification at MoWT identified 88 assets of which 63 ICT items were mainly Lenovo desktop computers, monitors, uninterruptible power supply (UPS) units, video-conferencing equipment and HP Color LaserJet printers; one Toyota Hilux pickup; and 24 other assets. The 24 records grouped under other assets comprised 16 keyboards, four Dell OptiPlex 7090 desktop system units, two Lenovo Think Book notebooks, and two records without usable asset descriptions (entered as 'Ministry of Local Government' and 'PPDA'), as presented in Figure 6.

Figure 6: Assets verified at MoWT

Condition and functionality: All the 88 assets were verified found working and in use; none was broken down.

Marking and Identification: Of the 88 verified assets, 63 (71.6%) were engraved with 62 having the UgIFT marking while; 25 (28.4%) were not engraved.

Financial Value of assets: Recorded value: UGX 340,968,220.The detailed breakdown of the asset value by category is indicated in table 3.

Table 3: MoWT asset values by category

| Asset category | Assets | Recorded cost UGX |
| --- | --- | --- |
| ICT equipment | 63 | 126,534,110 |
| Vehicle | 1 | 196,018,110 |
| Other assets | 24 | 18,416,000 |
| Total | 88 | 340,968,220 |

### Ministry of Education and Sports

Asset availability: The verification at the Ministry of Education and Sports (MoES) established that the ministry had 10,783 assets. All the assets are ICT equipment and these include 9,324 TELA handsets, 1,001 tablets (976 of them inspection tablets), 456 laptops, a photocopier and a printer. The breakdown of these assets is shown below in figure 46c. Teacher, Effectiveness and Learner Achievement (TELA) is the system, financed by UgIFT, that the ministry uses to monitor attendance and performance in schools; the handsets and inspection tablets are deployed in local governments and remain MoES assets.

Figure 46c: Assets verified: MoES

Condition and functionality: All the 10,783 assets (100.0%) are in good working condition and in use. All the 456 laptops are in good condition, properly engraved and in use.

Table 12b: Condition and use of assets: MoES

| Status | Assets | Share |
| --- | --- | --- |
| Good working condition and in use | 10,783 | 100.0% |
| Not working or not in use | 0 | 0.0% |
| Total | 10,783 | 100.0% |

Marking and Identification: Of the verified assets, 458 (4.2%) were engraved, all with the UgIFT marking, while 10,325 (95.8%) were not engraved. None of the handsets or tablets carries an engravement mark.

Table 12c: Engraving status of assets: MoES

| Engraving status | Assets | Share |
| --- | --- | --- |
| Engraved with the UgIFT marking | 458 | 4.2% |
| Not engraved | 10,325 | 95.8% |
| Total | 10,783 | 100.0% |

Financial Value of assets: The recorded value is UGX 14,760,581,751, the highest among the MDAs.

### Ministry of Agriculture, Animal Industry and Fisheries

Asset availability: The team verified UgIFT assets at the Ministry of Agriculture, Animal Industry and Fisheries (MAAIF) and established that it held 2,045 assets. These included 1,206 ICT equipment, 2 vehicles and 837 others.  The ICT items were mainly 819 tablets, 211 computers (162 desktops and 49 laptops), 149 monitors and 15 printers. The breakdown of the assets mentioned above is shown in figure 46d.

Figure 46d: Assets verified: MAAIF

Condition and functionality: All 2,045 assets (100.0%) are in good condition and in use. All 211 computers and 819 tablets are in good condition, properly engraved and in use.

Table 12d: Condition and use of assets: MAAIF

| Status | Assets | Share |
| --- | --- | --- |
| Good working condition and in use | 2,045 | 100.0% |
| Not working or not in use | 0 | 0.0% |
| Total | 2,045 | 100.0% |

Marking and Identification: Of the 1,227 verified assets, 1,204 (98.1%) are engraved, 1,200 (97.8%) with the UgIFT marking, and 23 (1.9%) were not engraved, among them two drones, a handheld global positioning system (GPS) unit and a projector.   The laptops and printers had the UgIFT engraving.

Table 12e: Engraving status of verified assets: MAAIF

| Engraving status | Assets | Share of verified assets |
| --- | --- | --- |
| Engraved with the UgIFT marking | 1,200 | 97.8% |
| Other engraving | 4 | 0.3% |
| Not engraved | 23 | 1.9% |
| Total verified assets | 1,227 | 100.0% |

Financial Value of assets: The recorded value was UGX 1,844,366,458.

### Ministry of Health

The verification at the MoH did not find the Ugift Asset Register but relied on the listing provided by the Ministry of Finance, Planning and Economic Development.

Asset availability:  A total of 264 assets were verified. Of the 264 assets, 39 were ICT equipment (laptops and photocopiers), 25 assets were transport assets (motor vehicles and motor cycles) and 200(Electronic shredders and Heavy duty Binders) were other assets as indicated in Figure 46e.

Figure 46e: Assets verified at MoH

Condition and functionality: The assets in good working condition were 263 (99.6%). Among those in good condition and in use were 26 computers (2 desktops and 24 laptops), Shredders and heavy duty bidders.  Only one asset ie a pick-up double cabin was not in good working condition and had been boarded off.

Marking and Identification: Out of the 73 movable assets, 41(56%) were engraved while 32 (44%) were not engraved. There were 14 (19%) assets that were properly engraved with UgIFT marks and serial numbers.

Financial Value of assets: The MoH assets had a recorded value of UGX 953,859,009.

### Office of the Prime Minister

The Assets Register for the Office of the Prime Minister was not obtained and no list of assets was provided.  The verification relied on the listing obtained from the Ministry of Finance, Planning and Economic Development.

Asset availability: Office of the Prime Minister received 10 assets which were all HP laptop computers as shown in Figure 46f.

Figure 46f: Assets verified: OPM

Condition and functionality: Seven assets (70.0%) were in good working condition and in use. Three (30.0%) were damaged, and out of use.

Marking and identification: All the 10 laptops were properly engraved with the UgIFT markings.

Financial Value of assets: The recorded value of these computers in OPM was UGX 53,535,300.

### Office of the Prime Minister

The Assets Register for the Office of the Prime Minister was not obtained and no list of assets was provided.  The verification relied on the listing obtained from the Ministry of Finance, Planning and Economic Development.  Office of the Prime Minister received 10 assets which were all HP laptop computers as shown in Figure 46f.

Figure 46f: Assets verified: OPM

Seven assets (70.0%) were in good working condition and in use. Three (30.0%) were damaged, and out of use. All the 10 laptops were properly engraved with the UgIFT markings. The recorded value of these computers was UGX 53,535,300.

### 1.1.1 Ministry of Water and Environment

Asset availability: The Asset Verification at the Ministry of Water and Environment found out that the ministry keeps a Log book with UgIFT assets which does not conform to UgIFT Standards. The logbook recorded 2,939 assets, all classified as ICT equipment.

The verified assets received by the Ministry were 2,368 tablets out of which 2,344 were of Euron type, 188 Computers with their keyboards and UPS unit of which 31were laptops. The Ministry also received 16 real time kinematic GPS machines.

The 172 items previously shown as other assets are ICT-related items and are included in the ICT equipment total. They comprise 157 keyboards recorded with Dell OptiPlex computers, 7 airborne ground-penetrating radar units, 3 Samsung Galaxy Tab S9 tablets, 2 Lenovo ThinkBook notebooks, 1 Kyocera heavy-duty copier, 1 Huawei 65-inch infrared screen and 1 UPS unit.

Condition and functionality: The findings further indicated that all 2,939 assets (100.0%) were in good working condition and non were broken down.

Marking and Identification: The ministry received a total of 2939 assets, 2,782 verified assets, 2,740 (98.5%) were engraved, 2,707 (97.3%) with the UgIFT marking, and 42 (1.5%) were not engraved.

Financial Value of the assets: The recorded value was UGX 5,993,100,537.

Figure 46g. presents the UgIFT assets verified for MoWE.

Figure 46g: Assets verified: MoWE

### Ministry of Gender, Labour and Social Development

Asset availability: The Asset Verification at the Ministry of Gender, Labour and Social Development found out that the ministry keeps a UgIFT asset register which had 10 UgIFT assets. These comprised of 8 Lenovo ThinkPad Laptops, and 2 Samsung Tablets. Figure 46h presents the UgIFT assets verified for MoGLSD.

Condition and functionality: The findings further indicate that all the verified UgIFT assets were in good working condition and in use.

Marking and Identification: A total of Eight Lenovo ThinkPad Laptops (80.0%) were properly engraved with the UgIFT markings and the Two Samsung Tablets (20.0%) were not engraved.

Financial Value of the assets: The findings pointed out that the recorded value to be UGX 20,120,000.

Figure 46h: Assets verified: MoGLSD

### National Environment Management Authority

Asset availability:

National Environment Management Authority (NEMA) had 6 ICT items; 4 laptops, a printer and a heavy-duty photocopier.

Condition and functionality: All 6 (100.0%) were working and in use.

Figure 46i: Assets verified: NEMA

Marking and Identification:

One (16.7%) ie the heavy duty photocopier was engraved while the other 5 (83.3%) were not engraved.

Asset values: The recorded value is UGX 27,324,409.

The detailed breakdown of the asset value by category is indicated in table ..

### Public Procurement and Disposal of Public Assets Authority

Public Procurement and Disposal of Public Assets Authority (PPDA) did not provide a Ugift Asset Register. The verification relied on the information obtained from the Ministry of Finance, Planning and Economic Development.

Asset availability: A total of 5 assets were verified in PPDA; these were 3 Lenovo ThinkPad laptops, a Samsung Galaxy tablet and an HP printer as indicated in Figure 46j.

Figure 46j: Assets verified at PPDA

Condition and functionality All the 5 assets were in good working condition and in use.

Marking and identification: All the laptops, tablets and printer were properly engraved with the UgIFT marking.

Financial Value of assets: The MF register does not state a recorded cost or net book value for these assets.

### Office of the Auditor General (OAG)

Asset availability:

Evidence gathered during the verification confirmed that OAG had no Ugift asset register rather a list which indicated 20 assets; 18 of which were ICT items (16 laptops and 2 printers) and 2 pickup vehicles. The above information is depicted in figure 46k.

Condition and functionality: All 20 (100.0%) were in good condition, engraved and in use.

Marking and Identification: Six (30.0%) were properly engraved with the UgIFT markings and 14 (70.0%) were not properly engraved with Ugift markings. The engravement was carrying the office's own asset code or vehicle registration number for the two pickups.

Figure 46k: Assets verified at OAG

Asset Values: The assets were worth UGX 228,773,680.

The detailed breakdown of the asset value by category is indicated in table….

### Ministry of Local Government

Asset availability: The asset verification at the Ministry of Local Government (MoLG) found that the ministry kept a UgIFT asset register and had 13 UgIFT assets; one double-cabin pickup and 12 ICT items. The ICT assets comprised of 6 computers, 4 computer peripherals and 2 heavy duty photocopiers. Figure 46l presents the UgIFT assets verified for MoLG.

Figure 46l: Assets verified: MoLG

Condition and functionality:  The findings further indicate that all 13 (100.0%) verified UgIFT assets were in good condition and in use.

Asset marking and Identification: Out of the 13 assets, eight (61.5%) were engraved while five (38.5%) were not.  Of the eight assets that were engraved, 7 (53.8%) were engraved with a UgIFT markings while one was not. In terms of ICT equipment which formed the bulk of assets, 3 (50.0%) were engraved and 3 (50.0%) were not.

Financial Value of assets: The findings pointed out the recorded value to be UGX 31,114,879.

### Ministry of Lands, Housing and Urban Development

Asset availability: The findings from the verification exercise indicate that MoLH &UD had 27 UgIFT assets. These include 25 Honda motorcycles and 2 other assets (Helmets).

Figure 46m: Assets verified at MoLHUD

Additionally, the ministry received survey equipment and other motorcycles that it gave out to local governments.

Condition and functionality:  All the 27 (100.0%) were in good condition and in use, and none was broken down.

Asset marking and Identification: All the 27 (100.0%) were not engraved with UgIFT markings. It was also noted that the motorcycles did not have the UgFT labelling but were identified by their registration numbers only.

Financial Value of assets: The findings further indicate the recorded value to be UGX 597,549,997.

## Results from blood banks

UgIFT financed the construction of the Arua and Hoima regional blood banks, which were completed and commissioned, and the rehabilitation of Soroti Regional Blood Bank. The three Blood Banks operate under Uganda Blood Transfusion Services (UBTS) and were verified.

Asset availability:

This part counts the assets verified. Arua Regional Blood Bank held 277 assets (44.2%). Figure 57 shows the count, and Table 23 lists it.

Figure 57: Assets verified: Blood banks

Table 23: Availability of assets: Blood banks

| Institution | Assets verified | Share |
| --- | --- | --- |
| Arua Regional Blood Bank | 277 | 44.2% |
| Hoima Regional Blood Bank | 119 | 19.0% |
| Soroti Regional Blood Bank | 115 | 18.4% |
| Uganda Blood Transfusion Services | 115 | 18.4% |
| Total | 626 | 100.0% |

### Condition of assets

602 assets (96.2%) were in good condition, of which 602 were in use and 0 were in store. 6 (1.0%) were broken and 18 (2.9%) were not in use for another reason. The lowest share in good condition was Arua Regional Blood Bank at 91.3%. Figure 58 shows the split. Table 24 states the counts.

Figure 58: Condition of assets: Blood banks

Table 24: Condition of assets: Blood banks

| Institution | Assets verified | Good condition |  | Broken | Other |
| --- | --- | --- | --- | --- | --- |
|  |  | In use | In store |  |  |
| Arua Regional Blood Bank | 277 | 253 | 0 | 6 | 18 |
| Hoima Regional Blood Bank | 119 | 119 | 0 | 0 | 0 |
| Soroti Regional Blood Bank | 115 | 115 | 0 | 0 | 0 |
| Uganda Blood Transfusion Services | 115 | 115 | 0 | 0 | 0 |
| Total | 626 | 602 | 0 | 6 | 18 |

Good condition is assets in use plus assets in store. Broken assets are counted on their own, including broken assets found in store. Other assets are not in use for another reason. The four condition columns sum to assets verified.

### Identification, including engraving

Of 605 movable assets, 43 (7.1%) were engraved and 562 (92.9%) were not engraved. 26 (4.3%) carried the UgIFT marking and 17 (2.8%) carried another marking only. Figure 59 shows the position. Table 25 sets out the counts.

Figure 59: Engraving of movable assets: Blood banks

Table 25: Identification of assets: Blood banks

| Institution | Assets verified | Movable assets | Engraved | Properly engraved | Not engraved |
| --- | --- | --- | --- | --- | --- |
| Arua Regional Blood Bank | 277 | 257 | 43 (16.7%) | 26 (10.1%) | 214 (83.3%) |
| Hoima Regional Blood Bank | 119 | 118 | 0 (0.0%) | 0 (0.0%) | 118 (100.0%) |
| Soroti Regional Blood Bank | 115 | 115 | 0 (0.0%) | 0 (0.0%) | 115 (100.0%) |
| Uganda Blood Transfusion Services | 115 | 115 | 0 (0.0%) | 0 (0.0%) | 115 (100.0%) |
| Total | 626 | 605 | 43 (7.1%) | 26 (4.3%) | 562 (92.9%) |

Movable assets exclude buildings, structures and land. Properly engraved means the UgIFT marking. A dash means the assets are identified through property and site records rather than engraving.

### Financial aspects

Recorded value was UGX 1,451,584,715 and net book value at 30 September 2026 was UGX 937,479,171. Accumulated depreciation was UGX 514,105,544. Figure 60 compares recorded value and net book value. Table 26 gives the figures.

Figure 60: Recorded value and net book value: Blood banks

Table 26: Recorded value and net book value: Blood banks

| Institution | Assets | Recorded value UGX | Depreciation UGX | Net book value UGX |
| --- | --- | --- | --- | --- |
| Arua Regional Blood Bank | 277 | 1,091,262,791 | 430,462,000 | 660,800,791 |
| Hoima Regional Blood Bank | 119 | 278,006,206 | 21,690,290 | 256,315,916 |
| Soroti Regional Blood Bank | 115 | 29,317,538 | 25,122,550 | 4,194,988 |
| Uganda Blood Transfusion Services | 115 | 52,998,180 | 36,830,704 | 16,167,476 |
| Total | 626 | 1,451,584,715 | 514,105,544 | 937,479,171 |

Recorded value is the cost in the verification records. Net book value is that cost less accumulated depreciation to 30 September 2026, and is not taken below zero.

UgIFT financed the construction of the Arua and Hoima regional blood banks, which were completed and commissioned, and the rehabilitation of Soroti Regional Blood Bank. The photographs show the buildings, donor rooms and cold-chain equipment, and the engraving found on equipment at Arua and Hoima.

| Completed blood bank building at Arua Regional Blood Bank, Arua City | Soroti Blood bank |
| --- | --- |
| Blood bank refrigerator at Arua Regional Blood Bank, Arua City | Platelet agitator at Arua Regional Blood Bank, Arua City |
| Donor couches in the donor room at Hoima Regional Blood Bank, Hoima City | Blood bank refrigerator Soroti Blood bank |
| Benchtop centrifuge at Hoima Regional Blood Bank, Hoima City | Markings PEP II/UBTS/COMP/11/016 and UBTS/UGIFT/ARBB/UPS/001 on uninterruptible power supplies at Arua Regional Blood Bank, Arua City |

## Local government level results

The asset verification exercise at the LG level covered all the 176 LGs across the country with 629 UgIFT facilities that received support from UgIFT programme of which 371 are Health Centres and 258 are Seed Secondary Schools.  A total of 208,975 assets were verified, of which 63,599 were for Health Centres and 145,376 were for Seed Secondary Schools across all LGs. Of the 208,975 assets, 195,503 (93.6%) were in good condition and in use while 3,119 (1.5%) were not in use.   3,382 were broken assets. The details are presented in sections 3.3 (Health Centres) and 3.4 (Seed Secondary Schools).

## Health Centres

### Availability of the assets

The verification findings indicate that health facilities received 63,599 assets across the different categories which include; clinical equipment, clinical furniture, maternity ward equipment, ICT equipment, buildings, land and other movable assets. Consumables are excluded. Table 13 and Figure 47 present the assets by category.

Table 13: Availability of assets in Health Centres

| Asset category | Assets verified | Share |
| --- | --- | --- |
| Clinical equipment | 25,960 | 40.8% |
| Clinical furniture | 20,139 | 31.7% |
| Maternity ward equipment | 7,438 | 11.7% |
| ICT equipment | 410 | 0.6% |
| Health centre buildings | 1,525 | 2.4% |
| Other health centre assets | 8,124 | 12.8% |
| Land | 3 | 0.0% |
| Total | 63,599 | 100.0% |

Figure 47: Assets verified: Health centres

### Asset condition and functionality

The findings indicate that of the 63,599 health centre assets, 60,547 (95.2%) were in good condition, 57,918 (91.1%) were in use and 2,629 (4.1%) were in store. A further 660 (1.0%) were broken and 2,392 (3.8%) were not in use for other reasons. ICT equipment had the lowest share in good condition at 89.3%. Figure 48 and Table 14 present the condition of the assets.

Figure 48: Condition of assets: Health centres

Table 14: Condition of assets: Health centres

| Asset category | Assets verified | Good condition |  | Broken | Other |
| --- | --- | --- | --- | --- | --- |
|  |  | In use | In store |  |  |
| Clinical equipment | 25,960 | 22,507 | 1,677 | 220 | 1,556 |
| Clinical furniture | 20,139 | 19,110 | 360 | 277 | 392 |
| Maternity ward equipment | 7,438 | 6,918 | 303 | 69 | 148 |
| ICT equipment | 410 | 361 | 5 | 5 | 39 |
| Health centre buildings | 1,525 | 1,495 | 0 | 6 | 24 |
| Other health centre assets | 8,124 | 7,527 | 284 | 83 | 230 |
| Land | 3 | 3 | 0 | 0 | 0 |
| Total | 63,599 | 57,918 | 2,629 | 660 | 2,392 |

Of the 2,392 (3.8%) health-centre assets not in use for other reasons, included those that were not delivered to the facility (still in stores at LGs), idle, had missing parts, lacked power, not required at the facility, rooms/ wards for installation of the equipment, held at another facility, awaiting installation, lost/missing and unused because staff were not trained or no specialist was available to operate the equipment.  Examples include a wall-mounted blood pressure machine at Butawata Health Centre III (Mubende District) recorded as not functional; a wheelchair at Aarapoo Health Centre III (Serere District) that had not been delivered; a patient screen at Ayer Health Centre III (Kole District) that was on the delivery note but not seen; a paediatric bed at Okwerodot Health Centre III (Kole District) supplied without a mattress; and an autoclave machine at Anamwany Health Centre III (Amolatar District) left unused for lack of electricity.

In terms of buildings, they are categorised into two i.e. residential (482) and non-residential buildings (1,043). Residential buildings are staff houses and other buildings described as residential. Table 15 and Figure 49 depict the building categories.

Table 15: Health Centre Buildings

| Building type | Assets verified | Share |
| --- | --- | --- |
| Residential buildings | 482 | 31.6% |
| Non-residential buildings | 1,043 | 68.4% |
| Total | 1,525 | 100.0% |

### Asset marking and Identification

Of the 63,599 assets in Health Centres; 62,071 are movable assets of which 9,446 (15.2%) were engraved and 52,625 (84.8%) were not engraved. It was noted that 3,817 (6.1%) carried the UgIFT identifiers and 5,629 (9.1%) carried other modes of marking with no UgIFT identifiers as depicted in Figure 49 and Table 16.

Figure 49: Engraving of movable assets: Health centres

Table 16: Identification of assets at Health centres

| Asset category | Assets verified | Movable assets | Engraved | Properly engraved with UgIFT | Not engraved |
| --- | --- | --- | --- | --- | --- |
| Clinical equipment | 25,960 | 25,960 | 2,815 (10.8%) | 1,043 (4.0%) | 23,145 (89.2%) |
| Clinical furniture | 20,139 | 20,139 | 3,934 (19.5%) | 1,576 (7.8%) | 16,205 (80.5%) |
| Maternity ward equipment | 7,438 | 7,438 | 1,510 (20.3%) | 815 (11.0%) | 5,928 (79.7%) |
| ICT equipment | 410 | 410 | 155 (37.8%) | 133 (32.4%) | 255 (62.2%) |
| Health centre buildings | 1,525 | - | - | - | - |
| Other health centre assets | 8,124 | 8,124 | 1,032 (12.7%) | 250 (3.1%) | 7,092 (87.3%) |
| Land | 3 | - | - | - | - |
| Total | 63,599 | 62,071 | 9,446 (15.2%) | 3,817 (6.1%) | 52,625 (84.8%) |

Financial Value of assets: The findings indicate that the recorded value of assets was UGX 259,662,759,164 and the net book value was UGX 218,378,252,366, while accumulated depreciation was UGX 41,291,769,808 as at 30 September 2026. Table 17 gives the recorded value and net book value.

Table 17: Recorded and net book values at Health centres

| Asset category | Assets | Recorded value UGX | Depreciation UGX | Net book value UGX |
| --- | --- | --- | --- | --- |
| Clinical equipment | 25,960 | 32,419,253,988 | 12,264,441,553 | 20,154,812,435 |
| Clinical furniture | 20,139 | 16,115,597,625 | 6,920,036,277 | 9,202,824,358 |
| Maternity ward equipment | 7,438 | 7,419,395,159 | 3,270,066,317 | 4,149,328,842 |
| ICT equipment | 410 | 876,467,375 | 646,446,250 | 230,021,125 |
| Health centre buildings | 1,525 | 198,198,049,954 | 17,166,034,514 | 181,032,015,440 |
| Other health centre assets | 8,124 | 4,583,995,063 | 1,024,744,897 | 3,559,250,166 |
| Land | 3 | 50,000,000 | 0 | 50,000,000 |
| Total | 63,599 | 259,662,759,164 | 41,291,769,808 | 218,378,252,366 |

Recorded value is the cost in the verification records. Net book value is that cost less accumulated depreciation to 30 September 2026, and is not taken below zero.

## Seed Secondary Schools

### Availability of the assets

The findings showed that the Seed Secondary Schools received 145,376 assets covering the following categories; School buildings, Water facilities, School furniture, Computers and related equipmets such as monitors, UPS units and keyboards, ICT equipment including; printers, photocopiers, cameras and projectors and other school assets such as laboratory items, electrical items, plant and machinery and sports equipment. Table 18 presents the details.

Table 18: Availability of assets at Seed Secondary Schools

| Asset category | Assets verified | Share |
| --- | --- | --- |
| School buildings | 4,341 | 3.0% |
| Water facilities | 594 | 0.4% |
| School furniture | 109,646 | 75.4% |
| Computers and related equipment | 10,266 | 7.1% |
| ICT equipment | 1,503 | 1.0% |
| Other school assets | 19,026 | 13.1% |
| Total | 145,376 | 100.0% |

### Asset condition and functionality

Out of 145,376 assets; 138,075 (95.0%) were in good condition. Of those in good condition, 137,585 were in use and 490 were in store. The verification further established that 2,722 (1.9%) were broken while 4,579 (3.1%) were not in use for other reasons. Table 19 indicates the Asset condition.

Table 19: Condition of assets: Seed secondary schools

| Asset category | Assets verified | Good condition |  | Broken | Other |
| --- | --- | --- | --- | --- | --- |
|  |  | In use | In store |  |  |
| School buildings | 4,341 | 4,238 | 3 | 14 | 86 |
| Water facilities | 594 | 560 | 0 | 15 | 19 |
| School furniture | 109,646 | 104,233 | 0 | 2,455 | 2,958 |
| Computers and related items | 10,266 | 8,777 | 301 | 208 | 980 |
| ICT equipment | 1,503 | 1,395 | 30 | 11 | 67 |
| Other school assets | 19,026 | 18,382 | 156 | 19 | 469 |
| Total | 145,376 | 137,585 | 490 | 2,722 | 4,579 |

Good condition is assets in use plus assets in store. Broken assets are counted on their own, including broken assets found in store. Other assets are not in use for another reason. The four condition columns sum to assets verified

School furniture (desks, tables, chairs, shelves and stools) is the largest category with 109,646 assets. Of these, 104,233 were in good conditions and in use while 2,455 were broken. Computers and related equipment had 8,777 in use.

### Asset marking and Identification

Of the 138,671 movable assets, 35,121 (25.3%) were engraved where as 103,550 (74.7%) were not engraved. 14,861 (10.7%) carried the UgIFT markings and 20,260 (14.6%) carried other markings as shown in Table 20.

Table 20: Identification of assets at Seed Secondary Schools

| Asset category | Assets verified | Movable assets | Engraved | Properly engraved | Not engraved |
| --- | --- | --- | --- | --- | --- |
| School buildings | 4,341 | - | - | - | - |
| Water facilities | 594 | 96 | 0 (0.0%) | 0 (0.0%) | 96 (100.0%) |
| School furniture | 109,646 | 109,646 | 31,656 (28.9%) | 14,405 (13.1%) | 77,990 (71.1%) |
| Computers and related equipment | 10,266 | 10,059 | 2,445 (24.3%) | 310 (3.1%) | 7,614 (75.7%) |
| ICT equipment | 1,503 | 1,503 | 169 (11.2%) | 5 (0.3%) | 1,334 (88.8%) |
| Other school assets | 19,026 | 17,367 | 851 (4.9%) | 141 (0.8%) | 16,516 (95.1%) |
| Total | 145,376 | 138,671 | 35,121 (25.3%) | 14,861 (10.7%) | 103,550 (74.7%) |

Movable assets exclude buildings, structures and land. Properly engraved means the UgIFT marking. A dash means the assets are identified through property and site records rather than engraving.

3.7.4 Financial Value of assets

The recorded value was UGX 678,247,549,426, the net book value was UGX 576,704,905,370 and accumulated depreciation was UGX 101,549,907,057 as at 30 September 2026 as shown in Table 21.

Table 21: Recorded value and net book value: Seed secondary schools

| Asset category | Assets | Recorded value UGX | Depreciation UGX | Net book value UGX |
| --- | --- | --- | --- | --- |
| School buildings | 4,341 | 495,160,116,359 | 54,728,357,865 | 440,431,758,495 |
| Water facilities | 594 | 3,076,630,427 | 817,399,552 | 2,259,230,875 |
| School furniture | 109,646 | 94,322,583,307 | 18,004,437,908 | 76,325,408,399 |
| Computers and related equipment | 10,266 | 25,434,940,136 | 13,385,662,572 | 12,049,277,564 |
| ICT equipment | 1,503 | 3,790,186,812 | 2,174,847,712 | 1,615,339,100 |
| Other school assets | 19,026 | 56,463,092,385 | 12,439,201,448 | 44,023,890,937 |
| Total | 145,376 | 678,247,549,426 | 101,549,907,057 | 576,704,905,370 |

Recorded value is the cost in the verification records. Net book value is that cost less accumulated depreciation to 30 September 2026.

Completion Status of Facilities

The verification established that there were a number of facilities that were either completed or not completed. Table 27 provides the details.

Table 27: Programme-list facilities verified, completed and providing services

| Measure | Health centres | Seed schools | Total |
| --- | --- | --- | --- |
| Programme list | 371 | 258 | 629 |
| Works completed | 320 (92.2%) | 155 (63.8%) | 475 (80.5%) |
| Works not completed | 27 (7.8%) | 88 (36.2%) | 115 (19.5%) |

Counts are facilities. Verified and accounted for through reconciliation are percentages of the programme list; the other percentages are of verified facilities.

Table 27 indicates that works were completed at 475 of the verified facilities (80.5%) while works were not complete at 115 (19.5%).  Eighty-eight schools (36.2%) were still under construction or not yet handed over by the contractor compared to 27 (7.8%) incase of health facilities.

The photos below show some of the facilities that are complete

| Figure 89: Health centre building at Kibiri HC III, Makindye-Ssabagabo Municipal Council (Buganda) | Figure 90: Health centre buildings and covered walkway at Kihuukya HC III, Hoima City (Bunyoro) |
| --- | --- |

| Figure 91: Binocular microscope at Kihuukya HC III, Hoima City (Bunyoro) |  |  | Figure 93: Maternity block entrance and access ramp at Kamuli HC III, Tororo District (Bukedi) |  |
| --- | --- | --- | --- | --- |
| Figure 94: Classroom furnished with desks and a whiteboard at Gyagenda Memorial Seed Secondary School, Kalangala District (Buganda) |  | Figure 95: Books displayed on library shelves at Sibanga Seed School, Manafwa District (Bugisu) |  | Figure 96: ICT laboratory block and entrance ramp at Sisiyi Seed Secondary School, Bulambuli District (Bugisu) |

The photos below show some of the facilities that are still under construction.

| Figure 74: Unfinished school block at Got Apwoyo Seed Secondary School, Nwoya District (Acholi) | Figure 75: Unfinished classroom block at Sidok Seed Secondary School, Kaabong District (Karamoja) |
| --- | --- |

| Figure 76: Latrine block under construction at Sidok Seed Secondary School, Kaabong District (Karamoja) | Figure 77: Building works and construction materials at Ndhew Seed Secondary School, Nebbi District (West Nile) |
| --- | --- |

| Figure 78: School block awaiting completion at Butungama Seed Secondary School, Ntoroko District (Tooro) | Figure 79: Building works at a seed secondary school, Kiboga District (Buganda) | Figure 80: Classroom block with earthworks in the foreground at Kihungya Seed Secondary School, Buliisa District (Bunyoro) |
| --- | --- | --- |

| Figure 81: Unfinished laboratory building at a health centre, Sironko District (Bugisu) | Figure 82: Biology laboratory under construction at a seed secondary school, Buliisa District (Bunyoro) | Figure 83: Unfinished laboratory interior at Kihungya Seed Secondary School, Buliisa District (Bunyoro) |
| --- | --- | --- |

| Figure 84: Library interior under construction at Kihungya Seed Secondary School, Buliisa District (Bunyoro) | Figure 85: ICT laboratory interior under construction at Kitawoi Seed Secondary School, Kween District (Sebei) |
| --- | --- |

| Figure 86: Laboratory benches with cupboard doors not yet fitted, in a science laboratory block recorded as under construction, at King Solomon Seed Secondary School, Kagadi District (Bunyoro) | Figure 87: Empty computer laboratory at Kaptum Seed Secondary School, Kween District (Sebei), where the buildings had not been handed over and no ICT equipment had been received |
| --- | --- |

## Field Observations,

## Location and Name changes

The verification exercise established that there were mismatches between information from the programme list and what was found on the ground. It was found that out of 629 facilities verified, 590 (93.8%) matched properly with the programme list as obtained from the MoFPED. A total of 39 facilities (6.2%) had inconsistancies with the progromme list which included; i) those operating under different names; ii) facilities found on the programme list but did not benefit from the programme; and iii) facilities that were found on ground to have benefited from the programme but were not included on the programme list. These inconsistencies were accounted for through reconciliation. Table 29 provides the details.

Table 29: Inconsistencies between the programme list and the facilities found

| Outcome | Health centres | Seed schools | Total | Facilities (programme-list name and district: operating or receiving name) |
| --- | --- | --- | --- | --- |
| Facilities on the programme list but not on ground | 7 | 3 | 10 | Health centres: Olok HC II (Pader); Alik HC II (Lira); Acimi HC II (Oyam); Acokara HC II (Oyam); Ariba HC II (Oyam); Busia Eastern Division (Busia Municipal Council); Butoloogo HC II (Kassanda) Seed schools: Eastern Division (Tororo Municipal Council); Central Division (Jinja City); Kishangara Seed School (Ibanda) |
| Replaced by another facility | 4 | 0 | 4 | Health centres: Oweko HC II (Nebbi): Pamaka HC III; Loinya HC II (Maracha): Liko HC III, already on the programme list; Ngomoromo HC II (Lamwo): Pangira HC III; Musandama HC II (Ntoroko): Butungama HC III |
| Operates under another name | 10 | 20 | 30 | Health centres: Kocheka HC II (Bukedea): Kangole/Kocheka HC III; Dabani (Busia): Buwumba HC III; Mantoroba HC II (Bundibugyo): Busanga HC III; Kidubuli HC II (Kabarole): Iruhura HC III; Nyabuswa HC II (Kabarole): Nyambuusa HC III; Kabbo (Mubende): Nakawala HC III; Kikoola (Kakumiro): Mukoora HC III; Kyakatebe HC II (Kassanda): Namabaale HC III; Kagganda HC II (Lwengo): Mbirizi SSS; Bussi HC II (Wakiso): Zinga HC III, already on the programme list Seed schools: Kadungulu Seed School (Serere) for Kagwara SSS; Pallisa (Pallisa) for Akadot SSS; Bunambutye Seed School (Bulambuli) for Bumufuni SSS; Igombe (Bugweri) for Mpiita SSS; Butagaya (Jinja) for Buwala SSS; Mwema Seed School (Namayingo) for Mutumba SSS; Kimenyedde Seed School (Mukono) for St Andrews Ndwaddemutwe SSS; Nsiika T/C (Buhweju) for Ndibarema Memorial SSS; Kagadi (Kagadi) for King Solomon SSS; Kiryanga Seed School (Kagadi) for St Catherine Kicucura SSS; Ruteete (Kagadi) for Kitegwa Community SSS; Kasenda Seed School (Kabarole) for St Paul Nyabweya SSS; Kabonero (Bunyangabu) for Katugunda SSS; Kyamukube Town Council (Bunyangabu): Nsuura SSS; Bufumira Seed School (Kalangala): Nekemiya Memorial SSS; Kiringente Seed School (Mpigi): Wamatovu SSS; Mpumudde Seed School (Lyantonde): Rwamabara SSS; Buhanika (Hoima): Kidukuru SSS; Maddu Seed School (Gomba): return submitted as Kyayi Seed School; Mugarama, new facilities for St Mugagga (Kibaale): St Mugagga Vocational SSS |
| Not a UgIFT beneficiary | 2 | 1 | 3 | Health centres: Alira HC II (Oyam); Buyinda HC II (Kaliro) Seed schools: Kiziranfumbi Seed School (Kikuube) |
| UgIFT assets relocated to another facility | 2 | 1 | 3 | Health centres: Alangi (Zombo) to Amwonyo HC III; Ther-uru HC II (Zombo) to Atyak HC III Seed schools: Abanga (Zombo) to Kango SSS |
| Exists with no UgIFT assets | 2 | 3 | 5 | Health centres: Pandwong HC II (Kitgum Municipal Council); Rwamujojo HC II (Sheema Municipal Council) Seed schools: Bumbaire Seed School (Bushenyi); Kyamuhunga (Bushenyi); Kashenshero (Mitooma) |
| Total | 27 | 28 | 55 |  |

Counts are programme-list facilities. HC means health centre; SSS means Seed Secondary School.

## Complete works and bring stored assets into use

Finding. Of the 590 facilities verified, 475 (80.5%) had completed works and 115 (19.5%) had works outstanding: 27 health centres (7.8% of those verified) and 88 seed schools (36.2%). Of the 115, 63 were already providing services, while 24 verified facilities, 21 of them seed schools, were not yet providing services; 22 of these 24 had works outstanding. At Ndhew and Mamba Seed Secondary Schools in Nebbi, unfinished buildings delayed installation: science equipment was held at district headquarters, and Mamba accommodated its computers in older structures.

Of the 13,500 assets not in use, 3,200 (23.7%) were in storage at 181 facilities, 164 health centres and 17 seed schools; at national level the asset records place no assets in storage, although the field teams observed furniture left in a former MoFPED store and equipment kept in the Hoima blood bank stores (sections 3.1.1 and 3.2). Of the stored assets, 190 (5.9%) were waiting for power, 80 (2.5%) for a building or room and 141 (4.4%) were held at district stores or another facility, while 519 (16.2%) were described as new, boxed or in good condition. More widely, 1,324 assets not in use (9.8%), at 79 facilities, were waiting for power (331, 2.4% of assets not in use), a building or room (483, 3.6%), installation or assembly (493, 3.6%), trained users (16) or staff (1), and a further 97 (0.7%) lacked accessories, parts or consumables.

Facility accounts point to the same blockers. Of the 477 facilities that described services and challenges, 156 (32.7%) reported idle or unusable equipment: 71 of these (45.5%) linked it to power, 32 (20.5%) to installation and 27 (17.3%) to incomplete buildings or lack of space. Lungulu Seed Secondary School in Nwoya kept computers boxed in store pending a power connection, and at Nansanga Seed Secondary School in Budaka 27 of 28 desktop computers remained packed for lack of reliable power.

Finding. Skills and staffing limited the use of equipment most at health centres. Of the 156 facilities that reported idle or unusable equipment, 52 (33.3%) linked it to staff being unable to operate the equipment; 51 of these were health centres, 45.9% of the 111 health centres reporting idle equipment. Training or skills to operate equipment was raised as a gap by 85 facilities (17.8%), 82 health centres (28.9%) and 3 seed schools (1.6%), and 61 facilities (12.8%) asked for training or orientation on the equipment. Staffing was raised by 154 facilities (32.3%), and 9 of the facilities with idle equipment (5.8%) had no personnel or specialist to use it.

At Bubago Health Centre III in Kamuli, staff needed training to operate and maintain an oxygen concentrator. At Sop Sop Health Centre III in Tororo, much of the equipment remained in store because staff did not know how to operate it, and Avogera Health Centre III asked for user orientation and technical skills.

## Service delivery Improvements

# Asset management

## Maintenance and repairs

Maintenance keeps UgIFT assets working for the services they were bought to support. Most of the verified assets are furniture, clinical equipment and computers in daily use at health centres and seed schools, where wear and breakage are to be expected. Routine checks, a record of faults and a dependable route for repair decide whether a broken item returns to use quickly or stays out of service. During the verification, each facility was asked how it maintains, repairs, services or replaces UgIFT assets and whether it keeps a regular record of their functionality or breakdown.

Repair arrangements. Of the 469 facilities that described their maintenance arrangements, 260 (55.4%) met repairs at facility level, from their own funds or with their own staff. Health centres named Primary Health Care funds (94 of 278, 33.8%), while schools named the capitation or Universal Secondary Education grant, parents' contributions or the school budget (52 of 191, 27.2%). Busaale Health Centre III in Kayunga used Primary Health Care funds for repairs, and Kagumba Seed Secondary School in Kamuli had repaired broken furniture during the second term. A facility could describe more than one arrangement.

Support from outside the facility was cited by 151 facilities (32.2%): district offices, mainly the District Health Officer, 84 (17.9%); regional referral hospital workshops or national teams 52 (11.1%); hired technicians and artisans 27 (5.8%); and contractors or suppliers under defects liability, guarantee or warranty 12 (2.6%). Major medical equipment repairs depended on this support. Todora Health Centre III in Nwoya worked through the District Health Officer and the Gulu Regional Referral Hospital technical team, Avogera Health Centre III in Buliisa received support from Hoima Regional Referral Hospital, and Bundimulangya Health Centre III in Bundibugyo obtained a team through the District Health Officer.

In all, 97 facilities (20.7%), 59 of them schools, had not yet needed maintenance because the assets were new, not yet handed over or the buildings were still under construction, and 36 (7.7%) reported no repair arrangement, with broken items set aside or not repaired. Funds for maintenance and repair were reported as insufficient, particularly for major repairs, by 32 of the 505 facilities that described maintenance or challenges (6.3%). At Kyankaramata Health Centre III in Kyenjojo, Primary Health Care funds met minor repairs, but the cost of major repairs was a constraint.

Figure 98 compares these arrangements at health centres and seed schools. Health centres relied more on outside technical support (41.0% of health centres against 19.4% of schools), while schools more often had not yet needed maintenance (30.9% against 13.7%).

Figure 98: Most facilities met repairs from their own funds or staff

Frequency. Few facilities worked to a fixed maintenance interval. Of the 494 programme-list facilities that described how they maintain UgIFT assets or check their condition, 50 (10.1%) did so at a fixed interval. Of these 50, 14 (28.0%) worked annually, 11 (22.0%) monthly, 10 (20.0%) quarterly, 9 (18.0%) every school term, 3 (6.0%) twice a year and 3 (6.0%) weekly or daily, as Figure 99 shows. A further 18 facilities (3.6%) described routine or scheduled servicing without a set interval, mostly scheduled visits by regional referral hospital maintenance teams, and 62 (12.6%) repaired items as the need arose. Ngwedo Seed Secondary School in Buliisa engaged a caretaker every month and used the Directorate of Industrial Training for furniture repairs, while Busaale reviewed asset condition every quarter.

Figure 99: Annual, monthly and quarterly checks were the most common stated intervals

Records. Of the 463 facilities that answered, 318 (68.7%) kept a regular record of asset functionality or breakdowns, 36 (7.8%) kept a partial or informal record, 80 (17.3%) kept none and 29 (6.3%) had not yet started because the assets were new or the facility was not yet operating. Of the 478 facilities that answered, 355 (74.3%) held a record of the UgIFT assets they received, 40 (8.4%) held a partial record, such as delivery notes only or a general register that does not identify UgIFT items, and 83 (17.4%) held none. Kagumba Health Centre III in Kamuli kept an asset condition book, a simple practice that other facilities can adopt.

# Recommendations

Recommendation. Facility managers and school governing bodies should keep the local and regional repair arrangements that already work and adopt a fixed routine: a condition check at least every school term in schools and every quarter in health centres, and a full count of UgIFT assets each year. Each facility should keep a condition book or fault list naming each item requiring action, the responsible person and the agreed completion date; the 36 facilities with no repair arrangement and the 80 with no functionality or breakdown record should set these up first.

District health and education offices should review unresolved repairs each quarter and arrange technical assistance, and regional referral hospital workshops should include UgIFT equipment in their scheduled visits. Annual maintenance plans should separate minor repairs, which facilities can meet from Primary Health Care funds or school grants, from specialist and major repairs that need district or national funding, as the experience at Kyankaramata shows, and their costs should be included in the next budget cycle. A repair should count as complete only when the item has been checked and returned to safe use, or formally assigned another outcome.

Recommendation. Facility managers, district health and education officers, engineers and technical teams should prioritise unsafe furniture, electrical concerns and failed equipment needed for essential services. Withdraw unsafe items, obtain technical assessments and verify safe operation after repair. The broken down and not functional assets should be assessed in order of their effect on care and teaching, beginning with clinical equipment and the school furniture that makes up most of the broken down assets; items beyond economic repair should receive a formal disposal decision. At national level, the Office of the Prime Minister should decide on repair or replacement of its three damaged laptops, and Uganda Blood Transfusion Services (UBTS) should repair or replace the six broken blood pressure machines at Arua Regional Blood Bank. Keep damaged assets separate from usable assets awaiting installation so that each receives the appropriate action

Recommendation. District Accounting Officers, engineers, health and education officers and contractors should coordinate outstanding buildings, utilities, furniture and equipment through site-specific completion plans for each of the 115 facilities with works outstanding, starting with the 22 of them that were not yet providing services. Installation should follow confirmation that rooms, power, water and security are ready. Stored assets described as new or in good condition should be issued to the rooms where they are needed, and each asset waiting for power or installation should have a named date for connection and testing. Protect services already operating during construction, and complete testing and signed handover before closing each action.

Recommendation. District health officers, facility managers, suppliers and regional technical teams should provide practical training for staff who use specialist equipment, starting with the health centres that linked idle equipment to a lack of skills, including oxygen equipment users at Bubago and Sop Sop and staff requiring orientation at Avogera. Handover should include a demonstration, basic maintenance guidance and a named route for technical support. Future supply contracts should make on-site demonstration to the staff who will use the equipment a condition of acceptance, and staffing reviews should take account of the equipment each health centre now holds.

Recommendation. Institution asset managers and district finance, health and education offices should engrave verified movable assets with the UgIFT marking and confirm their locations and custodians, starting with hospital equipment, the Ministry of Education and Sports handsets and tablets, and the Lungulu holdings. Assets carrying another marking only should receive the programme identifier at their next check. Resolve the continuing allocation of equipment at Todora, Paraa and Masafu through signed transfer or receipt documentation, bring assets held at district stores to their facilities once rooms are ready, and complete delivery of the items still with suppliers.

The Ministry of Works and Transport should retain the completed tracing record and keep the confirmed custodians and locations current. Losses should be reported and investigated under the public finance rules, and every facility should hold a list of the UgIFT assets it received, showing each item, its engraving and its custodian. Maintain site, ownership and handover records for buildings and land.

Recommendation. The Ministry of Finance, Planning and Economic Development, with the Ministry of Health, the Ministry of Education and Sports and the local governments concerned, should approve a corrected programme list. It should remove or annotate the 18 entries that were not UgIFT facilities in practice, with the reason for each change; link the 4 replaced and 30 renamed entries to one facility identifier, keeping the former names as aliases; record the 3 relocations with signed transfers and receipts; correct the construction status of the 48 entries that differed from the field; and add the 3 confirmed additional beneficiaries. The other 21 names found outside the programme list should be resolved through the same checks of identity, programme approval and asset custody. The corrected list should then guide decisions wherever planned locations differed from what teams found. Appendix F lists every facility concerned.

# Annexures

UgIFT Programme provided assets to other national and subnational agencies that were not directly involved in implementation such as KCCA, MODVA, hospitals and health centres across the country

Movable assets exclude buildings, structures and land. Properly engraved means the UgIFT marking.