# Amanang HC III - facility report

# 1. Identification

| Facility | Amanang HC III |
| --- | --- |
| Type | Health centre |
| Local government | Bukwo District |
| Region / sub-region | Eastern / Elgon |
| Date(s) of visit | 2026-08-24, 2026-08-26 |
| Team members present | Alydo Mary Topista, Nakiwala Doreen, Shadrack |
| Supervisor | Kassim Luminsa |
| Informant interviewed | Not recorded |

# 2. Entry

The visitors' book was photographed here, so the team is signed in on the facility's own record. Nothing about getting in or being allowed to work was raised.

# 3. Condition and status

The four things this exercise sets out to settle. What the visit settled is entered below, what it did not is marked not reported, and nothing here is filled in from anywhere else.

| Dimension | What was established on site |
| --- | --- |
| Ownership | Not reported. No land title, ownership document or ownership statement was recorded for this facility. |
| Functionality | Reported for some items: Bag valve mask(2) 1 not seen |
| Usage / performance | Not reported. |
| Location | Only the facility itself. No room, block or store was recorded against individual assets. |

# 4. Supplied against found

This facility appears on the district delivery note. Of its 27 outpatient lines, 4 were counted here and 23 were not. Supplied and found are kept apart: the figures below are what the note says against what was counted.

| Item | Supplied | Found |
| --- | --- | --- |
| Drip Stand | 3 | 5, recorded as Drip stand |
| Examination Couch | 2 | 4, recorded as Examination couch |
| Examination Light | 2 | not settled - Examination lights LED, Examination light all answer to this line |
| Patient Screen | 3 | 5, recorded as Patient screen |

Counted here but not on that schedule: Bag valve mask, Bench, Delivery bed, Examination light, Examination lights LED, Kangaroo mother care chair, Medical waste bin, Neonatal beds, Non Residential building, Office chair, Oxygen concentrator, Paediatric beds, Pit latrine and wash rooms, Refrigerator, Residential building, Suction apparatus, Water tanks. Some may sit on the maternity schedule, which has not been gone through.

A handwritten equipment handover list is also on file for this facility, in two views. It carries 33 lines with a quantity against each, is dated 15 June 2025, and is signed by the delivering technician, the LC1 chairperson and the health unit management committee chairperson. It records what was handed over. Its lines have not yet been set against what was counted here, and that is carried as an open item.

# 5. Engraving and identification

Not engraved (1). Medical waste bins.

No serial number was recorded against any item here.

# 6. Obsolete, unserviceable or for disposal

These were noted on site, and no others:

Bag valve mask(2) 1 not seen.

Nothing was recommended for disposal in terms.

# 7. Operation and maintenance

Nothing was reported about operation, maintenance or the challenges the facility administration raised. The toolkit's discussion guide - maintenance, functionality records, and how UgIFT support has helped service delivery - was not answered for this facility.

# 8. Queries

Three photographs first recorded at Amanang were recorded again at Kapkoros HC III.

A handwritten equipment handover list of 33 lines for Amanang HC III has not been gone through.

The delivery note's maternity schedule of roughly 44 lines has not been gone through.

The informant discussion guide was not answered for this facility, so questions 1a, 1b, 2, 3 and 4 of the toolkit are outstanding.

The toolkit filled in by hand on site and naming this facility has not come in, so nothing here is verified.