# Busia District - local government report

# 1. Identification

| Local government | Busia District |
| --- | --- |
| Region / sub-region | Eastern / Bukedi |
| Team | Team 13 - Kayongo Tonny, Lydia Nakiganda |
| Supervisor | Kassim Luminsa |
| Supervisor's contact | +256 702 806116 |
| Dates worked | 2026-08-24 to 2026-08-26 |
| Date of submission |  |

# 2. Coverage

| Facility | Type | State | Return | Photographs |
| --- | --- | --- | --- | --- |
| Sikuda Seed Secondary School | School | verified | Incomplete | 96 |
| Sikuda HC III | Health centre | verified | Incomplete | 0 |
| Buwembe HC III | Health centre | verified | Incomplete | 154 |
| Majanji HC III | Health centre | verified | Incomplete | 168 |
| Buwumba HC III | Health centre | verified | Incomplete | 153 |
| Bumunji HC III | Health centre | verified | Incomplete | 99 |
| Dabani | Health centre | pending | No return | 0 |

Allocated 5 - reported on 6 - verified 6. Five of the six worked are on the programme list; Buwumba HC III is on none. Dabani is pending.

Every return above falls short where ownership went unestablished or nothing was counted on the day. Each facility's own report says what else its return lacks.

No photograph of any asset was sent in from Sikuda HC III and Dabani, so the status of every item there rests on the hand-filled register alone.

# 3. The local government record

| Required | Status |
| --- | --- |
| Courtesy call on the CAO or Town Clerk | Part. Three visitors' books signed, none photographed |
| Record of assets held at the district | Present. Four delivery notes of 26 May 2023, reviewed |
| Interviews with the CFO, DEO and DHO | Part. The DEO and two officers of the DHO's office were seen |
| Debrief to the local government | No record. |

# 4. Key findings

Six facilities are verified from hand-filled registers. Sikuda Seed Secondary School and all five health centres worked here filled registers naming each facility.

UgIFT equipment is being moved out of the facilities it was supplied to. Requisition vouchers at Bumunji, Buwembe and Majanji record transfers to Masafu Hospital.

Nothing at any of the six was counted on the day.

Sikuda HC III has a register and no photographs of its assets.

Ownership was assessed nowhere.

# 5. Supplied against found

At Sikuda Seed Secondary School the school's own record was set against a physical count. At the five health centres the hand-filled register is the found side and nothing was counted against it.

# 6. Obsolete, unserviceable or for disposal

Sikuda Seed Secondary School: two school desks broken and a cracked laboratory stool still in use.

Bumunji HC III: an examination couch torn open and a bedside locker with laminate lifting.

Majanji HC III: faulty stethoscopes and a height board in poor condition.

Buwembe HC III: refrigerators out of service and torn outreach bags.

Nothing was listed for disposal.

# 7. Outstanding queries

No photograph of the district visitors' book exists and two designations on the health sheet cannot be read.

The district's four delivery notes came out of a facility, Buwembe holds a fuller record than the district, and the district's asset list was never shared.

Those notes carry 75 lines, name no facility against one of them, and are signed by nobody at either end.

UgIFT equipment is being moved out of the facilities it was supplied to, on the District Health Officer's authority, and no asset record follows it.

The cover block of the school's hand-filled register was not photographed.

The school's books carry 124 laboratory stools against the 118 counted.

The school's register carries three classroom blocks on one sheet and four on another, priced from a district record that is not on file.

Every mark on an asset here is a facility name, so two identical items cannot be told apart anywhere in Busia.

No serial was taken at the school for the cameras, the switch or the standby power units.

Five health centres were verified from hand-filled registers naming each facility, and nothing at any of the five was counted on the day.

Count the equipment room by room at all five verified health centres and set each count against its register and against any delivery note or inventory the facility holds.

The inventories at Majanji HC III and Buwembe HC III are the facilities' own records, verify nothing, and list faulty items nobody has since checked.

The Globe Corporation notes read NIL against most of what was to be delivered to Majanji HC III.

Equipment is delivered and left in its packaging at all four facilities that returned photographs.

Assets given by charities and by a named donor stand among the UgIFT assets and nothing separates them.

Sikuda HC III was verified from its hand-filled register and no photograph of any asset there is on file.

The record on file carries no entry for the hundred and sixty-eight sheets and photographs returned from Majanji HC III.

The Buwembe HC III return came in three days late under no line of writing, so who photographed it and when is not established.

One serial was taken at Buwembe HC III and one at Majanji HC III, and nothing else at either carries a number of its own.

Five things photographed in this district cannot be named from the frames.

Buwumba HC III was worked and verified though it is on no programme list, while Dabani is on the list and has had no visit.

Busia is allocated five facilities and the programme list names six.

The list carries four of these health centres at level II and the district calls them III and II by turns.

The inventory at Buwembe HC III records items to be replaced and a microscope borrowed from Mbehenyi without some parts.

A printed list of UgIFT items at Buwembe HC III carries quantities and a figure of 142,500,000, and the sheet that would name it is missing.

Five UgIFT works at Buwembe HC III carry their own plaques and appear on no record of assets on file.

A debrief was planned for the close of the work here and nothing records that it was held.

# 8. Sign-off

| Verifier | Not signed |
| --- | --- |
| Supervisor | Kassim Luminsa - not signed |
| Supervisor's contact | +256 702 806116 |
| Date of submission |  |