# Buwagogo Seed School - facility report

# 1. Identification

| Facility | Buwagogo Seed School |
| --- | --- |
| Named on the programme list | Buwagogo Seed School |
| Type | School |
| Local government | Manafwa District |
| Region / sub-region | Eastern / Bugisu |
| Date of visit | 2026-09-02 |
| Team members present | Kayongo Tonny, Lydia Nakiganda |
| Informant interviewed | None recorded |
| Supervisor | Kassim Luminsa |
| Supervisor's contact | +256 702 806116 |
| Date of submission |  |

# 2. Entry

On 2 September the team reached Buwagogo Seed Secondary School in Manafwa. A hand-filled register naming the school is on file together with 3 photographs. Lydia Nakiganda is named as verifier on the cover page. A district stores requisition and a school letter on stolen computers are on file with the register.

# 3. Condition and status

The four things the exercise exists to establish. Only what was established on site appears here; the rest is marked as not reported, not guessed.

| Dimension | What was established on site |
| --- | --- |
| Ownership | Not reported. The guide says only the computers have a facility record and the rest is with the contractor. |
| Functionality | Established on the hand-filled register. A school letter of 5 February 2025 reports eight computers stolen from the laboratory. |
| Usage / performance | Partly established. The guide notes access to computers and more learners, and also understaffing, insecurity, short timber in the furniture, delayed commissioning and delayed funds. |
| Location | Recorded on the register. Photographs of boxed ICT were sent in with the acknowledgement that installation by the contractor is still pending. |

# 4. Supplied against found

The hand-filled register is the found side. A stores requisition of 7 March 2024 lists twenty-eight monitors and CPUs, a server, UPS units, a printer, a projector and network gear received pending installation. Nothing was counted on the day against either document.

# 5. Engraving and identification

Not reported beyond what the register marks.

# 6. Obsolete, unserviceable or for disposal

Eight computers were reported stolen, police reference CRB 06/2025. Nothing was listed for disposal.

# 7. Operation and maintenance

The discussion guide was answered. The school uses its own funds for repair and has a committee to report breakdowns.

# 8. Queries

Confirm what of the March 2024 ICT consignment has been installed and what remains boxed.

Establish what was recovered of the eight stolen computers and whether replacement is owed.

Nothing here was counted on the day.

Ownership was not established.