CONSULTANCY SERVICES TO VERIFY AND RECORD ASSETS UNDER THE UGIFT PROGRAMME

REF: MOFPED/UGIFT/CONS/25/26/00015

PROGRESS REPORT 2

SUBMITTED BY:

Plot 31, Bukoto Street

P.O Box 7657, Kampala, Uganda
+256 (0) 39 2000216/0772525235
email: cpa@cpa.ug

# www.cpa.com

September 2026

Table of Contents

1.	INTRODUCTION	1

1.1	Background	1

1.2	Justification of the verification	3

1.3	Objectives of the Assignment	3

1.4	Scope of Work	3

1.5	Expected deliverables	4

2.	PROGRESS ON THE TASKS	5

2.1.	Verification exercise	5

2.2.	Report compilation	6

3.	CHALLENGES FACED	6

4.	OUR PRAYER	8

5.	ANNEXUS	9

5.1.	MDA verification status	9

# INTRODUCTION

## Programme Background

The Uganda Intergovernmental Fiscal Transfers (UgIFT) Program is a government programme implemented through a Program-for-Results (PforR) Launched and aligned with the broader IGFT Reform Programme (2015). UgIFT 1.0 began with US$200 million in FY2017/18, supporting Education and Health, and was later expanded through additional financing of US$300 million, including US$240 million in credit and US$60 million in grants, with US$50 million from the IDA Refugee Support Window, expanding beyond Education and Health to water and Environment and Agriculture (micro-scale irrigation) making the overall funding total of US$500 million.

The Intergovernmental Fiscal Transfer Reform Programme (IGFT RP) was revised in 2020 to align with the Third National Development Plan (2020/21 - 2024/25), and to directly contribute to Four (04) Programmes i.e. Human Capital Development, Public Sector Transformation, Natural Resources, Environment, Climate change, Land and Water Management, and Development Plan Implementation.

The Overall development objective of the UgIFT Programme was to: “Improve the adequacy, equity, and effectiveness of financing and the oversight, management, and delivery of Local Government services in Education, Health, Water and Environment, and Agriculture (micro-scale irrigation), including refugees and their host communities”.

Specifically, the Programme sought to:

- Increase the adequacy and predictability of fiscal transfers to Local Governments for service delivery;

- Improve the equity and transparency of allocation mechanisms through the introduction of formula-based transfers;

- Strengthen performance incentives and accountability systems for Local Governments; and

- Expand access to quality education and health infrastructure, particularly in underserved areas.

The UgIFT Program had four components aimed at strengthening the intergovernmental fiscal transfer system while supporting investments in service delivery infrastructure. These included;

Component 1: Reform of the Intergovernmental Fiscal Transfer System

This supported the design and implementation of a reformed fiscal transfer framework based on objective and transparent allocation criteria. This resulted into introduction of formula-based grants - Revised allocation formulas reflecting population, infrastructure gaps, and service delivery needs

Component 2: Education Infrastructure Development

This component financed the construction and upgrading of education facilities, particularly government secondary schools in underserved sub-counties. This involved Construction of new secondary schools - Classrooms, laboratories, administration blocks, sanitation facilities, and teachers’ houses in the different local governments.

Component 3: Health Infrastructure Development

This supported investments in health facilities to improve access to primary health care services at the local level. The major outputs under the component were construction and upgrading of health centers - Staff accommodation and sanitation facilities.

Component 4: Local Government Performance and Institutional Strengthening

This aimed at Strengthening local government capacity in planning, budgeting, procurement, and infrastructure management. Under this component, Annual local government performance assessments have been undertaken across the 176 Local governments, Capacity building and technical support Strengthened monitoring and reporting systems across the Local governments.

The Programme was implemented through a clearly defined results framework that connected actions and incentives across three levels of government to strengthen service delivery outcomes. The programme came to an end in December 2025 and had accomplished the following outputs under the different components

- Budget Support

- Education: 196 of 259 Seed Schools are complete of which 189 are operational

- Health: 354 of 373 health facility upgrades/new constructions (HC II to HC III) are complete

- Water and Environment: 758 - piped water systems, 5,398- point water sources, 7,082 water supply systems rehabilitated, 325 designs completed, and 256 sanitation facilities in

- Agriculture (Micro-scale Irrigation): Over 6,235 irrigation systems were installed (4,843 hectares under irrigation), 632 irrigation demonstration sites in 135 LGs set up,

- Refugee intervention: 51 primary schools and 35 health facilities in refugee hosting districts (RHD) were transitioned and integrated into the LG service

- Blood banks: Regional Blood Banks in Arua and Hoima were completed, commissioned while Soroti Regional Blood Bank was rehabilitated

- Under grant management

Assets for institutional strengthening and retooling including ICT equipment and; vehicles. The Ministry of Finance planning and Economic development (MoFPED) through PFM Coordination Unit (RCU) manages the Government of Uganda counterpart funding of the programme to support the grant management component of the UgIFT programme. The grant management supports in financing of Central Government actions intended to achieve programme objectives and disbursement linked indicators (DLIs). To this end, MoFPED through RCU supported MDAs to acquire different assets meant to support programme implementation.

## Justification of the verification

The UgIFT programme implementation came to an end on 31st December 2025. As part of the programme closure activities, MoFPED through RCU, carried out an end of programme asset verification exercise to take stock of the assets procured under the programme to help put in place plans to hand them over to government for sustainability purposes. The exercise was conducted by Sejjaaka Kaawaase & Co Certified Public Accountants.

It was conducted at two levels namely; 1) National level Ministries, Departments and Agencies (MDAs) of Government; 2) all the government secondary schools in underserved sub-counties; and health facilities upgrade from HCII to HCIII levels distributed across the country.  At the National level, the verification focused on retooling assets including ICT equipment such as Computers, Tablets and Photocopiers; Furniture (tables, chairs, desks, stools, shelves, wadrobs and cupboards); Motorcycles and Motor vehicles. The verification involved; Verification of the Asset’s Records, Physical and Functional Verification; Data Consolidation and Recommendations

At the central government level, the MDAs that received UgIFT assets were visited for asset verification by the verification teams appointed by the Consultant While at the Local Government level, all the 176 LGs (Districts, Cities and Municipalities) were also visited and the assets verified.

## Objectives of the Assignment

The objective of the assignment was to undertake verification and recording of all assets acquired under the UgIFT Programme. Specifically, the assignment intended to;

- Identify and verify the existence of the assets

- Verify the assets condition and status: specifically, the condition on functionality, usage/performance and location among others

- Assess financial management aspects: residual value of the investments/hardware/tools for purposes of financial reporting for project closure

- List the assets that are obsolete, unserviceable and require disposal

- Develop a computerized database of the investment/hardware/tools to facilitate recording of new deployed assets/investments

- Undertake PFM Assessment on Asset Management practices (including sustainability, Operations and Maintenance) of the UgIFT implementing LGs

## Scope of Work

The assignment was conducted in all selected UgIFT beneficiary institutions distributed across the country and involved the following tasks.

- Verification of the Asset’s Records

- Physical and Functional Verification

- Data Consolidation and Recommendations

- IFMIS Asset Register Update, Integration, and Migration

- PFM Assessment of the UgIFT Asset Management Practices

## Deliverables

Key expected outputs of the consultant include:

(i)	Report with the list and current status of assets acquired under the programmes;

(ii)	An automated up-to-date assets data base of UgIFT Investments across MDALGs;

(iii)	Report on the estimated value of assets under the programme as well as operations and maintenance arrangements;

(iv)	IFMS-Ready Asset Register and Data Migration Report

(v)	Report on functionality of assets relating to systems investments;

(vi)	Report on Assessment of Asset Management Practices, Risks and recommendations

# PROGRESS ON THE TASKS

The inception Phase started with submission of draft inception and presented to the task force team on …. June 2026. A final inception report was completed and report submitted on .…June 2026. This provided inception report included the detailed methodology, the lists of the facilities including schools and Health centres, the National level agencies where the verification exercise covered. Final approval of the inception report was done on …June 2026.

## Verification exercise

- Literature review

The exercise started with review of existing information from the project secretariat. This included the available asset registers at both national and local government level. It involved review of district asset register to understand the recording and registration patterns of the acquired assets in relation to the IFMIS register available at ministry of Finance. This review noted several differences and inconsistencies regarding the components of the asset register across the different MDAs and Local government

- Pilot test verification

Based on the findings, it was necessary for a physical visit to establish and ascertain how these assets are registered. The pilot was undertaken in Wakiso District Local Government and verification done at Buloba Health centre and Sumbwe seed school. This exercise helped in refining the data collection tool and the deployment plan based on experience gained from the pilot.

- National level verification

The National level Physical verification exercise started on 24th July 2026. This covered 15 MDAs including; Ministry of Works and transport (MoWT), Ministry of Education and Sports (MoES), Ministry of Agriculture Animal Industries and Fisheries (MAAIF), Ministry of Health (MoH), Office of the Prime Minister (OPM), Ministry of Water and Environment (MoWE), Ministry of Gender, Labour and Social Development (MoGLSD), Local Government Finance Commission, National Environment Management Authority (NEMA), Public Procurement and Disposal of Assets Authority (PPDA),Office of the Auditor General (OAG), Ministry of Public Service (MoPs), Ministry of lands housing and Urban Development, Ministry of Local Government (MoLG),and Ministry of Finance, Planning and Economic Development (MoFPED). The verification progress for each of the MDAs is indicated in Annex 1 of the report.

- Local Government Verification

This exercise is the last phase of the physical verification exercise and is expected to commence on the 24th August to 11th September 2026. A number of preparatory activities have been accomplished along this phase including the training materials, deployment plans. The training took place between 21st and 22nd August and physical verification started on the 24th of August across Local governments, seed schools, Health centres and Blood banks and concluded on 7th September 2026.

Prior to the actual field visits, the coordination team, from RCU sent out notification to the Local Governments through formal introductory letters. This was followed by the team from SK&CO Certified Public Accountants through telephone calls to notify each of the LGs about the exact date of the verification exercise.

During the field verification, the verification team, held entry meetings with the LG leadership, reviewed the reports with the LG officials, and moved to the facilities where the team carried out a physical verification of the assets. This involved office assets of fixed nature provided to support the programs in the LGs. In the Local governments, the team also took photographic evidence to clearly show status of the assets as supporting evidence during the field visits. This enabled physical and functional verification. However, the physical verification exercise did not include small office equipment like Stapling machines or punching machines and small school laboratory equipment that are disposable.

Additionally, the team the team engaged the administrators/management of the facility to discuss functionality aspects relating to the objectives of establishing the facility, and enlist any operational and maintenance challenges among others.

## Data compilation and Cleaning

From 7th September, 2026 to date, is receiving field data, consolidating, cleaning it and validating all the data from the field. This process involves.

- Data Cleaning & Validation based on outlier identification and correction

- Matching verified physical assets with existing asset registers.

- Documenting all discrepancies: missing assets, unrecorded assets, misclassified assets.

## Report compilation

The team is currently compiling a report of the MDA verification exercise as part of the general deliverable. This exercise includes compilation of an asset register including all verified assets at MDA level. It also involves compilation and analysis of issues relating to asset management among others. This will be followed by a detailed analysis of the assets to indicate functionality of assets relating to systems investments.

Additionally, the cleaned field data will be analysed to generate both statistical and financial reports.

- The statistical analysis will generate information regarding the status of the UgIFT assets including the status of management, operation and maintenance, completed and functionality among others.

- Financial analysis will provide information regarding Financial Valuation. This included indication of current value and remaining useful life for each asset., Assessing residual value based on the depreciation methods and market conditions.

# CHALLENGES FACED

Delays in approvals and clearances of deliverables. The exercise pace was affected by delayed approval of the inception report. Where as the inception was submitted on …June 2026, a formal approval was obtained on …June 2026. This affected progression to the next level of the assignment leading to time loss.

Delays in issuance of introductory letters and communication to the respective MDAs and Local government. Given the sensitivity of the required information, the consultant required prior communication from the project management team and introductory letters to the respective MDAs and Local governments prior to physical visits. This took longer than expected pending the end of financial year activities. The Letters were issues on June ,25th,2026 one month after the commencement of the exercise. This affected the progress of the exercise.

Institutional changes at MDA level. The exercise covers assets from inception of the program since 2019. The institutions have undergone several changes and some have shifted premises. This affected physical verification of assets. During this period, the changes in personnel leading to loss of institutional memory. Hence physical verification at the MDA required several call backs as the MDAs traced for the assets. This also affected the timelines for the exercise.

Delays in payment of milestone deliverables: The exercise experience delays in the payment of the inception milestone. Whereas the consultant has enough resources to start the exercise, including financing of the inception phase activities, the consultant faced challenges facilitating the down stream activities that required large sum of money given the national wide coverage. The consultant anticipated to use the inception payment to finance the physical verification phase which took longer than anticipated. As per the plan, the Local government and the National level verification were supposed to be simultaneously undertaken which never happen. The consult opted to start with the national level exercise based on the available financial resources. This has been substantially done to completion. The Local government exercise will commence immediately the inceprion funds are availed to the consultant.

Inadequate Asset Identification, Tagging and Engraving

A significant proportion of UgIFT-funded equipment and assets had not been adequately labelled, tagged or engraved. This presented a major challenge because many facilities possess similar equipment and furniture supplied through different programmes and funding sources. At some sites, assets had been engraved; however, the identification marks were not sufficiently unique to distinguish individual assets provided by UgIFT.

Difficult terrain and poor physical accessibility of facilities

Physical accessibility presented a significant operational challenge especially for facilities located in areas characterised by difficult terrain and limited transport accessibility such as Bwesumbu HC III, Bwesumbu Seed School, Buhuhira and Kabingo in Kasese District. This led the teams to overshoot the anticipated time for data collection. Additionally, the field team encountered situations where facilities could not be physically accessed especially for schools since it was holiday time.

# OUR PRAYER

Based on the progress so far accomplished and the challenges highlighted under section three, It’s anticipated that the remaining time on the contract of up to 25th September 2026, may not be adequate to complete the task. It’s in respect of this reality that we request the coordination team to give a no cost contract extension by 30 Calendar days to accomplish the assignment.

# ANNEXUS

## MDA verification status

| No | MDA | Status | Notes/remarks/comment |
| --- | --- | --- | --- |
| 1 | Ministry of Works and transport (MoWT) | Verification Completed | MoWT had no UgIFT asset register but the information about the assets was availed through handover reports and physical verification |
| 2 | Ministry of Education and Sports (MoES) | Verification Completed | MoES had no UgIFT asset register but had a soft copy of all the assets and the needed information. The Ministry has a system that aids in the monitoring of the schools attendance and performance Teacher Effectiveness and Learners Assessment (TELA) and this was financed by UgIFT Programme. |
| 3 | Ministry of Agriculture Animal Industries and Fisheries (MAAIF) | Verification Completed | MAAIF had a good record of the Assets but not in the required format. |
| 4 | Ministry of Health (MoH) | Verification Completed | The Ministry had no UgIFT Asset register. |
| 5 | Office of the Prime Minister (OPM) | Verification Completed | OPM did not have a UgIFT Asset register. Currently the Laptops are not in use and the users reported that the machines are of low capacity compared with the tasks to be handled such as performance assessment of Local Government (LGMSD) |
| 6 | Ministry of Water and Environment (MoWE) | 80% Complete | The ministry does not have a UgIFT asset register, it only has a list of assets in hardcopies. They also received new Equipment in the last financial year of which Finance had no record. |
| 7 | MoGLSD | Verification Completed | The Ministry had a UgIFT asset register but not in the required format which they shared with the team. All the assets were functional |
| 8 | Local Government Finance Commission. | Verification Completed | Did not Receive any Asset from UgIFT |
| 9 | NEMA | Verification Completed | The Authority had no UgIFT asset register. All their equipment (3 Laptops & 1heavy duty printer) were not engraved; awaiting for the Ministry of Finance to send a team to engrave them. |
| 10 | PPDA | Verification Completed | The Authority had no UgIFT asset register but the team physically verified the assets and got the list of all items |
| 11 | OAG | Verification Completed | All assets verified |
| 12 | MoPs | Verification Completed | They did not receive any Asset from UgIFT. they were supporting the programme in recruitment of staff. |
| 13 | Ministry of lands | Verification Complete | The Ministry did not have a Ugift Asset Register. They received one survey equipment and 12 motor cycles which were given out to some Local Governments. A list of these and their beneficiaries was provided |
| 14 | MoLG | Verification Completed | The Ministry had a well organised UgIFT asset register. the register included a vehicle which the Ministry of Finance did not have in the records provided to the team. |
| 15 | MoFPED | Verification Completed | The Ministry has a UgIFT Asset register and a consolidated Register for all MDAs that received UgIFT Assets. |