# Manafwa District - review of the record of assets held at the local government

# 1. What the district holds

Two papers naming Buwagogo Seed Secondary School are on file. One is a Manafwa District stores requisition of 7 March 2024 for twenty-eight monitors and CPUs, a server, UPS units, a printer, a projector and network gear, signed as received pending installation by the contractor. The other is a school letter of 5 February 2025 to the Chief Administrative Officer reporting eight computers stolen from the laboratory. Nothing was handed over that names the other five facilities reached in this district.

# 2. What it covers

The two papers cover Buwagogo only, and only its ICT. Butta, Sisuni, Khabutoola, Sibanga Seed School and Bukimanayi HC III have nothing at district level to be checked against.

# 3. Completeness

The district handed over no combined register of its own. The two papers are a stores issue and a theft report, not a holding of all programme assets in Manafwa.

# 4. What it can and cannot establish

Supplied ICT quantities for Buwagogo can be read from the requisition once they are set against what the school holds today. The theft letter gives a police reference and a count of eight computers. The other five facilities cannot be checked against this district until a record naming them is produced.

# 5. Queries

Obtain the district's record of programme assets for all six facilities, or a written statement of what it holds.