# Manafwa District - local government report

# 1. Identification

| Local government | Manafwa District |
| --- | --- |
| Region / sub-region | Eastern / Bugisu |
| Team | Team 13 - Kayongo Tonny, Lydia Nakiganda |
| Supervisor | Kassim Luminsa |
| Supervisor's contact | +256 702 806116 |
| Dates worked | 2026-09-02 to 2026-09-03 |
| Date of submission |  |

# 2. Coverage

| Facility | Type | State | Return | Photographs |
| --- | --- | --- | --- | --- |
| Bukimanayi HC III | Health centre | verified | Incomplete | 0 |
| Khabutoola | School | verified | Incomplete | 0 |
| Buwagogo Seed School | School | verified | Incomplete | 3 |
| Butta | School | verified | Incomplete | 0 |
| Sisuni | School | verified | Incomplete | 3 |
| Sibanga Seed School | School | verified | Incomplete | 84 |

Allocated 6 - reported on 6 - verified 6. All six facilities the programme list names in Manafwa were reached on 2 and 3 September and all six are verified from hand-filled registers.

Every return above falls short where ownership went unestablished or nothing was counted on the day. Each facility's own report says what else its return lacks.

No photograph of any asset was sent in from Bukimanayi HC III, Khabutoola and Butta, so the status of every item there rests on the hand-filled register alone.

# 3. The local government record

| Required | Status |
| --- | --- |
| Courtesy call on the CAO or Town Clerk | No record |
| Record of assets held at the district | Stores requisition and theft letter for Buwagogo only |
| Interviews with the CFO, DEO and DHO | No record |
| Debrief to the local government | No record |

# 4. Key findings

All six facilities are verified from hand-filled registers naming each one.

Butta and Sisuni are still under construction, with the contractor in charge and teachers not yet deployed at Butta.

Khabutoola and Sibanga are not yet handed over to school management.

Computers have been stolen from two of the schools. Eight went from Buwagogo's laboratory on the night of 4 February 2025, police reference CRB 06/2025, and Sibanga records ten monitors and twenty processors gone.

Manafwa produced no combined district register. A stores requisition and a theft letter cover Buwagogo ICT only.

# 5. Supplied against found

All six have hand-filled registers as the found side. A stores requisition lists Buwagogo's ICT pending installation. Nothing was counted at any of the six.

# 6. Obsolete, unserviceable or for disposal

Eight computers are reported stolen at Buwagogo and thirty units at Sibanga. Nothing was listed for disposal at the other four.

# 7. Outstanding queries

Manafwa produced a Buwagogo stores requisition and a theft letter, and nothing covering the other five facilities.

No call at the district offices is recorded for Manafwa.

No officer of Manafwa is named as interviewed.

The programme list carries Bukimanayi HC II and the register names level III.

Butta is still under construction, with the contractor in charge and no teachers deployed yet.

Sisuni is still under construction, has no UgIFT asset record, and ICT and the laboratory are not yet functional.

Khabutoola still has the contractor on site and keeps no functionality records yet.

Sibanga is still under the contractor and the district and has not been handed over to school management.

Buwagogo has a record only for computers; twenty-eight monitors and CPUs were received pending installation.

Eight computers were stolen from Buwagogo's laboratory on the night of 4 February 2025, police reference CRB 06/2025.

Sibanga records ten monitors and twenty processors stolen, with eighteen monitors and eight processors held at the district stores.

No photograph of any asset was sent in from Bukimanayi HC III, Khabutoola or Butta.

Nothing at the six facilities reached in this district was counted on the visit days.

No debrief to Manafwa is recorded.

# 8. Sign-off

| Verifier | Not signed |
| --- | --- |
| Supervisor | Kassim Luminsa - not signed |
| Supervisor's contact | +256 702 806116 |
| Date of submission |  |