# Namboko - facility report

# 1. Identification

| Facility | Namboko |
| --- | --- |
| Named on the programme list | Namboko |
| Type | School |
| Local government | Namisindwa District |
| Region / sub-region | Eastern / Bugisu |
| Date of visit | 2026-09-01 |
| Team members present | Kayongo Tonny, Lydia Nakiganda |
| Informant interviewed | None recorded |
| Supervisor | Kassim Luminsa |
| Supervisor's contact | +256 702 806116 |
| Date of submission |  |

# 2. Entry

On 1 September the team reached Namboko Seed Secondary School in Namisindwa. A hand-filled register naming NAMBOKO SEED SECONDARY SCHOOL is on file together with 118 photographs. Nobody is named as having received the team.

# 3. Condition and status

The four things the exercise exists to establish. Only what was established on site appears here; the rest is marked as not reported, not guessed.

| Dimension | What was established on site |
| --- | --- |
| Ownership | Not reported. |
| Functionality | Established on the hand-filled register. Seventeen chairs, two laboratory stools and some ICT lines are marked non-functional or stolen. |
| Usage / performance | Partly established. The guide says UgIFT improved education service but the school is still under defect liability, lacks fencing and has inadequate science materials. |
| Location | Recorded on the register and shown in photographs of classroom blocks, the laboratory, staff quarters, kitchen, latrines and water tanks. |

# 4. Supplied against found

The hand-filled register is the found side and nothing was counted on the day.

# 5. Engraving and identification

Chairs in the photographs carry NAMBOKO SEED SEC SCH markings. The register records labelled furniture on several lines.

# 6. Obsolete, unserviceable or for disposal

Seventeen chairs and two laboratory stools are broken; stolen monitors and CPUs appear in the ICT remarks.

# 7. Operation and maintenance

The discussion guide was answered. The school is under defect liability, asks for early commissioning and fencing, and says administrators should come early enough.

# 8. Queries

Confirm what the contractor still owes under defect liability.

Fence the school; the guide cites insecurity without it.

Nothing here was counted on the day.

Ownership was not established.