FIELD REPORT ON UgIFT ASSET VERIFICATION

YUMBE DISTRICT

- The CAO was not around but he made clear communications to the DEO and the DHO about our coming early enough.

- We met with the DHO and told us about the health facilities under ugift which were;

- Kerwa health center III

- Mocha health center III

- Lobe health center III,

- Amanyiri health center III

- Nyori health center III

- Lobe health center III was not on the list from ministry but we visited it since the DHO had it in their records.

- Some instruments for amanyiri HC III were at district stores due to limited space at the facility

- We didn’t verify the instruments because they were packed in heavy solid wooden boxes

The DEO had the following schools under ugift program

- Kerwa seed secondary school

- Drajini seed secondary school and

- Lodonga seed secondary school

Some computers for Kerwa and drajini seed ss were at the district offices because th schools did not have complete computer laboratories

KERWA HEALTH CENTER III

The facility didn’t have an asset register but had inventory records

Some assets were engraved and some weren’t engraved

Incharge was new and knew less about the facility

CHALLENGES

The incharge was new and would find hardship identifying assets from ugift given the fact that not all assets were engraved

RRECOMMENDATIONS

Senior inventory management personnel must be maintained at the facility for proper inventory tracking

MOCHA HEALTH CENTER III

The facility kept records of the assets and delivery notes

The assets were not engraved

The incharge was on an annual leave but provided information over phone

CHALLENGES

The records were not well organized so we had to organize them to get accurate records

RECOMMENDATIONS

A professional records person is needed to make proper records and track inventory easily

LOBE HEALTH CENTER III

The facility only has an OPD ward built by ugift which is empty and yet to start functioning

The facility does not receive any equipment from the ugift program

The incharge was new and had scanty information

CHALLENGES

The incharge was new in office and had scanty knowledge about the facility’s full back ground

RECOMMENDATIONS

Clear orientation of the new incharge before handing over office

KERWA SEED SECONDARY SCHOOL

Headteacher was away in Kampala but delivered information over phone

There was a staff who helped us open the rooms for verification

No clear assets records were available, only school inventory records

CHALLENGES

The headteacher was new and wouldn’t give full information

RECOMMENDATIONS

Fully briefing the headteachers about the school and ugift program

AMANYIRI HEALTTH CENTER III

The buildings were not yet in use and for that reason most of the equipment wasn’t picked at the district stores

CHALLENGES

The records were not organized to separate ugift records alone from other assets

RECOMMENDATIONS

Separate asset register should be put in place for ugift assets.

NYORI HEALTH CENTER III

The facility hand over was taking place soon officially

The in charge we found guided us through the facility

CHALLENGES

There was no separate ugift asset register and proper record keeping

RECOMMENDATION

Proper record keeping should be encouraged

DRAJINI SEED SECONDARY SCHOOL

The assets were not engraved

Some of the ICT equipment were in the stores and not in use

CHALLENGES

The school didn’t have proper records kept

RECOMMENDATIONS

Keeping of proper records by the facility should be priotised for inventory tracking

LODONGA SEED SECONDARY SCHOOL

The headteacher complained of the poor quality of chairs supplied by contractors and the tables were too high for students

Some of the work was still pending

CHALLENGES

The facility didn’t possess proper records for the assets supplied

RECOMMENDATIONS

Sensitizing the headteachers of the importance of record keeping