## FIELD REPORT ON UgIFT ASSET VERIFICATION.

## Facility visited: KYANKARAMATA HC III

## Introduction

A field exercise was conducted to verify UGIFT assets in kyankaramata HC III in kyenjojo district. The exercise involved onsite physical verification of all asset acquired under UgIFT program for the period 2018-2025. This was intended to establish the status of the assets and identify any issues requiring follow-up

Process/ methodology.

The team kick started the exercise with a courtesy visit to the office of the Chief administrative officer, kyenjojo district local government where it met with the deputy chief administrative officer and then had an entry meeting with the team in his office. The team present an introductory letter where recommended and forwarded the team to the relevant officers, in charges /head teachers at schools and health centres funded by UGIFT.

After the meeting Chief administrative officer with the team, dispatched to different facilities where KATO CHARLES, went to Kyankaramata hc III.

At Kyankaramata hc III, the incharge had an asset list barked by delivery notes for items received from UGIFT.

The exercise involved physical counting and verification of assets, taking photographic evidence of the available equipment.

The absence of asset registers both at the district offices and health centres slowed down the verification process and some crucial information on asset numbers, life in months could not be obtained.

Un assembled equipment at the health facility made it hard to verify some assets since they were tightly packed in the store.

The newly constructed maternity building and staff house at the facility were leaking and the walls were being affected by dampness which affected the quality of equipment being used in the facility.

Inadequate storage at health centres was also a challenge, to properly store UGIFT assets.

In addition, the facility staff did not know the some of the medical equipment, their functions, and that they were supplied with some equipment that should be used in schools e.g. counting chambers, glucometers were supplied with strip, but they were used up and the facility could not get their replacement from NMS

# Recommendations

The Program implementers should make final payments to the suppliers of medical equipment after receiving confirmation from the end users about the quality of the equipment supplied, and that all equipment has been assembled.

Facility in charge should be involved during the procurement of medical equipment so that issues of over stock and facility needs are catered for.

The glucometers should be replaced since their strips were not available at NMS order platform.