# Tororo District - local government report

# 1. Identification

| Local government | Tororo District |
| --- | --- |
| Region / sub-region | Eastern / Bukedi |
| Team | Team 13 - Kayongo Tonny, Lydia Nakiganda |
| Supervisor | Kassim Luminsa |
| Supervisor's contact | +256 702 806116 |
| Dates worked | 2026-08-27 to 2026-08-31 |
| Date of submission |  |

# 2. Coverage

| Facility | Type | State | Return | Photographs |
| --- | --- | --- | --- | --- |
| Malaba Seed School | School | verified | Incomplete | 147 |
| Namwaya HC III | Health centre | verified | Incomplete | 142 |
| Sop Sop | School | verified | Incomplete | 168 |
| Iyolwa | School | verified | Incomplete | 118 |
| Kamuli HC III | Health centre | verified | Incomplete | 87 |
| Sop Sop HC III | Health centre | verified | Incomplete | 86 |

Allocated 6 - reported on 6 - verified 6. All six facilities on the programme list were reached and all six are verified from hand-filled registers.

Every return above falls short where ownership went unestablished or nothing was counted on the day. Each facility's own report says what else its return lacks.

# 3. The local government record

| Required | Status |
| --- | --- |
| Courtesy call on the CAO or Town Clerk | Present. The Chief Administrative Officer received the team |
| Record of assets held at the district | Part. Seed-school workbook only |
| Interviews with the CFO, DEO and DHO | No record |
| Debrief to the local government | No record |

# 4. Key findings

All six facilities are verified. Malaba Seed School, Sop Sop Seed School, Namwaya HC III, Iyolwa, Kamuli HC III and Sop Sop HC III each hold a hand-filled register naming the facility. The last three registers came in on 2 September.

Tororo handed over a combined seed-school workbook but no health record. Nine hundred and fifty-six asset lines cover Malaba, Sop Sop and Iyolwa; nothing was offered for the three health centres.

Nothing at any facility was counted on the day.

No officer answerable for assets was seen at the district offices.

# 5. Supplied against found

Every facility has a hand-filled register as the found side. Nothing was counted at any of them.

# 6. Obsolete, unserviceable or for disposal

Nothing in this district was named for disposal.

# 7. Outstanding queries

The call on the Chief Administrative Officer opened the work here, and what was said beyond the welcome is not recorded.

No visitors' book was photographed at the office of the Chief Administrative Officer or the Town Clerk.

The District Education Officer was out of the office and the District Health Officer's team was engaged, so neither interview was held.

Tororo handed over a combined seed-school workbook of nine hundred and fifty-six asset lines for Malaba, Sop Sop and Iyolwa, and nothing for the three health centres.

All six facilities reached in Tororo are verified from hand-filled registers naming each facility.

Malaba Seed School's hand-filled register came in without its discussion guide or cover block.

Sop Sop Seed School's hand-filled register came in without its cover block.

The Iyolwa hand-filled register writes NYOLWA SEED SECONDARY SCHOOL against the programme name Iyolwa.

Kamuli HC III's register records five adult beds redistributed to Atangi HC III, one delivery bed to Malaba HC IV and poor-quality tables from the supplier.

Sop Sop HC III's register and informant say much of the equipment delivered is still in the store because staff lack knowledge of how to operate it.

Nothing at any of the six facilities reached in this district was counted on the day.

No debrief has been given to Tororo on what the six facilities showed.

# 8. Sign-off

| Verifier | Not signed |
| --- | --- |
| Supervisor | Kassim Luminsa - not signed |
| Supervisor's contact | +256 702 806116 |
| Date of submission |  |